## Development_Risk_Sample
Record Type | District | Sub-District | Portfolio | Project | Sub-Project | Project Name_x | BU Attributes | Project Status | Risk ID | Date Raised | Last Review | Risk Title | Risk Description | Cause | Effect | Approval Date | Risk Status | Closed Date | Risk Owner | Progress Stage | RIBA Phase | Current Rationale | Current Probability | Target Rationale | Target Probability | Current Risk Score | Current Risk Level | Target Risk Score | Target Risk Level | Current EMV | Target EMV | Current ETV | Target ETV | Exposure | Driver | Stage | Category 1 | Current Band | Category 2 | Category 3 | Category 4 | RBS | Exposure Start | Exposure End | escalation | Project Name_y | Plan ID | High level Description | Response ID | Response Owner | title | status | description | Start Date | Due Date | Days from Due | Response Due | Completed_Closed | Last updated | Planned Cost | Actual Cost | Percent Complete
Project Risk | Residential Valley | South Hub | Hospitality | PRJ-922 | SUB-17 | King Inc | aggregate robust applications | Delayed | RISK-1000 | 2025-12-07 | 2026-03-19 | Delay in material delivery | Contain create notice able civil option. | Feeling common develop also three huge each. | Would girl effect everybody. | 2025-12-12 | Open |  | Christopher Hayes | Design | Technical Design | Collection Republican threat work democratic choice source. | 3 | Her prevent artist culture miss per. | 1 | 11 | High | 8 | Medium | 375988.68 | 117313.12 | 440133.73 | 186630.58 | 210176.31 | Regulatory | Pre-Concept | Design | B | Operational | Internal | Secondary | RBS-560 | 2026-01-28 | 2026-06-22 | Yes | Beck Inc | PLAN-7899 | Partner easy room idea just. | RESP-50077 | Jason Rivera | Mitigation action 1 | Open | Service style government stay space above. | 2026-03-01 | 2026-06-25 | -115 | 2026-06-25 |  | 2026-03-02 11:53 | 3813230.65 | 4313349.07 | 12.3
Project Risk | Residential Valley | South Hub | Hospitality | PRJ-108 | SUB-15 | Stewart, Kent and Hoffman | integrate turn-key systems | Completed | RISK-1001 | 2025-06-12 | 2025-08-07 | Delay in design approval | Type teacher member interesting report. Itself because high mission shoulder life. | Work minute model program his music music from. | Show game century risk eye plant bad process. | 2025-06-13 | Escalated |  | Joseph Hogan | Design | Technical Design | Operation star fine bring painting also. | 3 | Pass reduce information feeling. | 2 | 16 | Critical | 8 | High | 444894.55 | 168518.44 | 171458.42 | 132928.01 | 976976.41 | Design Change | Closeout | Schedule | A | Commercial | Internal | Primary | RBS-488 | 2025-06-20 | 2025-11-23 | Yes | Cruz, Baker and Cunningham | PLAN-6499 | Score maintain wrong keep just memory. | RESP-76083 | Anna Stewart | Mitigation action 2 | Open | Scene end dark case. | 2026-03-01 | 2026-05-23 | -82 | 2026-05-23 |  | 2026-03-02 11:53 | 3594296.44 | 3207364.02 | 5.37
Project Risk | Residential Valley | North Hub | Theme Park | PRJ-430 | SUB-7 | Patel, Gonzalez and Fowler | implement world-class initiatives | Completed | RISK-1002 | 2025-11-07 | 2026-02-07 | Delay in design approval | Task build force. Cut bank memory last. | Audience single his perhaps fly executive. | Detail determine resource bag fast. | 2025-11-30 | Escalated | 2026-05-09 | Susan Rivers | Closeout | Technical Design | Could generation little describe state fast become international. | 3 | Experience meeting happen record. | 3 | 14 | Low | 5 | Medium | 346731.03 | 152674.89 | 166516.92 | 36812.7 | 267054.44 | Design Change | Design | Cost | A | Commercial | Interface | Primary | RBS-356 | 2025-12-13 | 2026-04-18 | Yes | Castro, Baker and Stevens | PLAN-4690 | If ahead mention. | RESP-40661 | Ashley Kim | Mitigation action 3 | Open | Central west list fly range few. Mr activity design may. | 2026-03-01 | 2026-05-07 | -66 | 2026-05-07 | 2026-05-09 | 2026-03-02 11:53 | 2190597.63 | 1975351.79 | 7.8
Project Risk | Central Development | North Hub | Hospitality | PRJ-854 | SUB-19 | Morales and Sons | aggregate front-end methodologies | Delayed | RISK-1003 | 2026-02-11 | 2026-03-13 | Delay in utility relocation | Much my far. Affect political rise wish parent low movie. Unit low son better how house executive. | All yard region sport parent. | Forget president black success within score above rule. | 2026-02-21 | Open | 2026-06-16 | Mark Edwards | Design | Technical Design | My care actually table protect. | 5 | Arrive administration sit Mr western. | 5 | 25 | Critical | 5 | High | 444868.73 | 108123.14 | 64954.35 | 46603.54 | 385217.28 | Regulatory | Pre-Concept | Procurement | B | Technical | Internal | Primary | RBS-349 | 2026-02-14 | 2026-04-06 | No | Compton, Rodriguez and Copeland | PLAN-3402 | Low financial hour main. | RESP-47503 | Jennifer Harris | Mitigation action 4 | Closed | Degree without forget. | 2026-03-01 | 2026-06-05 | -95 | 2026-06-05 | 2026-06-16 | 2026-03-02 11:53 | 2797055.24 | 2612888.26 | 86.95
Project Risk | Central Development | Waterfront | Infrastructure | PRJ-975 | SUB-10 | Ellis Group | cultivate open-source applications | Active | RISK-1004 | 2025-06-11 | 2025-07-28 | Delay in material delivery | Reflect very during rest a activity center. Apply since concern hard Democrat friend. | Adult to push break though why. | Consider environment voice guess. | 2025-06-17 | Open | 2026-06-22 | Laura Smith | Closeout | Construction | Collection upon protect present treatment indeed. | 5 | Yeah never discuss can situation. | 3 | 10 | High | 3 | Low | 162246.24 | 34361.98 | 280047.23 | 114664.61 | 966807.82 | Funding | Closeout | Design | C | Operational | Internal | Primary | RBS-851 | 2025-08-04 | 2025-12-17 | Yes | Bailey-Farrell | PLAN-3435 | Through bad issue. | RESP-87858 | Justin Guerra | Mitigation action 5 | In Progress | Door administration design church true case. | 2026-03-01 | 2026-06-07 | -97 | 2026-06-07 | 2026-06-22 | 2026-03-02 11:53 | 3732625.73 | 3359966.04 | 9.01
Project Risk | Central Development | North Hub | Hospitality | PRJ-165 | SUB-4 | Conway-Ball | transform strategic e-services | On Hold | RISK-1005 | 2025-10-30 | 2025-12-25 | Delay in material delivery | This view speak Republican change back remember. Personal all moment however end challenge personal. Eye everybody prepare entire west. | At space draw player mind than. | Begin player civil recent far big. | 2025-11-25 | Closed | 2026-04-19 | Lisa Foley | Execution | Construction | But beyond manager it authority small which. | 2 | Still eat message training. | 4 | 22 | High | 1 | Critical | 106781.86 | 183712.26 | 423935.64 | 50542.33 | 157541.76 | Supply Chain | Concept | Procurement | C | Technical | External | Primary | RBS-322 | 2025-11-16 | 2026-03-03 | Yes | Simpson Group | PLAN-7188 | Significant meeting road information able performance get edge. | RESP-70782 | Jeffrey Walters | Mitigation action 6 | Open | Treatment quite style production political put ten. Experience worry store weight whether company whom. | 2026-03-01 | 2026-04-04 | -33 | 2026-04-04 | 2026-04-19 | 2026-03-02 11:53 | 941864.87 | 815601.09 | 73.17
Project Risk | Central Development | Waterfront | Mixed Use | PRJ-304 | SUB-5 | Campbell-Gomez | maximize revolutionary niches | Active | RISK-1006 | 2025-10-24 | 2026-02-01 | Delay in material delivery | Help likely away watch girl property. Building boy concern public our identify part. Record environment exist owner list mind rule. | Bank not accept natural. | Memory religious management natural north skill product. | 2025-11-11 | Mitigating | 2026-04-22 | Lori Walters | Concept | Handover | Author size clear everybody successful. | 4 | Style vote community thought civil. | 1 | 24 | High | 10 | Low | 59513.6 | 181307.21 | 179122.26 | 102874.59 | 419742.87 | Contractor Delay | Execution | Design | B | Operational | Interface | Primary | RBS-288 | 2025-11-20 | 2026-02-21 | No | King-Kim | PLAN-9055 | Knowledge half affect already management instead. | RESP-77816 | Erin Warren | Mitigation action 7 | Closed | Wrong part it woman. Season community easy evidence method magazine door who. | 2026-03-01 | 2026-04-12 | -41 | 2026-04-12 | 2026-04-22 | 2026-03-02 11:53 | 1964120.58 | 2291708.79 | 72
Project Risk | Entertainment Zone | Waterfront | Hospitality | PRJ-251 | SUB-14 | White Inc | architect cross-media experiences | On Hold | RISK-1007 | 2025-03-08 | 2025-04-08 | Delay in foundation works | Where yes animal network north soldier. Generation catch oil crime. Determine ground situation apply. | Often part treatment customer president mother. | Human best put blue. | 2025-03-10 | Open | 2026-05-21 | Eileen Joyce | Closeout | Concept | Success reality very policy nice finish radio. | 4 | Though note consumer old total during ago. | 1 | 21 | High | 15 | High | 332018.29 | 50606.29 | 164157.66 | 174721.06 | 904943.61 | Design Change | Design | Stakeholder | B | Operational | External | Secondary | RBS-683 | 2025-03-17 | 2025-05-07 | Yes | Wilson Group | PLAN-1356 | What catch card their position enough. | RESP-67762 | Mark Davis | Mitigation action 8 | Closed | Create various worker resource. | 2026-03-01 | 2026-05-10 | -69 | 2026-05-10 | 2026-05-21 | 2026-03-02 11:53 | 2784784.02 | 2853483.62 | 62.86
Project Risk | Central Development | North Hub | Hospitality | PRJ-486 | SUB-18 | Frederick-Newton | incubate efficient bandwidth | Delayed | RISK-1008 | 2025-09-20 | 2025-10-07 | Delay in utility relocation | Remain whatever glass woman learn. High society major somebody company understand improve movie. Opportunity such month live. | Work cell mission your mother poor pretty. | Door record yard despite. | 2025-09-29 | Closed | 2026-06-01 | Kelsey Christensen | Execution | Concept | Imagine item loss heart everything include similar. | 2 | Onto occur with bill house open. | 4 | 20 | High | 1 | Low | 18684.22 | 138517.89 | 487436 | 42938.41 | 227591.81 | Design Change | Concept | Cost | C | Operational | Internal | Primary | RBS-506 | 2025-10-01 | 2025-12-23 | No | Thompson-Lutz | PLAN-2835 | Pick determine group put husband style audience. | RESP-11196 | Kenneth Wilson | Mitigation action 9 | Closed | Shoulder last produce style. Clearly north try effect late thought. | 2026-03-01 | 2026-05-17 | -76 | 2026-05-17 | 2026-06-01 | 2026-03-02 11:53 | 1978037.48 | 1983389.26 | 42.07
Project Risk | Sports District | Mountain Edge | Infrastructure | PRJ-421 | SUB-7 | Harrison, Martin and Martinez | re-intermediate intuitive markets | Delayed | RISK-1009 | 2025-08-14 | 2025-11-02 | Delay in material delivery | Account up imagine meet. Or customer PM over one. | Song southern already realize. | Likely second feel cover bar compare Congress. | 2025-08-31 | Open |  | Ryan Baker | Closeout | Design | Stand ever chair. | 2 | Modern seek science same. | 1 | 24 | High | 2 | Low | 41403.5 | 56101.8 | 42412.35 | 96022.33 | 666480.46 | Funding | Concept | Cost | B | Technical | Interface | Primary | RBS-176 | 2025-09-06 | 2026-01-10 | No | Harrison, Vasquez and Day | PLAN-5046 | Specific business thought growth son behind. | RESP-90429 | Chase Coleman | Mitigation action 10 | In Progress | Attack leave bed think forward cultural check author. | 2026-03-01 | 2026-06-25 | -115 | 2026-06-25 |  | 2026-03-02 11:53 | 580478.57 | 603105.29 | 46.57
Project Risk | Sports District | South Hub | Mixed Use | PRJ-251 | SUB-1 | Johnson, Pitts and Heath | streamline vertical e-services | Active | RISK-1010 | 2025-05-05 | 2025-05-15 | Delay in utility relocation | Whose design require my cost. Newspaper young anyone. Business well administration. | Goal cost class but move decade as. | How role bag six their sister organization. | 2025-05-20 | Mitigating | 2026-06-26 | Karen Padilla | Execution | Handover | Page enter author tough campaign third. | 2 | Tough reveal if. | 5 | 14 | Critical | 9 | Critical | 275511.26 | 33870.84 | 402930.33 | 62674.73 | 560109.46 | Funding | Pre-Concept | Design | C | Commercial | External | Secondary | RBS-895 | 2025-05-30 | 2025-09-14 | Yes | Phillips, Wagner and Alvarez | PLAN-9642 | On mind during state trial. | RESP-79822 | Jonathan Hodge | Mitigation action 11 | Closed | Box pass wait loss. Forward order job true us finally industry. | 2026-03-01 | 2026-06-21 | -111 | 2026-06-21 | 2026-06-26 | 2026-03-02 11:53 | 2830836.51 | 2935049.81 | 52.64
Project Risk | Sports District | Mountain Edge | Theme Park | PRJ-286 | SUB-15 | Todd, Rivera and Vega | grow granular portals | Completed | RISK-1011 | 2025-12-22 | 2026-03-08 | Delay in material delivery | Recent best situation over national task different. Response east high wear many especially trade. Assume most simply process medical alone police sit. | Nice campaign hair mother. | Yes everything several else. | 2026-01-07 | Closed | 2026-07-05 | Maria Davis | Concept | Handover | Lot next choice total. | 2 | Herself catch line series. | 3 | 11 | Medium | 5 | High | 494760.16 | 172714.91 | 458494.69 | 37920.02 | 835304.73 | Regulatory | Pre-Concept | Schedule | B | Commercial | Internal | Secondary | RBS-978 | 2025-12-25 | 2026-05-21 | Yes | Brown PLC | PLAN-1837 | Want station key guess. | RESP-44382 | Christopher Ho | Mitigation action 12 | Open | Why care clearly note alone. Continue TV dog material. | 2026-03-01 | 2026-06-18 | -108 | 2026-06-18 | 2026-07-05 | 2026-03-02 11:53 | 3096039.16 | 2532740.82 | 22.28
Project Risk | Central Development | North Hub | Theme Park | PRJ-460 | SUB-5 | Hoffman-Williams | benchmark back-end vortals | On Hold | RISK-1012 | 2025-05-20 | 2025-08-30 | Delay in foundation works | Less most myself minute more list pass. Of official focus reality organization professional stuff item. | Low unit structure interest. | Stop wish late. | 2025-05-30 | Escalated |  | Michael Navarro | Closeout | Construction | Box summer others back miss huge bed pick. | 2 | Culture traditional during describe least. | 2 | 23 | Critical | 10 | Medium | 116632.37 | 151925.99 | 121467.68 | 145572.68 | 641356.89 | Supply Chain | Closeout | Schedule | B | Technical | External | Primary | RBS-765 | 2025-05-23 | 2025-10-16 | Yes | Randall, Dunn and Williams | PLAN-8267 | Offer without woman. | RESP-84512 | Michael French | Mitigation action 13 | Closed | Truth TV my case around. It eat PM southern. | 2026-03-01 | 2026-04-30 | -59 | 2026-04-30 |  | 2026-03-02 11:53 | 4114117.53 | 3552212.84 | 94.42
Project Risk | Entertainment Zone | South Hub | Mixed Use | PRJ-447 | SUB-10 | Waller Group | enhance magnetic portals | Delayed | RISK-1013 | 2025-11-16 | 2026-03-11 | Delay in design approval | Turn wall reason environmental art. According education lawyer either tend often. Though capital forward reality free so. | Major specific whole sell recently newspaper. | Several produce attack wish. | 2025-12-10 | Mitigating |  | Christopher Lindsey | Execution | Concept | Hold better rock go structure. | 1 | Very seven never. | 3 | 13 | Critical | 2 | Medium | 295275.99 | 79805.24 | 57980.84 | 139148.54 | 885978.25 | Funding | Closeout | Design | B | Operational | External | Secondary | RBS-157 | 2025-12-06 | 2026-02-03 | Yes | Williams, Mercer and Zhang | PLAN-6237 | Seat oil time house again never there write. | RESP-55119 | Mr. Jacob Williams | Mitigation action 14 | Open | Cost one whatever which all news organization. Whether stand education both under imagine. | 2026-03-01 | 2026-05-12 | -71 | 2026-05-12 |  | 2026-03-02 11:53 | 4050126.92 | 3268345.67 | 21.75
Project Risk | Residential Valley | Waterfront | Theme Park | PRJ-498 | SUB-20 | Wilkinson Inc | morph robust networks | Completed | RISK-1014 | 2025-06-07 | 2025-09-30 | Delay in design approval | Successful memory theory. Hair make eat education know on relationship. Whatever shoulder no through. | Interview give door later material three. | Clear study break anyone continue pay add. | 2025-06-14 | Open |  | Karen Miller | Closeout | Construction | Plan require return bill goal pay middle. | 2 | Whole force language region within treat sport. | 1 | 16 | High | 1 | High | 285350.34 | 149858.65 | 226011.74 | 24134.14 | 595500.97 | Contractor Delay | Concept | Schedule | B | Commercial | Internal | Primary | RBS-735 | 2025-08-03 | 2026-01-15 | Yes | Hatfield PLC | PLAN-8188 | Successful country reduce bag. | RESP-65689 | Kayla Wilson | Mitigation action 15 | Closed | Fire director foreign them friend husband. | 2026-03-01 | 2026-05-01 | -60 | 2026-05-01 |  | 2026-03-02 11:53 | 3796194.82 | 3512733.44 | 23.33
Project Risk | Sports District | Mountain Edge | Infrastructure | PRJ-872 | SUB-3 | Bauer PLC | leverage back-end schemas | Delayed | RISK-1015 | 2025-04-08 | 2025-06-24 | Delay in utility relocation | Strategy happen onto. | Stand degree stop less cost reality Democrat. | Air conference accept air these. | 2025-04-11 | Escalated | 2026-06-15 | Erica Pena | Design | Design | Result play follow threat smile order. | 1 | Green good environmental media evidence read top community. | 4 | 23 | Critical | 13 | Low | 395822.93 | 37962.25 | 478000.51 | 58729.96 | 125684.54 | Contractor Delay | Closeout | Procurement | A | Technical | External | Secondary | RBS-708 | 2025-05-07 | 2025-08-03 | Yes | Skinner, Campbell and Walker | PLAN-6129 | Push happy glass forget rather rich watch town. | RESP-29694 | Lindsey Allen | Mitigation action 16 | In Progress | Establish team phone civil will management. | 2026-03-01 | 2026-06-10 | -100 | 2026-06-10 | 2026-06-15 | 2026-03-02 11:53 | 4395242.12 | 4299658.42 | 73.31
Project Risk | Central Development | Waterfront | Theme Park | PRJ-130 | SUB-19 | Wilkins PLC | monetize cross-platform supply-chains | On Hold | RISK-1016 | 2025-10-22 | 2025-11-15 | Delay in utility relocation | One recognize my specific. | Item second adult social. | Race research person campaign standard action. | 2025-11-10 | Mitigating | 2026-06-09 | Madison Gallagher | Execution | Construction | Child reach during under fly spend. | 5 | Run management instead can a than call. | 1 | 18 | Medium | 14 | Low | 340080.59 | 53389.34 | 312742.66 | 118289.52 | 328599.1 | Supply Chain | Concept | Cost | B | Technical | External | Secondary | RBS-806 | 2025-11-09 | 2026-03-06 | No | Walker, Hall and Gamble | PLAN-6826 | Matter detail section hope most threat direction. | RESP-25890 | Andrew Schultz | Mitigation action 17 | In Progress | Plan southern after. | 2026-03-01 | 2026-05-28 | -87 | 2026-05-28 | 2026-06-09 | 2026-03-02 11:53 | 1596080.33 | 1706610.02 | 57.98
Project Risk | Central Development | Mountain Edge | Theme Park | PRJ-738 | SUB-10 | Green-Henderson | target strategic ROI | Completed | RISK-1017 | 2026-02-03 | 2026-04-19 | Delay in design approval | Miss every money ball often. Significant now must program. Water interview beat leg business guess. | Guess music impact subject friend heavy father. | Role off media race model past report. | 2026-02-04 | Mitigating |  | Dr. Kevin Vasquez MD | Concept | Construction | Election reveal particularly include. | 3 | Later miss hospital think claim structure course. | 1 | 6 | Medium | 2 | Low | 435283.5 | 94934.99 | 445755.41 | 21749.25 | 584526.01 | Funding | Execution | Schedule | C | Commercial | Internal | Primary | RBS-146 | 2026-03-31 | 2026-09-09 | No | Carr-Mcfarland | PLAN-7476 | Interview argue education traditional. | RESP-62235 | Hayden Ferguson | Mitigation action 18 | Closed | Hit beyond later situation. Look age plant stage build site newspaper. | 2026-03-01 | 2026-06-21 | -111 | 2026-06-21 |  | 2026-03-02 11:53 | 4937088.15 | 3961593.67 | 70.49
Project Risk | Central Development | North Hub | Hospitality | PRJ-430 | SUB-11 | Williams Ltd | integrate rich convergence | Active | RISK-1018 | 2025-05-14 | 2025-07-03 | Delay in utility relocation | People control meet color well. Side star wall some Republican. Dinner stuff move physical face majority north. | Almost statement make most boy positive. | Military capital feel citizen. | 2025-06-02 | Escalated |  | Jennifer Bradley | Execution | Concept | Dark nation ahead someone whole top answer. | 5 | Turn war interest artist fear subject girl film. | 2 | 10 | High | 1 | Critical | 135692.77 | 94832.78 | 121373.32 | 171827.42 | 635845.72 | Contractor Delay | Design | Procurement | B | Commercial | Interface | Primary | RBS-960 | 2025-07-13 | 2025-12-23 | No | Hunter-Lopez | PLAN-3174 | Particular behind box contain each development. | RESP-46551 | Leslie Oconnell | Mitigation action 19 | Open | Source new west very five military. | 2026-03-01 | 2026-04-07 | -36 | 2026-04-07 |  | 2026-03-02 11:53 | 3364297.97 | 3898845.5 | 25.22
Project Risk | Sports District | Mountain Edge | Infrastructure | PRJ-561 | SUB-14 | Dunn Group | syndicate seamless web services | Delayed | RISK-1019 | 2025-11-30 | 2026-01-04 | Delay in foundation works | Body star yet my business. According environmental ahead hear collection world. | Last heart factor care official. | Play drop mean. | 2025-12-02 | Closed |  | Christopher Porter | Closeout | Construction | Threat generation low popular. | 5 | Prepare turn cell politics enjoy across standard plant. | 2 | 25 | Low | 4 | Medium | 204068.31 | 147896.25 | 122661.67 | 92772.37 | 311463.38 | Design Change | Pre-Concept | Cost | C | Operational | Internal | Primary | RBS-696 | 2026-01-17 | 2026-05-23 | Yes | Murphy and Sons | PLAN-1924 | Month opportunity security head leg. | RESP-22647 | Christian Dunn | Mitigation action 20 | Open | Ready check health exactly sometimes. | 2026-03-01 | 2026-06-11 | -101 | 2026-06-11 |  | 2026-03-02 11:53 | 3473735.98 | 3522254.33 | 98.17
Project Risk | Entertainment Zone | North Hub | Infrastructure | PRJ-519 | SUB-9 | Rodriguez-Leblanc | orchestrate efficient e-services | Active | RISK-1020 | 2025-12-12 | 2026-04-03 | Delay in design approval | Card marriage difference. Big inside kid. | Believe six special their. | Bit someone plan financial language deal. | 2025-12-31 | Escalated |  | Raymond Wood | Design | Handover | Maybe near military family. | 2 | Next choice animal may necessary contain firm. | 4 | 17 | High | 15 | Low | 68094.08 | 22105.96 | 335285.92 | 67330.6 | 222460.14 | Supply Chain | Design | Cost | A | Technical | External | Secondary | RBS-204 | 2026-01-15 | 2026-03-19 | Yes | Gomez-Lopez | PLAN-7247 | Sign knowledge manager involve create. | RESP-78466 | Diana Morris | Mitigation action 21 | Closed | Tough agency reality. Product anyone building sense nature. | 2026-03-01 | 2026-04-04 | -33 | 2026-04-04 |  | 2026-03-02 11:53 | 1451073.75 | 1564971.09 | 92.53
Project Risk | Central Development | North Hub | Mixed Use | PRJ-525 | SUB-13 | Ferguson-Guzman | target integrated bandwidth | Completed | RISK-1021 | 2025-06-14 | 2025-08-19 | Delay in design approval | Thank candidate positive have scene well recently. Machine season member. Present house interest research. | Throw set business perhaps walk speak between. | Current security political now region pattern despite. | 2025-07-13 | Mitigating |  | Allison Flowers | Concept | Handover | Student key knowledge activity. | 2 | Identify summer woman box pay. | 4 | 8 | High | 1 | Medium | 101652.05 | 109834.31 | 130197.87 | 75042.68 | 313574.22 | Funding | Execution | Design | A | Operational | External | Secondary | RBS-582 | 2025-06-26 | 2025-08-15 | No | Reese-Mills | PLAN-2989 | Job need drop doctor. | RESP-96884 | Scott Anderson | Mitigation action 22 | In Progress | Media big lead when here statement. Mother space win main wonder figure store. | 2026-03-01 | 2026-04-04 | -33 | 2026-04-04 |  | 2026-03-02 11:53 | 550380.27 | 654224.27 | 23.05
Project Risk | Entertainment Zone | South Hub | Hospitality | PRJ-947 | SUB-2 | Anderson LLC | disintermediate vertical e-markets | On Hold | RISK-1022 | 2025-04-13 | 2025-06-16 | Delay in material delivery | Something bag development indicate close. Imagine six news provide two also. | Green recognize issue street resource seat red. | Sometimes smile center anything by. | 2025-04-25 | Escalated |  | Alison Taylor | Pre-Concept | Technical Design | Home far card but final develop form. | 3 | Only wear world produce recent respond direction. | 2 | 23 | High | 20 | Medium | 78554.24 | 128780.27 | 288034.56 | 130295.82 | 617906.91 | Design Change | Execution | Design | A | Commercial | Internal | Secondary | RBS-771 | 2025-05-21 | 2025-10-25 | No | Ware-Rogers | PLAN-1684 | South health night middle property. | RESP-61073 | Sierra Smith | Mitigation action 23 | Open | Language crime rest big government then same. | 2026-03-01 | 2026-06-12 | -102 | 2026-06-12 |  | 2026-03-02 11:53 | 2053353.37 | 1676931.61 | 64.81
Project Risk | Central Development | Mountain Edge | Theme Park | PRJ-356 | SUB-4 | Myers and Sons | maximize interactive communities | Delayed | RISK-1023 | 2025-07-12 | 2025-09-26 | Delay in utility relocation | Hold very talk fine management. Themselves tend weight light. | During pattern where amount on outside. | Game hope arm thought country daughter soon. | 2025-07-14 | Escalated | 2026-06-15 | Lori Dyer | Design | Construction | Industry seven line glass require hot. | 3 | Feeling support into ground. | 2 | 20 | Critical | 10 | Low | 189156.47 | 143224.57 | 20613.02 | 141733.28 | 453699.89 | Contractor Delay | Design | Schedule | A | Technical | Interface | Secondary | RBS-782 | 2025-08-02 | 2025-10-30 | Yes | Ford-Stone | PLAN-5103 | Single generation interview box commercial public. | RESP-29290 | Geoffrey Martinez | Mitigation action 24 | In Progress | Whose image land arrive laugh development. Say speech along participant like last see research. | 2026-03-01 | 2026-06-14 | -104 | 2026-06-14 | 2026-06-15 | 2026-03-02 11:53 | 3976071.52 | 4251407.8 | 70.41
Project Risk | Central Development | Mountain Edge | Mixed Use | PRJ-115 | SUB-20 | Ayala, Munoz and Fernandez | empower extensible e-business | Delayed | RISK-1024 | 2025-05-26 | 2025-07-09 | Delay in design approval | Out public protect dream suffer rest available hot. My free movie kitchen interest. Seven media wide American commercial whatever. | Land senior themselves issue open guy. | Its development customer maintain east while realize. | 2025-06-23 | Mitigating |  | Karen Ward | Concept | Handover | I fly morning door heavy past. | 1 | Enough voice medical least. | 1 | 8 | Low | 4 | Critical | 390616.63 | 141101.48 | 367977.4 | 49676.01 | 915831.35 | Contractor Delay | Closeout | Schedule | A | Commercial | Internal | Primary | RBS-209 | 2025-07-10 | 2025-10-08 | Yes | Holmes-Davis | PLAN-9864 | Support entire back market teach. | RESP-26241 | Lori Benson | Mitigation action 25 | Closed | Director level rest step. Pattern ten nation positive project least. | 2026-03-01 | 2026-06-01 | -91 | 2026-06-01 |  | 2026-03-02 11:53 | 3556693.84 | 3980062.12 | 73.45
Project Risk | Central Development | North Hub | Mixed Use | PRJ-677 | SUB-7 | Wiley-White | iterate intuitive portals | On Hold | RISK-1025 | 2025-06-20 | 2025-08-26 | Delay in design approval | Major its head sing run pattern hair. Within inside interest skill chair week. | Program direction condition rate begin senior score. | Billion table leg page reduce. | 2025-07-15 | Mitigating |  | Alexander Fuller | Execution | Concept | Physical push drug network trip spring best. | 2 | Somebody serious wonder send guy child. | 3 | 24 | Critical | 10 | High | 444105.13 | 148929.77 | 60928.56 | 169044.53 | 127145.26 | Design Change | Execution | Schedule | A | Commercial | Interface | Secondary | RBS-723 | 2025-08-16 | 2025-10-29 | No | Meadows, Wade and Jordan | PLAN-1748 | Maintain budget floor improve recently. | RESP-56850 | Nicholas Simon | Mitigation action 26 | Open | Word technology ability despite movement day. | 2026-03-01 | 2026-04-29 | -58 | 2026-04-29 |  | 2026-03-02 11:53 | 862940.7 | 959356.93 | 89.63
Project Risk | Sports District | Waterfront | Infrastructure | PRJ-311 | SUB-8 | Lee, Carlson and Sims | aggregate distributed markets | On Hold | RISK-1026 | 2026-01-15 | 2026-04-29 | Delay in utility relocation | Bad size bring. Reality community partner. Remember hit market star. | Threat third adult institution visit director. | Pretty stock too turn try north. | 2026-01-30 | Open |  | Summer Kemp | Design | Concept | Impact cost too population degree cover leave. | 4 | Fear many system especially. | 2 | 13 | High | 1 | Low | 212261.48 | 40520.17 | 53453.98 | 198481.57 | 955310.7 | Supply Chain | Concept | Cost | B | Operational | Internal | Secondary | RBS-365 | 2026-02-18 | 2026-04-09 | No | Stanley Inc | PLAN-1756 | Energy key hospital we brother. | RESP-35869 | Diana Graham | Mitigation action 27 | Closed | Media own magazine. | 2026-03-01 | 2026-05-10 | -69 | 2026-05-10 |  | 2026-03-02 11:53 | 1614694.24 | 1569106.47 | 9.89
Project Risk | Sports District | Mountain Edge | Infrastructure | PRJ-649 | SUB-4 | Gentry-Yoder | facilitate cutting-edge e-tailers | Active | RISK-1027 | 2025-11-26 | 2026-01-27 | Delay in utility relocation | Feel nation smile remember really open positive. Sell magazine weight audience. | Attack life serve school support player. | Develop than treat television tonight whose candidate. | 2025-12-08 | Closed |  | Christopher Johnson | Design | Construction | Why world indicate break star quickly child. | 1 | Carry painting through executive. | 3 | 12 | Medium | 4 | Medium | 31657.7 | 70866.16 | 207063.23 | 56850.65 | 707938.11 | Funding | Pre-Concept | Design | A | Technical | Interface | Secondary | RBS-492 | 2025-12-28 | 2026-03-18 | No | Barnes, Patel and Carroll | PLAN-1277 | When president watch lead environmental direction purpose soldier. | RESP-41634 | Dylan Gilbert | Mitigation action 28 | Open | Under measure land. Child certainly life job drive why particularly. | 2026-03-01 | 2026-06-12 | -102 | 2026-06-12 |  | 2026-03-02 11:53 | 713214.67 | 847706.27 | 77.34
Project Risk | Residential Valley | South Hub | Infrastructure | PRJ-434 | SUB-16 | Donovan LLC | disintermediate viral content | On Hold | RISK-1028 | 2025-03-02 | 2025-04-17 | Delay in material delivery | Professor anything opportunity way poor job before. Seat sure conference price. Improve provide write inside control hotel. Keep country two by feeling. | Positive look probably vote her word lead feel. | All unit agent coach. | 2025-03-31 | Mitigating |  | Jon Simpson | Closeout | Technical Design | As record tax admit write court life. | 3 | Prevent summer camera guess degree interview into head. | 5 | 11 | Medium | 2 | Low | 277278.74 | 52773.39 | 315457.32 | 130042.71 | 886754.51 | Supply Chain | Closeout | Design | A | Commercial | External | Secondary | RBS-568 | 2025-03-13 | 2025-08-04 | Yes | Glass Inc | PLAN-6589 | Sport force hope such stock. | RESP-28722 | Alicia Ochoa | Mitigation action 29 | In Progress | Give short leader position long. Five mention blue middle. | 2026-03-01 | 2026-05-28 | -87 | 2026-05-28 |  | 2026-03-02 11:53 | 1509735.65 | 1732560.33 | 22.01
Project Risk | Sports District | North Hub | Mixed Use | PRJ-612 | SUB-13 | Torres, Rogers and Reynolds | re-intermediate out-of-the-box web services | Delayed | RISK-1029 | 2025-03-17 | 2025-05-04 | Delay in material delivery | Wrong when ask experience nearly. Congress improve social around officer sell board. Six instead those phone heart. | Sit first simply production cause mouth treatment feel. | Indeed ask do possible. | 2025-04-09 | Closed |  | Jacqueline Brown | Concept | Design | Role democratic face system. | 1 | Part avoid term trade summer she create. | 5 | 21 | High | 20 | High | 345636.98 | 77669.51 | 134390.28 | 22095.12 | 437869.1 | Regulatory | Closeout | Schedule | B | Commercial | Internal | Secondary | RBS-269 | 2025-03-24 | 2025-07-10 | Yes | French-Houston | PLAN-8079 | Brother economic without smile. | RESP-44262 | Mary Lambert | Mitigation action 30 | Closed | Bank tonight start production. Anything high political country away. | 2026-03-01 | 2026-04-13 | -42 | 2026-04-13 |  | 2026-03-02 11:53 | 343879.58 | 371473.81 | 8.44
Project Risk | Residential Valley | South Hub | Mixed Use | PRJ-960 | SUB-15 | Brown-Moody | synergize cross-platform applications | Active | RISK-1030 | 2025-05-03 | 2025-07-04 | Delay in material delivery | Traditional later near owner daughter. Spring try light draw. Theory performance make. | Own public international program model consumer. | Role heart new early stage. | 2025-05-23 | Mitigating |  | Laura Lee | Design | Concept | Them not name admit. | 3 | Training nearly fact significant food provide seek. | 3 | 8 | High | 3 | Critical | 347574.15 | 165289.32 | 428553.46 | 141066.11 | 656323.35 | Regulatory | Execution | Schedule | B | Technical | Internal | Secondary | RBS-843 | 2025-06-04 | 2025-10-21 | Yes | Gallagher PLC | PLAN-4292 | Again last stage rest. | RESP-69700 | Jimmy Byrd | Mitigation action 31 | In Progress | Half even campaign week age let. World mention college production. | 2026-03-01 | 2026-05-06 | -65 | 2026-05-06 |  | 2026-03-02 11:53 | 1560120.1 | 1689613.21 | 11.73
Project Risk | Residential Valley | South Hub | Theme Park | PRJ-148 | SUB-11 | Garcia, Gomez and Perry | enable extensible convergence | Completed | RISK-1031 | 2025-05-19 | 2025-08-31 | Delay in design approval | Police hope strong game. There cell condition happy how yard dark. Expect many serious bill political life. | Approach better each crime my few. | Really serious lead one. | 2025-05-28 | Closed | 2026-06-05 | Cameron Graham | Design | Concept | Identify sing event plan information well. | 5 | Expert news blue throughout. | 2 | 12 | Low | 2 | Low | 306447.08 | 77694.55 | 17300.73 | 150042.99 | 400263.36 | Design Change | Closeout | Cost | A | Operational | Interface | Secondary | RBS-130 | 2025-05-27 | 2025-09-10 | No | Kelly Inc | PLAN-4793 | For far we certain feel debate smile. | RESP-71387 | Eric Pearson | Mitigation action 32 | Open | Interest suddenly again west class eat. Design draw act worker week fear result training. | 2026-03-01 | 2026-05-24 | -83 | 2026-05-24 | 2026-06-05 | 2026-03-02 11:53 | 2146725.08 | 1942170.18 | 41.98
Project Risk | Entertainment Zone | North Hub | Infrastructure | PRJ-295 | SUB-6 | Vazquez Group | embrace real-time action-items | Completed | RISK-1032 | 2025-08-30 | 2025-12-19 | Delay in foundation works | Policy particularly central point society guy. Team number important research wind. Enough rate available cost short maintain ball general. | Purpose rich too probably citizen cup prove. | Arm case sister prevent join goal. | 2025-09-15 | Open | 2026-05-25 | Shannon Price | Design | Construction | Skin nothing thousand rather reflect. | 1 | Charge scientist difficult ahead. | 5 | 25 | High | 24 | Critical | 435747.29 | 11039.82 | 345570.88 | 113591.87 | 451784.69 | Funding | Pre-Concept | Schedule | B | Commercial | Interface | Secondary | RBS-512 | 2025-09-25 | 2026-01-25 | Yes | Barton-Gonzalez | PLAN-7593 | Daughter our ago. | RESP-46836 | Patricia Dominguez | Mitigation action 33 | Closed | Call production general north west. | 2026-03-01 | 2026-05-12 | -71 | 2026-05-12 | 2026-05-25 | 2026-03-02 11:53 | 2962578.33 | 3010223.26 | 70.87
Project Risk | Sports District | Waterfront | Mixed Use | PRJ-565 | SUB-8 | Floyd and Sons | engage cross-media info-mediaries | Completed | RISK-1033 | 2025-04-08 | 2025-07-15 | Delay in design approval | Grow industry room form bad thank. Their process sound create course laugh win. In support start according information. Organization west season class consumer. | Happen most which ever. | Beyond improve town research next risk operation. | 2025-04-19 | Mitigating |  | Michael Perez | Design | Construction | Argue garden everything drop. | 3 | Peace on impact speech. | 2 | 24 | Low | 20 | High | 423220.94 | 49094.22 | 456241.87 | 105033.5 | 697925.26 | Design Change | Design | Design | B | Operational | External | Primary | RBS-452 | 2025-04-13 | 2025-08-19 | Yes | Figueroa, Jackson and Johnson | PLAN-7207 | Ago future mother eight start street end. | RESP-67249 | Patrick Duncan | Mitigation action 34 | In Progress | Sport that name think. Around from candidate western next American relationship. | 2026-03-01 | 2026-06-25 | -115 | 2026-06-25 |  | 2026-03-02 11:53 | 2634546.01 | 2147188.81 | 70.16
Project Risk | Sports District | Waterfront | Infrastructure | PRJ-397 | SUB-17 | Clements, Morris and Humphrey | syndicate dot-com web services | Delayed | RISK-1034 | 2025-03-23 | 2025-04-08 | Delay in foundation works | Around stand product woman rest. Run forget part doctor how industry. Out ahead approach also all. | Write discussion case heart professor financial cup usually. | Even senior lot these poor than. | 2025-04-06 | Mitigating |  | Kathy Wiggins | Closeout | Technical Design | Individual time foreign can prove buy put. | 1 | Despite drop movie possible certainly politics population. | 1 | 19 | Low | 4 | Medium | 241331 | 68392.21 | 242772.83 | 102495.42 | 783103.11 | Funding | Design | Schedule | C | Operational | External | Secondary | RBS-821 | 2025-05-14 | 2025-09-27 | Yes | Cruz-Price | PLAN-8442 | Trip determine hospital like assume discuss friend. | RESP-59831 | Robert Reese | Mitigation action 35 | In Progress | Yourself general for price network. Style despite result example able research. | 2026-03-01 | 2026-04-04 | -33 | 2026-04-04 |  | 2026-03-02 11:53 | 1637731.26 | 1623965.24 | 9.77
Project Risk | Entertainment Zone | North Hub | Theme Park | PRJ-985 | SUB-13 | Nguyen Inc | evolve extensible schemas | Completed | RISK-1035 | 2025-10-20 | 2026-01-07 | Delay in design approval | Level feeling any like decide. Vote consumer already protect air key go. Manage member learn answer. | Call claim fact exactly together involve likely. | His bag bring ahead prove son. | 2025-11-06 | Escalated | 2026-04-25 | Shawn Gonzalez | Closeout | Concept | Usually natural choice. | 1 | Need five nearly big hundred arrive bed. | 1 | 6 | High | 1 | Critical | 464809.91 | 29709.16 | 300054.13 | 19381.65 | 892748.27 | Regulatory | Execution | Procurement | A | Operational | Interface | Secondary | RBS-829 | 2025-11-03 | 2026-02-05 | No | Cohen-Benton | PLAN-2105 | Ahead green daughter yet many. | RESP-41014 | Judy Murphy | Mitigation action 36 | Open | Despite follow decide response. Least admit large black positive. | 2026-03-01 | 2026-04-17 | -46 | 2026-04-17 | 2026-04-25 | 2026-03-02 11:53 | 4262438.4 | 4972520.21 | 74.02
Project Risk | Central Development | Mountain Edge | Theme Park | PRJ-349 | SUB-7 | Ford Ltd | whiteboard web-enabled e-markets | Active | RISK-1036 | 2026-01-06 | 2026-02-16 | Delay in foundation works | Meet company such point. | Pressure experience myself yes black majority. | Teacher mouth world major economy Congress. | 2026-01-24 | Escalated |  | Michelle Cain | Pre-Concept | Construction | Together director fill him huge break style. | 3 | Agent take food dream. | 5 | 23 | Critical | 19 | High | 424996.57 | 80742.44 | 107669.27 | 48935.38 | 967946.94 | Funding | Design | Cost | C | Commercial | Internal | Primary | RBS-374 | 2026-01-26 | 2026-06-29 | No | Macias, Gomez and Atkinson | PLAN-8584 | Behind agree business without blood. | RESP-82006 | Edward Black PhD | Mitigation action 37 | Closed | North finally stage get cultural. Significant quickly fine type through. | 2026-03-01 | 2026-05-04 | -63 | 2026-05-04 |  | 2026-03-02 11:53 | 2761527.82 | 3229465.41 | 36.25
Project Risk | Residential Valley | South Hub | Infrastructure | PRJ-942 | SUB-10 | Spencer Group | target end-to-end relationships | On Hold | RISK-1037 | 2025-09-02 | 2025-09-30 | Delay in foundation works | Interest program method order fast. Candidate determine another. | Television respond structure education. | None prevent player store challenge why. | 2025-09-14 | Escalated |  | Jacob Bryan | Closeout | Design | Former ready early opportunity bit same. | 2 | Less force measure word. | 4 | 16 | Low | 7 | Low | 194643.55 | 78233.04 | 44155.02 | 44172.67 | 828744.66 | Contractor Delay | Execution | Schedule | C | Technical | Interface | Primary | RBS-696 | 2025-10-05 | 2025-11-05 | Yes | Clay, Kline and Trevino | PLAN-8944 | Strong piece computer relate born sure role heart. | RESP-96182 | Andrea Hunt | Mitigation action 38 | Closed | Language heavy great charge artist ahead stage. That particularly bit economic. | 2026-03-01 | 2026-04-27 | -56 | 2026-04-27 |  | 2026-03-02 11:53 | 931255.87 | 954642.24 | 59.96
Project Risk | Central Development | North Hub | Mixed Use | PRJ-624 | SUB-14 | Smith, Thompson and Cook | strategize real-time deliverables | Completed | RISK-1038 | 2025-10-08 | 2025-12-19 | Delay in material delivery | Those although skin decade look people. Indeed improve everybody sign quality item. | Clearly minute car else check control interest. | Listen product think bit. | 2025-10-14 | Escalated | 2026-05-03 | Tara Zamora | Concept | Handover | Road Democrat room return. | 3 | Top whose ball analysis thought. | 4 | 20 | Medium | 10 | Medium | 226920.33 | 11468.93 | 350648.32 | 132689.71 | 333423.36 | Design Change | Closeout | Schedule | B | Commercial | Interface | Primary | RBS-677 | 2025-10-13 | 2026-03-24 | Yes | Kennedy and Sons | PLAN-9224 | Also particular appear history. | RESP-63464 | Phillip Harmon | Mitigation action 39 | Open | Read inside think question crime wrong. Off painting measure himself though much popular. | 2026-03-01 | 2026-04-19 | -48 | 2026-04-19 | 2026-05-03 | 2026-03-02 11:53 | 3012521.64 | 2707146.23 | 83.2
Project Risk | Sports District | Mountain Edge | Mixed Use | PRJ-253 | SUB-18 | Kaufman-Moran | extend customized experiences | Completed | RISK-1039 | 2025-10-07 | 2026-01-03 | Delay in utility relocation | Choose never bar learn your. Phone threat blue table can degree bed. | Early guess during family upon. | Sense police concern include race former. | 2025-10-11 | Mitigating | 2026-06-25 | Hailey Clark | Design | Design | Might way close coach. | 1 | Middle call measure. | 3 | 12 | High | 8 | Medium | 111895.82 | 146759.54 | 133289.95 | 105263.98 | 542397.85 | Funding | Pre-Concept | Procurement | A | Technical | External | Secondary | RBS-375 | 2025-10-19 | 2026-04-09 | Yes | Gregory-Wood | PLAN-4858 | Coach manage staff dog to effort. | RESP-69880 | Wayne Dixon | Mitigation action 40 | Closed | Challenge peace serious painting him attorney. | 2026-03-01 | 2026-06-05 | -95 | 2026-06-05 | 2026-06-25 | 2026-03-02 11:53 | 4902440.8 | 5681214.41 | 24.14
Project Risk | Entertainment Zone | Waterfront | Hospitality | PRJ-186 | SUB-4 | Patel-Sanders | engage granular portals | Active | RISK-1040 | 2025-07-06 | 2025-07-31 | Delay in utility relocation | May name nor article local. | Somebody wall middle stuff or hard. | Economic business other poor so. | 2025-07-09 | Closed |  | Kimberly Freeman | Execution | Design | Technology short word. | 2 | Civil environmental late discussion subject. | 5 | 13 | Medium | 2 | High | 423240.28 | 32086.32 | 264695.79 | 115278.89 | 653691.74 | Regulatory | Closeout | Schedule | B | Technical | Interface | Primary | RBS-204 | 2025-08-16 | 2025-12-12 | No | Larson and Sons | PLAN-5619 | Believe total interview character young language enter. | RESP-20832 | Samuel Saunders | Mitigation action 41 | Closed | Service evidence begin song. Pass fight return question quality interview. | 2026-03-01 | 2026-05-05 | -64 | 2026-05-05 |  | 2026-03-02 11:53 | 4534808 | 4953961.66 | 96.49
Project Risk | Residential Valley | South Hub | Hospitality | PRJ-323 | SUB-7 | Smith-Mccarthy | leverage bricks-and-clicks experiences | Delayed | RISK-1041 | 2026-02-10 | 2026-05-23 | Delay in design approval | Know choose minute pretty model event. Capital adult the vote single others include speech. Section something director student rate. | Whole generation tonight baby. | Spring policy our boy win concern. | 2026-03-01 | Escalated | 2026-05-02 | Debra Hughes | Design | Design | Carry safe question box. | 5 | West political road but tax. | 1 | 17 | Low | 7 | Critical | 470262.58 | 158545.45 | 247221.25 | 112318.1 | 148609.84 | Design Change | Pre-Concept | Cost | C | Operational | External | Secondary | RBS-866 | 2026-03-18 | 2026-08-10 | Yes | Mcdaniel-Smith | PLAN-1407 | Single despite believe expect. | RESP-68737 | Lisa Mitchell | Mitigation action 42 | Open | Region sport find away technology community hotel. | 2026-03-01 | 2026-04-30 | -59 | 2026-04-30 | 2026-05-02 | 2026-03-02 11:53 | 768435.32 | 682572.78 | 86.43
Project Risk | Residential Valley | Waterfront | Mixed Use | PRJ-569 | SUB-10 | Martinez, Vaughn and Dawson | re-intermediate cross-platform interfaces | Active | RISK-1042 | 2026-01-24 | 2026-05-10 | Delay in material delivery | Every event president religious become. Apply painting face son other similar simply material. | Thought ago prevent produce. | Authority region run think improve institution stay business. | 2026-02-17 | Open | 2026-05-19 | David Gill | Concept | Design | Far seven true line land south. | 5 | Point tough article during place. | 3 | 14 | Low | 11 | Low | 109844.59 | 113999.37 | 193671.73 | 130604.4 | 395256.78 | Contractor Delay | Closeout | Schedule | A | Operational | Internal | Secondary | RBS-998 | 2026-03-01 | 2026-05-26 | Yes | Stewart, Castillo and Newman | PLAN-8426 | Build whom approach thousand area decide. | RESP-69454 | Kevin Simpson | Mitigation action 43 | In Progress | Out late effort above child. Garden take never with parent. | 2026-03-01 | 2026-05-17 | -76 | 2026-05-17 | 2026-05-19 | 2026-03-02 11:53 | 4633220.42 | 4877601.76 | 47.24
Project Risk | Central Development | South Hub | Hospitality | PRJ-834 | SUB-9 | Becker, Smith and Kelly | streamline web-enabled channels | On Hold | RISK-1043 | 2026-01-19 | 2026-03-26 | Delay in material delivery | Student reduce despite front marriage area suggest over. Sing positive firm station firm happen official bad. Within whatever on group believe another. | Level thus provide appear last. | Board budget stop home perform. | 2026-02-05 | Closed |  | Christine Martin | Execution | Concept | Bad person middle example. | 5 | Cause need almost history. | 4 | 7 | Low | 6 | Low | 393594.21 | 126292.85 | 267506.3 | 12910.62 | 581348.26 | Contractor Delay | Concept | Design | A | Commercial | External | Secondary | RBS-520 | 2026-03-16 | 2026-04-21 | Yes | Phillips LLC | PLAN-1128 | Wall water example perhaps service. | RESP-52074 | Billy Floyd | Mitigation action 44 | Open | Current social mother century music. Wish somebody do mean important avoid. | 2026-03-01 | 2026-06-11 | -101 | 2026-06-11 |  | 2026-03-02 11:53 | 1092470.45 | 1065366.9 | 27.63
Project Risk | Entertainment Zone | South Hub | Mixed Use | PRJ-413 | SUB-11 | Watts-Cook | utilize granular users | On Hold | RISK-1044 | 2025-09-17 | 2025-10-11 | Delay in design approval | Yes reflect hour month contain. Memory according second guess into million. | Drive modern cell growth apply. | City season into late. | 2025-10-03 | Closed | 2026-04-25 | Antonio Riley | Concept | Construction | Different since range front. | 1 | Practice hand purpose whole participant leg. | 4 | 5 | Medium | 4 | High | 405403.68 | 172138.99 | 154306.25 | 83798.87 | 532160.89 | Regulatory | Pre-Concept | Schedule | B | Technical | External | Secondary | RBS-648 | 2025-09-22 | 2026-01-06 | Yes | Berry-Turner | PLAN-4552 | Company respond high place. | RESP-36522 | Jason Brown | Mitigation action 45 | In Progress | View sure another answer. | 2026-03-01 | 2026-04-20 | -49 | 2026-04-20 | 2026-04-25 | 2026-03-02 11:53 | 1323012.35 | 1341559.59 | 48.91
Project Risk | Sports District | South Hub | Theme Park | PRJ-119 | SUB-7 | Byrd Ltd | visualize rich interfaces | Completed | RISK-1045 | 2025-07-13 | 2025-10-04 | Delay in material delivery | Could job face last. | Page civil our camera. | Shake return music science art main. | 2025-07-27 | Closed |  | Gregory Massey | Design | Design | Myself admit culture cold source cell now include. | 2 | About model industry. | 1 | 14 | High | 10 | Critical | 124014.08 | 148602.05 | 130986.25 | 136742.52 | 154761.25 | Contractor Delay | Concept | Design | A | Operational | External | Secondary | RBS-849 | 2025-08-20 | 2026-01-20 | Yes | Nguyen, Raymond and Odonnell | PLAN-5716 | Discover bad than true exist painting. | RESP-37101 | Ian Nolan | Mitigation action 46 | In Progress | Certainly partner computer parent matter land development. | 2026-03-01 | 2026-06-05 | -95 | 2026-06-05 |  | 2026-03-02 11:53 | 3888250.88 | 3448939.96 | 79.59
Project Risk | Entertainment Zone | Mountain Edge | Theme Park | PRJ-787 | SUB-13 | Heath Inc | evolve cutting-edge eyeballs | On Hold | RISK-1046 | 2025-09-22 | 2025-12-08 | Delay in design approval | Give energy serve camera knowledge forget. Fire we blue throw budget certain else. | Turn top health guess. | Man bag mother whether. | 2025-10-16 | Open |  | Jody Reid | Pre-Concept | Technical Design | Value relate its. | 4 | Entire shoulder four especially up. | 1 | 12 | High | 10 | High | 457869.22 | 88966.98 | 453199.43 | 116436.39 | 246628.91 | Regulatory | Execution | Design | C | Technical | External | Secondary | RBS-424 | 2025-10-05 | 2026-01-02 | Yes | Brown-Wade | PLAN-6768 | Theory score check. | RESP-22310 | David Shields | Mitigation action 47 | In Progress | Set talk those trip voice. Around rest recognize value. | 2026-03-01 | 2026-05-18 | -77 | 2026-05-18 |  | 2026-03-02 11:53 | 4483888.09 | 4784281 | 85.65
Project Risk | Residential Valley | North Hub | Mixed Use | PRJ-192 | SUB-17 | Pennington, Williams and White | maximize innovative convergence | Delayed | RISK-1047 | 2025-12-31 | 2026-04-23 | Delay in design approval | Candidate ability order prove might place oil. Pretty nearly than yard. Major knowledge action. Look create stand. | Cultural project social information establish agent hot way. | Mention discussion name. | 2026-01-11 | Open | 2026-05-09 | Kevin Rodriguez | Design | Handover | Very manager perhaps among. | 1 | Structure truth weight reduce appear. | 5 | 8 | Medium | 8 | Low | 453263 | 55210.24 | 181146.86 | 146513.71 | 161388.97 | Funding | Concept | Procurement | B | Technical | Internal | Secondary | RBS-200 | 2026-01-06 | 2026-03-10 | No | Hess PLC | PLAN-5060 | Sense raise yeah building. | RESP-87441 | Brandon Luna | Mitigation action 48 | Closed | Foot respond perhaps yeah anything condition small water. | 2026-03-01 | 2026-04-28 | -57 | 2026-04-28 | 2026-05-09 | 2026-03-02 11:53 | 2695802.19 | 2206037.58 | 93.33
Project Risk | Central Development | South Hub | Theme Park | PRJ-464 | SUB-20 | King-Mccann | transform B2C architectures | Active | RISK-1048 | 2026-01-04 | 2026-02-01 | Delay in foundation works | Strong recently life drive fish defense piece. Full find parent deep right major. Reduce Congress mention agent officer base. | Position PM edge. | Republican staff exist senior. | 2026-01-10 | Open | 2026-07-10 | Nancy Barker | Pre-Concept | Technical Design | Decade need recognize boy. | 5 | White exist their name social computer. | 5 | 6 | Medium | 5 | Medium | 117719.99 | 111163.66 | 232202.84 | 20487.85 | 185075.34 | Regulatory | Pre-Concept | Schedule | B | Technical | Interface | Primary | RBS-381 | 2026-01-19 | 2026-07-03 | Yes | Sellers LLC | PLAN-2497 | While popular need think report start west discussion. | RESP-20156 | Andrew Lambert | Mitigation action 49 | Closed | Inside sell sign say get light. Early impact improve bill research direction. | 2026-03-01 | 2026-06-22 | -112 | 2026-06-22 | 2026-07-10 | 2026-03-02 11:53 | 2940721.54 | 3323211.14 | 12.78
Project Risk | Sports District | North Hub | Theme Park | PRJ-608 | SUB-10 | Lamb-Mann | generate 24/365 platforms | Completed | RISK-1049 | 2025-03-31 | 2025-05-09 | Delay in design approval | Bill kind mother artist. Space very within any challenge hope. | Their expert rate customer almost activity. | Us able rule must realize local rise. | 2025-04-21 | Closed | 2026-06-28 | Michael Stanton | Execution | Handover | Three condition analysis himself. | 5 | Unit draw measure trouble last each. | 3 | 22 | Medium | 10 | Critical | 272323.27 | 110464.56 | 27919.46 | 188876.43 | 954268.87 | Design Change | Execution | Stakeholder | A | Operational | Interface | Primary | RBS-465 | 2025-04-09 | 2025-05-26 | No | Hunter-Diaz | PLAN-5133 | Report model style job note box interesting. | RESP-16660 | Andrew Berry | Mitigation action 50 | Closed | Position poor green easy act those world. Sing tonight interest other style detail body. | 2026-03-01 | 2026-06-17 | -107 | 2026-06-17 | 2026-06-28 | 2026-03-02 11:53 | 221049 | 192384.82 | 58.15
Project Risk | Residential Valley | Mountain Edge | Mixed Use | PRJ-740 | SUB-3 | Hall, Davis and Manning | incentivize ubiquitous eyeballs | Delayed | RISK-1050 | 2025-08-27 | 2025-12-07 | Delay in design approval | Discussion laugh knowledge watch drop. | Dark into majority financial will green. | Front shake senior mission happy. | 2025-09-23 | Closed | 2026-06-18 | Claudia Curry | Execution | Design | Rock free focus traditional hour build. | 2 | None air themselves accept traditional fast act bag. | 3 | 15 | High | 4 | High | 387642.05 | 20598.88 | 36247.1 | 149809.2 | 729348.98 | Design Change | Design | Design | B | Technical | Internal | Primary | RBS-620 | 2025-09-15 | 2026-01-31 | No | Adams and Sons | PLAN-1483 | Clearly part central traditional. | RESP-66830 | Joseph Owen | Mitigation action 51 | In Progress | Around win popular. Style ball model involve author. | 2026-03-01 | 2026-06-03 | -93 | 2026-06-03 | 2026-06-18 | 2026-03-02 11:53 | 1032141.86 | 1052134.62 | 20.74
Project Risk | Residential Valley | North Hub | Theme Park | PRJ-661 | SUB-6 | Moody PLC | incubate best-of-breed e-business | On Hold | RISK-1051 | 2025-09-06 | 2025-12-27 | Delay in design approval | Yard people for yard deal important. Most sign road among stay. Reason week arrive up. | Individual consumer animal. | Provide run trouble score include these compare. | 2025-09-15 | Escalated | 2026-06-16 | Jeffrey Cook | Design | Concept | Idea black according develop into offer a yes. | 1 | Peace physical back. | 2 | 21 | Low | 11 | Critical | 223214.33 | 158519.73 | 272816.34 | 48414 | 187806.44 | Funding | Design | Stakeholder | C | Technical | Interface | Secondary | RBS-490 | 2025-10-23 | 2026-04-12 | Yes | Townsend-Smith | PLAN-5789 | Fast everyone population detail her raise film. | RESP-77675 | Mr. Gregory Mitchell | Mitigation action 52 | Open | Build student knowledge there rather. Now respond cultural bill message hospital truth. | 2026-03-01 | 2026-06-12 | -102 | 2026-06-12 | 2026-06-16 | 2026-03-02 11:53 | 3897721.05 | 4250281.44 | 61.75
Project Risk | Sports District | South Hub | Theme Park | PRJ-495 | SUB-20 | Powers Inc | optimize front-end portals | Completed | RISK-1052 | 2025-06-28 | 2025-10-10 | Delay in design approval | Important dream beautiful yourself toward while. Operation others nation pay upon. Market agent in clearly fill huge. | Stock benefit position road beautiful. | Bit owner they phone season author candidate measure. | 2025-07-24 | Closed | 2026-05-22 | Joshua Lowe | Concept | Design | Increase us appear but happy type accept. | 2 | Century choice show suffer party who wish. | 4 | 21 | Critical | 7 | Critical | 211413.95 | 21482.53 | 67811.9 | 77893.39 | 558157.58 | Design Change | Concept | Cost | B | Commercial | Internal | Secondary | RBS-301 | 2025-07-30 | 2025-12-15 | No | Ferguson-Johnson | PLAN-1980 | Drive gas detail laugh music condition. | RESP-18356 | Wendy Davidson | Mitigation action 53 | Open | Civil agreement left left the name vote. Blue run item maybe. | 2026-03-01 | 2026-05-21 | -80 | 2026-05-21 | 2026-05-22 | 2026-03-02 11:53 | 1647886.02 | 1850389.93 | 97.74
Project Risk | Residential Valley | Waterfront | Hospitality | PRJ-475 | SUB-9 | Clark-Baird | incentivize front-end architectures | Completed | RISK-1053 | 2025-11-22 | 2026-02-22 | Delay in design approval | Night itself law quite could movement than. Add reduce dinner commercial heart local feel. | About pretty along finish list increase property. | Smile police thousand will imagine explain. | 2025-12-21 | Mitigating |  | Michael Ortega | Closeout | Design | Plant begin action test. | 4 | Follow finish identify parent my onto list. | 5 | 23 | Medium | 14 | Medium | 417608.19 | 92093.3 | 261310.08 | 7229.53 | 149164.63 | Regulatory | Execution | Stakeholder | A | Commercial | External | Secondary | RBS-433 | 2025-12-20 | 2026-04-13 | No | Brown-George | PLAN-8519 | Drop mind number. | RESP-38054 | Gwendolyn Miller | Mitigation action 54 | Closed | Entire task Mr unit our treat. | 2026-03-01 | 2026-04-21 | -50 | 2026-04-21 |  | 2026-03-02 11:53 | 3499308.5 | 3082028.57 | 25.03
Project Risk | Entertainment Zone | Waterfront | Infrastructure | PRJ-566 | SUB-20 | Hill PLC | disintermediate rich channels | On Hold | RISK-1054 | 2025-04-04 | 2025-07-30 | Delay in foundation works | Agreement war six own thought future. Certain occur feeling need tough already. | Appear stand week administration. | Sea performance medical citizen. | 2025-04-22 | Open | 2026-05-30 | John Davis | Concept | Technical Design | Common need argue chair time school build support. | 4 | Instead among suggest sort owner address finally. | 5 | 21 | High | 15 | Critical | 181593.25 | 75837.35 | 407468.08 | 54792.45 | 202734.97 | Regulatory | Closeout | Design | C | Commercial | External | Primary | RBS-504 | 2025-05-21 | 2025-10-16 | No | Walter, Black and Marsh | PLAN-1981 | Drive station population key. | RESP-88561 | Christine Pruitt | Mitigation action 55 | Closed | Floor consider affect should every. Scientist play trade hear along factor free herself. | 2026-03-01 | 2026-05-24 | -83 | 2026-05-24 | 2026-05-30 | 2026-03-02 11:53 | 1421391.43 | 1663649.95 | 81.62
Project Risk | Central Development | Mountain Edge | Mixed Use | PRJ-500 | SUB-3 | Landry-Herrera | envisioneer scalable systems | Delayed | RISK-1055 | 2025-08-11 | 2025-10-12 | Delay in foundation works | Day authority family mention into. Pick worry cold affect Republican concern. | Same field technology college fact prevent. | Politics light impact back. | 2025-08-30 | Mitigating |  | Katherine Allen | Pre-Concept | Handover | Hard interesting entire several seem grow. | 1 | Type government edge build. | 4 | 22 | Low | 2 | Critical | 103036.29 | 48750.27 | 192986.93 | 141964.53 | 791333.45 | Supply Chain | Design | Schedule | C | Commercial | Internal | Primary | RBS-862 | 2025-09-25 | 2026-03-22 | No | Johnson, Mosley and Larsen | PLAN-5676 | Bed move read respond past professional. | RESP-85945 | Allison Gonzalez | Mitigation action 56 | Open | Whether notice traditional hope fact reach fall. | 2026-03-01 | 2026-05-21 | -80 | 2026-05-21 |  | 2026-03-02 11:53 | 1054906.03 | 928465.63 | 45.47
Project Risk | Entertainment Zone | North Hub | Mixed Use | PRJ-568 | SUB-17 | Warner-Ellis | disintermediate e-business technologies | Completed | RISK-1056 | 2025-09-02 | 2025-11-16 | Delay in design approval | Situation ground real tell building deep choice. | Recent daughter partner she. | Thing tonight prove. | 2025-09-27 | Closed | 2026-04-20 | Robert Mendoza | Closeout | Construction | Tree newspaper those another. | 5 | She though realize against industry always us. | 4 | 22 | High | 2 | Low | 301732.86 | 8167.44 | 163539.62 | 5442.89 | 394796.74 | Contractor Delay | Design | Procurement | B | Technical | Interface | Secondary | RBS-319 | 2025-10-27 | 2025-12-20 | Yes | Johnson-Smith | PLAN-9800 | Number happy TV on newspaper trial. | RESP-18995 | Ashley Huang | Mitigation action 57 | Open | Relate start simply. Mrs paper maintain me particularly outside. | 2026-03-01 | 2026-04-08 | -37 | 2026-04-08 | 2026-04-20 | 2026-03-02 11:53 | 2994348.56 | 2987112.55 | 60.31
Project Risk | Sports District | Waterfront | Theme Park | PRJ-920 | SUB-20 | Jenkins-Walker | re-intermediate seamless niches | On Hold | RISK-1057 | 2025-10-31 | 2026-02-12 | Delay in utility relocation | Top statement market. Lay firm computer carry. Director special value interest. | Technology easy such operation red strong result end. | Leave account art sing economic high senior. | 2025-11-27 | Open | 2026-06-23 | Chelsea Duran | Pre-Concept | Technical Design | Indeed camera gas different interest focus. | 3 | Identify include affect man state. | 3 | 11 | Medium | 3 | Medium | 340492.62 | 142911.32 | 300590.23 | 56014.32 | 977990.36 | Design Change | Pre-Concept | Stakeholder | C | Technical | Internal | Secondary | RBS-816 | 2025-12-10 | 2026-04-21 | No | Frank-Brown | PLAN-1094 | Early catch heavy least eat cell represent agency. | RESP-59707 | Stephanie Rivas | Mitigation action 58 | Closed | Point name total lot important source. Perform necessary opportunity data good include month. | 2026-03-01 | 2026-06-04 | -94 | 2026-06-04 | 2026-06-23 | 2026-03-02 11:53 | 1841736.11 | 2085167.1 | 87.38
Project Risk | Entertainment Zone | Mountain Edge | Infrastructure | PRJ-561 | SUB-13 | Hernandez, Hughes and Smith | exploit holistic applications | Active | RISK-1058 | 2025-03-06 | 2025-03-17 | Delay in foundation works | Think project social newspaper nearly. Improve could former clear certain just. | Ahead beat street season include west record. | Three science direction matter. | 2025-03-25 | Open |  | Lucas Williams | Concept | Concept | Likely let long social national everything. | 1 | Without do trial crime reduce watch. | 5 | 7 | Medium | 5 | High | 21266.3 | 148413.27 | 337491.5 | 36948.32 | 416167.25 | Contractor Delay | Design | Design | A | Operational | External | Primary | RBS-163 | 2025-04-12 | 2025-10-01 | No | Evans-Edwards | PLAN-2717 | Federal firm idea fish voice anyone. | RESP-99510 | Alyssa Phillips | Mitigation action 59 | In Progress | Decide surface born much. Audience citizen between memory. | 2026-03-01 | 2026-04-05 | -34 | 2026-04-05 |  | 2026-03-02 11:53 | 244601.29 | 262455.44 | 87.1
Project Risk | Sports District | South Hub | Infrastructure | PRJ-317 | SUB-11 | Singleton and Sons | transition value-added solutions | Delayed | RISK-1059 | 2025-07-10 | 2025-11-05 | Delay in foundation works | Act option today source course partner. Less including scientist while catch according bank. | Where sing challenge sea require contain. | Tax poor trouble enter million dinner animal. | 2025-08-03 | Closed |  | Natalie Tyler | Concept | Concept | Them meeting bank here have thank. | 2 | If road education also include take campaign easy. | 4 | 14 | High | 12 | Medium | 465942.7 | 13794.81 | 489623.23 | 149516.28 | 127318.59 | Contractor Delay | Execution | Procurement | B | Commercial | Internal | Primary | RBS-210 | 2025-08-24 | 2026-01-11 | No | Williams PLC | PLAN-8315 | Relationship fund amount Congress. | RESP-99135 | Todd Munoz | Mitigation action 60 | Open | Prepare south structure. Economy act likely word television six. | 2026-03-01 | 2026-04-22 | -51 | 2026-04-22 |  | 2026-03-02 11:53 | 734865.6 | 782023.9 | 6.14
Project Risk | Central Development | South Hub | Infrastructure | PRJ-782 | SUB-5 | Melendez LLC | extend B2B portals | Delayed | RISK-1060 | 2025-04-05 | 2025-07-10 | Delay in material delivery | Audience break rest cold. Article discover indeed which fall. | Around discuss herself. | Career difference training admit choice. | 2025-04-22 | Open |  | Debra Salazar | Pre-Concept | Technical Design | Bank value future American. | 5 | Turn billion black mention. | 2 | 17 | Medium | 15 | Low | 362031.14 | 12818.01 | 262601.43 | 63250.79 | 121267.49 | Contractor Delay | Execution | Schedule | C | Technical | Interface | Primary | RBS-236 | 2025-05-15 | 2025-09-17 | No | Smith Ltd | PLAN-7744 | Again enough over suddenly claim other. | RESP-85281 | Gabriel Stewart | Mitigation action 61 | In Progress | Wonder about lose meeting tax. Wear boy yard over. | 2026-03-01 | 2026-04-19 | -48 | 2026-04-19 |  | 2026-03-02 11:53 | 1538721.47 | 1671298.3 | 91.64
Project Risk | Central Development | North Hub | Hospitality | PRJ-400 | SUB-10 | Hall-Diaz | morph extensible content | Delayed | RISK-1061 | 2025-04-07 | 2025-04-28 | Delay in utility relocation | Authority list reveal charge customer cut. | Nearly rule whose mean. | Establish month fund read. | 2025-04-26 | Closed | 2026-04-21 | Sean Mullins | Design | Construction | Deal building figure school. | 4 | Democratic too deep although manager serious cut. | 2 | 13 | Medium | 13 | Medium | 405040.12 | 7722.38 | 139808.44 | 63675.75 | 386141.06 | Regulatory | Closeout | Stakeholder | A | Operational | External | Primary | RBS-497 | 2025-05-25 | 2025-08-03 | Yes | Riley-Bell | PLAN-1516 | Cost before even then cup college list. | RESP-61855 | Kevin Bautista | Mitigation action 62 | Closed | Sit success final reason. Along play energy expect today. | 2026-03-01 | 2026-04-10 | -39 | 2026-04-10 | 2026-04-21 | 2026-03-02 11:53 | 3411806.6 | 3434838.38 | 15.16
Project Risk | Entertainment Zone | Waterfront | Theme Park | PRJ-396 | SUB-4 | Huffman, Anderson and Garcia | re-intermediate virtual paradigms | Active | RISK-1062 | 2026-01-13 | 2026-02-11 | Delay in foundation works | Collection floor program west player hit feeling center. Amount total serious market sell. Of order lawyer across even while together. | Successful doctor front occur cup attention office. | Score happy language owner to keep. | 2026-01-29 | Closed | 2026-05-22 | Stanley Terrell | Concept | Design | Common read evidence once long will. | 1 | Give what major help trip visit significant. | 5 | 18 | High | 15 | High | 449291.75 | 112974.22 | 399283.79 | 66878.48 | 579542.57 | Design Change | Execution | Cost | B | Technical | Interface | Primary | RBS-965 | 2026-01-14 | 2026-05-06 | Yes | Williams Ltd | PLAN-8373 | Land necessary culture rule station author officer prevent. | RESP-62076 | James Shaw | Mitigation action 63 | Closed | Reflect rich will cut agreement two. Much economic try. | 2026-03-01 | 2026-05-08 | -67 | 2026-05-08 | 2026-05-22 | 2026-03-02 11:53 | 1680933 | 1644650.86 | 40.18
Project Risk | Central Development | South Hub | Theme Park | PRJ-240 | SUB-2 | Graham LLC | deliver enterprise vortals | On Hold | RISK-1063 | 2025-08-24 | 2025-11-26 | Delay in design approval | Place usually voice moment fast recently travel. Fish present buy again political way. Until during attorney whom identify likely. | Low represent occur data instead future. | Attack color line attention level consumer. | 2025-09-15 | Mitigating |  | Kim Martin DVM | Execution | Construction | With local central cause high daughter in. | 1 | Idea individual science raise me. | 5 | 5 | High | 1 | High | 85346.76 | 133243.11 | 494203.54 | 83301.58 | 717311.38 | Supply Chain | Closeout | Stakeholder | C | Commercial | Interface | Secondary | RBS-392 | 2025-10-17 | 2026-01-17 | Yes | Thompson-Foster | PLAN-5716 | Customer series fly look however. | RESP-23963 | Patrick Lutz | Mitigation action 64 | Closed | Respond I draw miss. Necessary serve hit clear college. | 2026-03-01 | 2026-05-26 | -85 | 2026-05-26 |  | 2026-03-02 11:53 | 2993053.96 | 2866604.46 | 12.13
Project Risk | Residential Valley | Mountain Edge | Hospitality | PRJ-240 | SUB-6 | Christian-Jackson | reinvent intuitive supply-chains | Active | RISK-1064 | 2025-11-20 | 2026-03-16 | Delay in material delivery | Weight range wall skill age. Season night something find case author. | Same source should reality. | Structure reduce interesting. | 2025-11-25 | Open | 2026-05-23 | Veronica Mcdonald | Closeout | Handover | Run west order stay. | 5 | Lose until its hold film. | 2 | 19 | Low | 19 | Medium | 468185.08 | 174642.59 | 143549.55 | 126183.29 | 636181.21 | Regulatory | Execution | Design | B | Commercial | Internal | Primary | RBS-331 | 2025-12-16 | 2026-01-19 | Yes | Koch Group | PLAN-3832 | Serve while professor security voice. | RESP-88851 | Johnny White | Mitigation action 65 | Closed | Concern individual drug himself interest. | 2026-03-01 | 2026-05-14 | -73 | 2026-05-14 | 2026-05-23 | 2026-03-02 11:53 | 3217960.56 | 2853961.01 | 68.51
Project Risk | Residential Valley | Mountain Edge | Theme Park | PRJ-122 | SUB-15 | Allen-Richards | implement interactive synergies | On Hold | RISK-1065 | 2025-05-15 | 2025-05-21 | Delay in design approval | Coach address generation staff. Indicate tonight civil benefit. Unit might space few meeting. | Benefit media compare accept door. | Half half brother customer candidate war nearly image. | 2025-05-21 | Open | 2026-05-09 | Sarah Dyer | Concept | Handover | Health range effect real movement become man. | 4 | Camera political item clearly rock eat have. | 3 | 14 | High | 9 | High | 344614.66 | 145800.56 | 71665.01 | 139809.69 | 739416.24 | Contractor Delay | Pre-Concept | Design | C | Commercial | External | Primary | RBS-604 | 2025-07-10 | 2025-11-09 | Yes | Taylor LLC | PLAN-7033 | Arm remember car. | RESP-41709 | Kathleen Evans | Mitigation action 66 | In Progress | Study pull least impact into single listen. Call believe benefit American up music. | 2026-03-01 | 2026-04-29 | -58 | 2026-04-29 | 2026-05-09 | 2026-03-02 11:53 | 2565564.83 | 2185947.34 | 25.2
Project Risk | Entertainment Zone | North Hub | Theme Park | PRJ-270 | SUB-3 | Morrison, Whitaker and Jackson | scale enterprise systems | On Hold | RISK-1066 | 2025-09-08 | 2025-11-29 | Delay in foundation works | Size begin book article care lot. Why involve citizen help save doctor state. | Edge wife blue trouble focus part wonder necessary. | Something black store. | 2025-09-10 | Mitigating | 2026-05-12 | Kevin Jones | Concept | Technical Design | Financial form city those. | 4 | Daughter leave point movie spend. | 3 | 22 | Medium | 18 | High | 76832.58 | 96122.41 | 431480.88 | 159909.43 | 935370.29 | Funding | Design | Schedule | B | Operational | External | Primary | RBS-110 | 2025-10-24 | 2025-12-07 | No | Robinson-Henderson | PLAN-6925 | A nice their official be. | RESP-97802 | Margaret Love | Mitigation action 67 | Open | Want police later unit white. Son few road it common. | 2026-03-01 | 2026-05-07 | -66 | 2026-05-07 | 2026-05-12 | 2026-03-02 11:53 | 63268.24 | 69213.63 | 11.53
Project Risk | Residential Valley | South Hub | Theme Park | PRJ-141 | SUB-4 | Donaldson, Davis and Vega | enhance value-added communities | Completed | RISK-1067 | 2025-06-14 | 2025-08-23 | Delay in utility relocation | Someone get security name. | Little teacher goal return learn available young government. | Ten cost international continue pull one wonder eight. | 2025-07-10 | Mitigating | 2026-05-02 | Brent Haley | Concept | Concept | Into him fill newspaper process measure throw. | 5 | Threat break whether indicate gun summer. | 1 | 7 | High | 6 | Low | 193217.59 | 63811.91 | 309046.34 | 156393.57 | 154020.92 | Design Change | Pre-Concept | Schedule | B | Operational | Internal | Primary | RBS-813 | 2025-08-07 | 2025-10-30 | Yes | Fritz, Mendez and Stevenson | PLAN-6555 | Say five physical always heart she thus. | RESP-88297 | Eddie Shepherd | Mitigation action 68 | Closed | Size team just baby recent. Worry do local but hotel benefit. | 2026-03-01 | 2026-05-01 | -60 | 2026-05-01 | 2026-05-02 | 2026-03-02 11:53 | 1300861.75 | 1501204.61 | 41.1
Project Risk | Central Development | South Hub | Infrastructure | PRJ-316 | SUB-6 | Henry, Lawrence and Morton | whiteboard turn-key vortals | Completed | RISK-1068 | 2025-11-18 | 2025-12-31 | Delay in foundation works | Cost address security sister on fire cup build. | Member tree specific different far organization within feel. | Support hand anyone stand. | 2025-12-10 | Escalated |  | Michael Smith | Design | Construction | Night true possible role. | 4 | Find full threat total anything this red. | 4 | 8 | Medium | 3 | High | 451430.62 | 128805.56 | 223335.68 | 107441.15 | 547015.06 | Regulatory | Pre-Concept | Design | B | Operational | Interface | Primary | RBS-357 | 2026-01-09 | 2026-02-25 | No | Frazier, Clark and Berger | PLAN-1535 | Throw safe air seat. | RESP-39362 | Christopher Riggs | Mitigation action 69 | Open | Rich behind including bring. Share beautiful protect financial piece book. | 2026-03-01 | 2026-05-19 | -78 | 2026-05-19 |  | 2026-03-02 11:53 | 488663.54 | 518131.52 | 84.04
Project Risk | Sports District | North Hub | Hospitality | PRJ-829 | SUB-15 | Ramsey, Simpson and Williams | transition sticky content | Active | RISK-1069 | 2025-07-07 | 2025-08-18 | Delay in design approval | Whole professional hair standard according may. Page do dog war shoulder. | Me yet bill production behavior. | Foreign image attorney indeed others health fish really. | 2025-07-21 | Open |  | Rebecca Jordan | Design | Handover | Still back cost argue how adult. | 4 | Both top fly many turn tonight newspaper. | 2 | 11 | Low | 9 | High | 29047.82 | 57647.76 | 64350.35 | 86601.08 | 288265.31 | Supply Chain | Concept | Cost | B | Operational | Interface | Primary | RBS-923 | 2025-08-22 | 2026-02-17 | No | Noble-Rush | PLAN-1679 | By model each create. | RESP-72065 | Robert Green | Mitigation action 70 | Closed | Something people half daughter stand watch television service. Ability population industry nice public body picture. | 2026-03-01 | 2026-06-26 | -116 | 2026-06-26 |  | 2026-03-02 11:53 | 1193683.42 | 1142747.2 | 93.68
Project Risk | Sports District | North Hub | Infrastructure | PRJ-551 | SUB-10 | Baker PLC | drive 24/7 eyeballs | Active | RISK-1070 | 2025-12-18 | 2026-02-05 | Delay in utility relocation | Turn foreign relationship beautiful loss point third. Our central its. Environmental parent form however beat develop to different. | Major field majority dark stop baby black owner. | Simple would bit who. | 2025-12-30 | Escalated | 2026-06-18 | Christina Brown DVM | Execution | Construction | One exactly hope movement team bag suffer important. | 3 | Short any bill likely concern. | 3 | 13 | Medium | 11 | High | 98372.83 | 155538.84 | 269976.38 | 33403.2 | 462470.86 | Supply Chain | Closeout | Stakeholder | B | Commercial | Internal | Secondary | RBS-965 | 2026-02-02 | 2026-06-12 | Yes | Park LLC | PLAN-1225 | Watch give visit. | RESP-33431 | Tammy Martin | Mitigation action 71 | Open | Either community bank leg. | 2026-03-01 | 2026-05-31 | -90 | 2026-05-31 | 2026-06-18 | 2026-03-02 11:53 | 3589134.04 | 3851648.47 | 78.24
Project Risk | Residential Valley | South Hub | Mixed Use | PRJ-154 | SUB-1 | Lloyd, Wilson and Hayden | empower killer solutions | Completed | RISK-1071 | 2025-07-02 | 2025-10-24 | Delay in foundation works | Performance edge participant anything power. House which message throw admit. Activity finally move cost home answer. Woman indicate base firm so computer leave success. | Sure population already suggest whatever ball yet. | Think Mrs next street. | 2025-07-05 | Escalated |  | Terri Washington | Pre-Concept | Design | Republican others size together debate way. | 2 | Resource of bit one first clearly. | 3 | 7 | Medium | 6 | Medium | 279063.17 | 182631.97 | 315496.53 | 132981.53 | 174811.51 | Supply Chain | Concept | Cost | B | Technical | Internal | Primary | RBS-700 | 2025-07-18 | 2025-09-24 | Yes | Schaefer-Bryant | PLAN-8271 | At director Mrs family medical hope. | RESP-42551 | Latasha Hamilton | Mitigation action 72 | Closed | Certain town yourself especially particular military really present. | 2026-03-01 | 2026-06-20 | -110 | 2026-06-20 |  | 2026-03-02 11:53 | 3237684.76 | 2983967.91 | 61.8
Project Risk | Central Development | Waterfront | Mixed Use | PRJ-323 | SUB-20 | Vega-Smith | streamline B2B relationships | Completed | RISK-1072 | 2025-08-21 | 2025-09-08 | Delay in design approval | Letter hundred especially offer international. Say lay here throughout forget break. | Top section anything growth just. | Her article campaign must white. | 2025-09-18 | Open |  | Jessica Berry | Closeout | Construction | Amount study customer worry. | 2 | Dinner like west. | 2 | 16 | Low | 16 | Low | 82210.45 | 90258.81 | 357780.13 | 159695.79 | 263401.71 | Regulatory | Pre-Concept | Cost | A | Operational | Internal | Primary | RBS-392 | 2025-10-04 | 2026-03-27 | No | Boyer-Ferguson | PLAN-2429 | Say often quality five on. | RESP-89912 | Jeffrey Anderson | Mitigation action 73 | Closed | Leg yet management individual dinner. Soldier approach look citizen. | 2026-03-01 | 2026-06-26 | -116 | 2026-06-26 |  | 2026-03-02 11:53 | 4226206.89 | 4073113.8 | 22.4
Project Risk | Residential Valley | Mountain Edge | Infrastructure | PRJ-634 | SUB-15 | Gutierrez LLC | incentivize one-to-one partnerships | On Hold | RISK-1073 | 2025-12-23 | 2026-03-10 | Delay in foundation works | Deep day scientist discuss standard. Right simply off miss case seek. Avoid six evidence receive event. Live sell public crime. | Two down respond rule me lot see. | Out from president us stay best. | 2026-01-08 | Closed | 2026-04-19 | Thomas Collins | Pre-Concept | Design | Anything property serious wish difficult. | 4 | Fund loss medical nothing. | 3 | 5 | High | 1 | High | 372681.56 | 87759.64 | 136071.39 | 9914.19 | 194663.97 | Design Change | Execution | Schedule | C | Technical | External | Primary | RBS-763 | 2026-01-04 | 2026-03-21 | No | Duncan-Salazar | PLAN-6684 | Evidence station economy three all. | RESP-99915 | Courtney Leon | Mitigation action 74 | Closed | Interesting ability collection example might affect food. Start their store friend any son real. | 2026-03-01 | 2026-04-07 | -36 | 2026-04-07 | 2026-04-19 | 2026-03-02 11:53 | 321018.23 | 282119.26 | 80.8
Project Risk | Central Development | Mountain Edge | Hospitality | PRJ-162 | SUB-11 | Stewart, Johnson and Hall | scale user-centric channels | Completed | RISK-1074 | 2025-08-23 | 2025-09-13 | Delay in material delivery | Economy today later including rock strategy certain. There phone street share yes. Effect management guess rise week early decide. | Keep occur art actually relate my. | Time Congress light face should. | 2025-09-20 | Escalated |  | Chris Khan | Execution | Design | House already billion return seat north offer. | 3 | Reality forward fight crime artist. | 2 | 14 | High | 6 | Low | 301164.77 | 43616.69 | 406238.29 | 31712.96 | 309661.04 | Funding | Execution | Design | B | Operational | Interface | Secondary | RBS-821 | 2025-09-24 | 2025-10-24 | No | Landry, Walton and Webb | PLAN-1463 | Wife fish his decide arrive certainly. | RESP-70765 | Stephanie Russell | Mitigation action 75 | Open | Tv evening speak agree with. | 2026-03-01 | 2026-06-04 | -94 | 2026-06-04 |  | 2026-03-02 11:53 | 1051752.28 | 934762.61 | 59.01
Project Risk | Residential Valley | Waterfront | Mixed Use | PRJ-982 | SUB-10 | Long-Thornton | mesh killer convergence | On Hold | RISK-1075 | 2025-06-24 | 2025-08-14 | Delay in material delivery | Me wonder hour. Allow good big pull town. | Special scene social task wish onto change. | Hotel get law service garden page instead. | 2025-07-18 | Escalated |  | Pamela Wells | Pre-Concept | Construction | Travel result open office international. | 3 | Whose play none animal sit eight people. | 3 | 20 | Medium | 5 | Medium | 19710.22 | 199059.08 | 224874.2 | 111459.82 | 175578.97 | Funding | Execution | Design | C | Operational | External | Primary | RBS-966 | 2025-07-02 | 2025-09-01 | Yes | Odonnell, Chavez and Anderson | PLAN-6850 | Share half true know. | RESP-94708 | Kathryn Tucker | Mitigation action 76 | Open | Data go television top. | 2026-03-01 | 2026-05-05 | -64 | 2026-05-05 |  | 2026-03-02 11:53 | 2750829.92 | 2643335.9 | 99.98
Project Risk | Residential Valley | North Hub | Hospitality | PRJ-907 | SUB-5 | Mitchell Ltd | deploy cross-platform info-mediaries | Completed | RISK-1076 | 2026-01-04 | 2026-02-14 | Delay in design approval | Task then miss believe. | Eight stand there. | Event until open business address defense natural water. | 2026-01-20 | Open | 2026-07-03 | Paul Nelson | Closeout | Handover | Party wife single heavy minute remember. | 3 | Behavior color too available loss least. | 3 | 10 | High | 9 | Medium | 20793.04 | 192273.85 | 73379.62 | 5392.74 | 122658.98 | Contractor Delay | Design | Schedule | C | Operational | Interface | Primary | RBS-276 | 2026-02-08 | 2026-07-17 | Yes | Diaz, Wallace and Booth | PLAN-2323 | Between crime training plan per church necessary special. | RESP-15277 | Shirley Boyle | Mitigation action 77 | Open | Bank nor continue month big despite serious. | 2026-03-01 | 2026-06-18 | -108 | 2026-06-18 | 2026-07-03 | 2026-03-02 11:53 | 2711585.48 | 2675937.53 | 19.36
Project Risk | Entertainment Zone | South Hub | Hospitality | PRJ-444 | SUB-19 | Marsh Group | revolutionize innovative e-business | Delayed | RISK-1077 | 2025-09-18 | 2025-11-04 | Delay in design approval | Door PM deal hospital be. Still late admit crime although budget. | Message camera partner situation attorney citizen coach that. | Information gas evidence right. | 2025-09-22 | Closed | 2026-07-09 | Brandon Bailey | Pre-Concept | Technical Design | Stock particular player name evening. | 4 | Toward spend admit. | 4 | 16 | Critical | 8 | Medium | 475320.41 | 108876.74 | 340122.69 | 14248.14 | 456146.8 | Design Change | Design | Procurement | A | Technical | Interface | Secondary | RBS-778 | 2025-10-16 | 2025-12-29 | No | Baker-Adkins | PLAN-6381 | Cut according police same mission history. | RESP-19912 | Joseph Andrews | Mitigation action 78 | Open | Above wonder discover station performance. | 2026-03-01 | 2026-06-27 | -117 | 2026-06-27 | 2026-07-09 | 2026-03-02 11:53 | 2734121.18 | 3173959.46 | 73.88
Project Risk | Entertainment Zone | South Hub | Hospitality | PRJ-408 | SUB-6 | Gilmore-Ward | enable rich supply-chains | Active | RISK-1078 | 2025-06-15 | 2025-07-16 | Delay in foundation works | Over because contain story else worker protect. Blood car painting may. Focus sense only one evidence grow collection put. | Similar wide throw shake interesting place entire. | Agree usually do allow upon. | 2025-07-05 | Open | 2026-06-02 | Gloria Davis | Execution | Concept | Rise result think. | 3 | Affect body test seek. | 5 | 12 | Medium | 11 | Critical | 323722.37 | 96067.74 | 110354.63 | 189163.77 | 780726.13 | Regulatory | Design | Design | B | Operational | External | Secondary | RBS-575 | 2025-06-29 | 2025-11-26 | No | Welch-Hunt | PLAN-3927 | Rule detail morning though create compare our though. | RESP-80358 | Samantha Pierce | Mitigation action 79 | Open | Yet baby face majority. | 2026-03-01 | 2026-05-19 | -78 | 2026-05-19 | 2026-06-02 | 2026-03-02 11:53 | 3478599.19 | 3721546.6 | 35.19
Project Risk | Entertainment Zone | Mountain Edge | Mixed Use | PRJ-466 | SUB-7 | Bailey-Thornton | redefine next-generation synergies | Active | RISK-1079 | 2025-07-13 | 2025-08-27 | Delay in foundation works | Four report sense energy especially improve indeed. Cultural same great sell form. | Along quickly employee especially factor effort capital city. | Like worker black without attorney rock. | 2025-07-20 | Closed |  | Angela Parker | Pre-Concept | Construction | Different create chair step focus. | 1 | Focus professor task. | 5 | 22 | High | 4 | Low | 490381.79 | 68677.6 | 371730.08 | 64791.42 | 110655.88 | Contractor Delay | Pre-Concept | Design | B | Technical | Interface | Secondary | RBS-926 | 2025-08-06 | 2025-11-03 | No | Adams, Marquez and White | PLAN-2504 | Coach student challenge score stand TV. | RESP-83957 | Robert Ruiz | Mitigation action 80 | Closed | Office north next body job in. | 2026-03-01 | 2026-04-08 | -37 | 2026-04-08 |  | 2026-03-02 11:53 | 900345.06 | 813521.93 | 95.95
Project Risk | Entertainment Zone | Mountain Edge | Mixed Use | PRJ-181 | SUB-5 | Pham-Foley | leverage world-class markets | Active | RISK-1080 | 2025-06-14 | 2025-08-11 | Delay in foundation works | Animal mention forward drug lot. Community group note early exactly together drug. Increase relationship great rock. | East claim draw heart material color. | Away happen form meet authority great half may. | 2025-06-22 | Open | 2026-04-13 | Tricia Reyes | Pre-Concept | Design | Push phone between professional baby so. | 2 | He phone believe beat present high many. | 5 | 18 | Medium | 6 | Critical | 465709.24 | 166624.93 | 172250.62 | 113165.59 | 624293.46 | Design Change | Design | Cost | A | Commercial | External | Secondary | RBS-902 | 2025-07-25 | 2025-10-03 | Yes | Gibson-Lewis | PLAN-8144 | Already trade ago school. | RESP-80825 | Samuel Perez | Mitigation action 81 | In Progress | Sport magazine wait film eat. Source federal yet between weight. | 2026-03-01 | 2026-04-12 | -41 | 2026-04-12 | 2026-04-13 | 2026-03-02 11:53 | 4996175.21 | 5171470.96 | 55.54
Project Risk | Central Development | North Hub | Mixed Use | PRJ-393 | SUB-11 | Thomas Group | leverage one-to-one e-commerce | Delayed | RISK-1081 | 2025-07-04 | 2025-10-06 | Delay in material delivery | Boy truth performance amount open itself. | Rate player account read final. | Increase director front difficult practice gas accept start. | 2025-07-05 | Escalated | 2026-06-09 | Evan Anderson | Pre-Concept | Construction | Amount cost student sister. | 3 | Off scene hold middle if citizen stock. | 5 | 25 | Low | 21 | High | 298887.48 | 55870.68 | 349734.6 | 77677.2 | 394665.35 | Funding | Design | Cost | B | Commercial | Internal | Secondary | RBS-673 | 2025-08-30 | 2025-12-26 | Yes | Castro, Stewart and Woods | PLAN-7913 | Rock responsibility possible. | RESP-94160 | Jennifer Brown | Mitigation action 82 | Open | Idea kind stop on quite. Keep south become. | 2026-03-01 | 2026-06-05 | -95 | 2026-06-05 | 2026-06-09 | 2026-03-02 11:53 | 4538673.79 | 4139552.75 | 72.59
Project Risk | Sports District | Waterfront | Infrastructure | PRJ-841 | SUB-14 | Palmer-Wells | repurpose 24/7 architectures | Delayed | RISK-1082 | 2025-04-30 | 2025-08-08 | Delay in material delivery | Listen up throughout car buy memory manage. | Eye window able something would century final. | Gun appear authority painting point visit customer support. | 2025-05-01 | Escalated | 2026-06-30 | John Griffin | Execution | Concept | Speak present stock even walk father. | 4 | Head physical laugh great budget serve seven bar. | 2 | 7 | Critical | 1 | Medium | 298526.61 | 111993.86 | 85946.95 | 117333.45 | 106855.91 | Supply Chain | Design | Cost | C | Operational | Interface | Primary | RBS-338 | 2025-05-23 | 2025-09-25 | Yes | Williams, Duncan and Williams | PLAN-4432 | Former product cold federal season statement. | RESP-58416 | Madeline Maldonado | Mitigation action 83 | Open | Form front new out yeah way. Impact camera hair. | 2026-03-01 | 2026-06-19 | -109 | 2026-06-19 | 2026-06-30 | 2026-03-02 11:53 | 314385.17 | 363096.98 | 82.86
Project Risk | Sports District | Mountain Edge | Hospitality | PRJ-449 | SUB-16 | Richardson-Jones | empower rich content | Active | RISK-1083 | 2025-11-05 | 2025-11-16 | Delay in material delivery | Perhaps PM operation simple economic before general. | Culture debate worry drive. | Home ability east mouth ok much. | 2025-11-07 | Escalated | 2026-04-23 | Caitlin Mathis | Pre-Concept | Handover | Give green finish. | 1 | Standard inside traditional rest. | 3 | 5 | Medium | 2 | Medium | 221160.49 | 190215.6 | 429694.12 | 129661.42 | 517073.61 | Funding | Pre-Concept | Stakeholder | A | Technical | Internal | Primary | RBS-869 | 2025-11-14 | 2026-02-28 | No | Haley Ltd | PLAN-6461 | Involve business usually talk body. | RESP-36491 | Renee Walker | Mitigation action 84 | Closed | At use bed official guess. | 2026-03-01 | 2026-04-17 | -46 | 2026-04-17 | 2026-04-23 | 2026-03-02 11:53 | 4687390.19 | 5561560.33 | 28.74
Project Risk | Sports District | South Hub | Mixed Use | PRJ-530 | SUB-12 | Austin, Jimenez and Williams | morph transparent infrastructures | Active | RISK-1084 | 2025-04-09 | 2025-06-08 | Delay in utility relocation | As response account past. Reality participant up activity whatever another defense. | Defense event letter support meeting fight. | Night western around perform no road democratic off. | 2025-04-19 | Mitigating | 2026-05-30 | Mark Baker | Closeout | Construction | News next state family church skill draw. | 3 | Property easy pick itself attack treatment. | 1 | 10 | Critical | 6 | Critical | 152980.8 | 68980.94 | 42348.6 | 35604.36 | 731618.76 | Contractor Delay | Concept | Schedule | B | Commercial | Interface | Primary | RBS-597 | 2025-05-05 | 2025-06-10 | Yes | Patel PLC | PLAN-4522 | Man type base clear. | RESP-59753 | Breanna Mills | Mitigation action 85 | Closed | Phone floor ability necessary trouble. | 2026-03-01 | 2026-05-10 | -69 | 2026-05-10 | 2026-05-30 | 2026-03-02 11:53 | 954997.28 | 1130721.8 | 78
Project Risk | Central Development | Mountain Edge | Hospitality | PRJ-420 | SUB-7 | Smith-Martinez | mesh back-end mindshare | On Hold | RISK-1085 | 2025-03-01 | 2025-03-16 | Delay in material delivery | Education analysis PM cover step probably stay no. Ask husband chance staff live second less. South activity everyone society factor. Fact course thus establish pretty. | Development bring story near nothing get. | Star senior interest soon story wind performance wonder. | 2025-03-10 | Mitigating | 2026-06-03 | Sabrina James | Execution | Handover | Box ask myself organization operation. | 2 | Deal wife onto low choice upon ask. | 2 | 6 | Medium | 5 | Medium | 426755.95 | 193413.45 | 344740.21 | 31674.94 | 157946.21 | Funding | Closeout | Cost | C | Commercial | Internal | Primary | RBS-644 | 2025-04-19 | 2025-05-22 | No | Combs LLC | PLAN-5653 | Beyond big bed state. | RESP-64268 | Thomas Roberts | Mitigation action 86 | In Progress | Page book positive address. Party whole speech. | 2026-03-01 | 2026-05-15 | -74 | 2026-05-15 | 2026-06-03 | 2026-03-02 11:53 | 1402105.89 | 1604268.71 | 84.41
Project Risk | Central Development | Waterfront | Infrastructure | PRJ-544 | SUB-17 | Edwards, Johns and Stone | engage magnetic technologies | Active | RISK-1086 | 2025-03-29 | 2025-05-08 | Delay in utility relocation | Them history hair security must. Politics various consider. | Kind development responsibility discover. | Sign my another see town. | 2025-03-31 | Open | 2026-06-09 | Traci Patrick | Pre-Concept | Construction | Suddenly fund seek above job race themselves. | 4 | Dream language past anything. | 3 | 10 | Medium | 9 | Critical | 301261.65 | 102644.56 | 128061.68 | 94100.45 | 196525.93 | Supply Chain | Execution | Procurement | A | Operational | Internal | Primary | RBS-242 | 2025-04-01 | 2025-06-12 | No | Perez Inc | PLAN-9633 | Figure quality lawyer agreement plan whose. | RESP-15507 | Dustin Coffey | Mitigation action 87 | Closed | Work anyone play stay current. Understand collection federal quickly physical figure national memory. | 2026-03-01 | 2026-06-02 | -92 | 2026-06-02 | 2026-06-09 | 2026-03-02 11:53 | 1941429.74 | 1633719.97 | 29.18
Project Risk | Entertainment Zone | North Hub | Theme Park | PRJ-260 | SUB-17 | Roman-Bailey | whiteboard leading-edge info-mediaries | Active | RISK-1087 | 2025-06-06 | 2025-07-05 | Delay in material delivery | Performance family door interest. Grow energy my instead myself catch maintain. Long politics five movie memory drug. | Family into baby after inside. | Guy thank near something while. | 2025-06-23 | Escalated | 2026-04-25 | Mrs. Annette Jones DDS | Design | Concept | Teacher partner church my food source. | 1 | Half reduce thus financial sister claim. | 3 | 5 | Medium | 1 | Critical | 167874.2 | 195047.53 | 178849.03 | 192261.36 | 921808.12 | Design Change | Closeout | Design | A | Commercial | Interface | Secondary | RBS-670 | 2025-07-12 | 2025-12-20 | No | Davis-Williams | PLAN-5079 | Seek everybody exactly natural. | RESP-21135 | Kathryn Webb | Mitigation action 88 | Closed | Second near term tend. Impact later drug move similar. | 2026-03-01 | 2026-04-05 | -34 | 2026-04-05 | 2026-04-25 | 2026-03-02 11:53 | 3339971.91 | 2907669.96 | 35.56
Project Risk | Residential Valley | North Hub | Mixed Use | PRJ-363 | SUB-9 | Carpenter-Hicks | drive vertical portals | Active | RISK-1088 | 2025-12-04 | 2026-03-04 | Delay in material delivery | Wall bed system middle again. Class firm thought keep outside. Activity send almost already page. | Find there term environment wish present manager. | Claim establish around machine season school know. | 2025-12-10 | Mitigating | 2026-06-22 | Andrew Owen | Pre-Concept | Construction | Study number image treatment pick television group police. | 2 | Too create far indeed station evening guy. | 1 | 17 | Medium | 8 | Medium | 432381.12 | 91437.38 | 131538.27 | 150210.69 | 703969.39 | Contractor Delay | Closeout | Design | B | Technical | External | Secondary | RBS-151 | 2025-12-29 | 2026-03-04 | No | Berger and Sons | PLAN-8163 | Discuss number myself member strong you. | RESP-92649 | Kenneth Brown | Mitigation action 89 | In Progress | Over include down water learn standard speak. Best region wear shoulder. | 2026-03-01 | 2026-06-10 | -100 | 2026-06-10 | 2026-06-22 | 2026-03-02 11:53 | 3676356.17 | 3744437.75 | 38.56
Project Risk | Central Development | Waterfront | Theme Park | PRJ-687 | SUB-9 | Ramirez, Roberts and Rivers | scale wireless channels | Delayed | RISK-1089 | 2025-11-03 | 2026-01-01 | Delay in utility relocation | Reveal consumer pretty world. Alone along which. Her account since. | Front sea soon technology stay. | Several western soldier report weight country carry. | 2025-11-17 | Escalated |  | Betty Haas | Closeout | Handover | Wall result growth look throughout herself. | 5 | Color address doctor sign anyone film. | 1 | 22 | Low | 2 | High | 301504.54 | 195450.51 | 18662.01 | 49543.23 | 518594.96 | Supply Chain | Design | Design | A | Operational | External | Primary | RBS-469 | 2025-11-22 | 2026-04-26 | Yes | Roberts LLC | PLAN-1131 | Civil require bit between meet someone not. | RESP-14719 | Larry Bradshaw | Mitigation action 90 | In Progress | Nor cover marriage community. | 2026-03-01 | 2026-04-12 | -41 | 2026-04-12 |  | 2026-03-02 11:53 | 4989905.46 | 5520021.46 | 65.94
Project Risk | Residential Valley | Mountain Edge | Theme Park | PRJ-851 | SUB-9 | Willis, Walker and Benjamin | utilize killer relationships | Completed | RISK-1090 | 2026-02-05 | 2026-05-18 | Delay in utility relocation | Us cold middle stop cold stuff cold. | Century whatever herself than million knowledge rock simply. | Get create look teacher travel foot. | 2026-02-26 | Escalated |  | Matthew Cooke | Execution | Concept | Become population throughout father also present now. | 3 | Daughter relationship think fly. | 5 | 7 | Low | 5 | Medium | 473917.17 | 66752.4 | 339344.98 | 125147.96 | 722181.07 | Design Change | Pre-Concept | Cost | B | Technical | External | Secondary | RBS-571 | 2026-02-07 | 2026-03-24 | No | Montgomery Group | PLAN-4024 | Low success impact fund future agreement cause admit. | RESP-24000 | Christine Mccann | Mitigation action 91 | Closed | Likely dark positive security true fact free. | 2026-03-01 | 2026-06-18 | -108 | 2026-06-18 |  | 2026-03-02 11:53 | 3182096.84 | 3525144.25 | 59.84
Project Risk | Sports District | North Hub | Hospitality | PRJ-701 | SUB-18 | Pierce Ltd | brand holistic interfaces | On Hold | RISK-1091 | 2025-09-05 | 2025-10-06 | Delay in foundation works | Commercial stop impact street nature in young. Inside piece defense start. | Miss street spend quickly choose though try. | Huge environmental wonder stop cover act Mr. | 2025-09-29 | Mitigating | 2026-07-17 | Peter Williams | Pre-Concept | Technical Design | Statement commercial explain body possible. | 5 | Nice glass fear he tree traditional expert. | 1 | 18 | Medium | 7 | Medium | 284803.71 | 34266.97 | 336039.57 | 137925.82 | 965336.44 | Supply Chain | Concept | Stakeholder | C | Technical | Interface | Secondary | RBS-340 | 2025-09-25 | 2026-01-19 | Yes | Pierce-Moore | PLAN-2643 | Bank visit Mrs form marriage. | RESP-65891 | Sandra Smith | Mitigation action 92 | In Progress | Own me focus life though process page. | 2026-03-01 | 2026-06-27 | -117 | 2026-06-27 | 2026-07-17 | 2026-03-02 11:53 | 3415580.53 | 2888738.94 | 54.1
Project Risk | Sports District | South Hub | Mixed Use | PRJ-606 | SUB-1 | Myers, Evans and Martin | unleash out-of-the-box schemas | On Hold | RISK-1092 | 2025-04-21 | 2025-05-04 | Delay in foundation works | Such inside real clearly body follow mother turn. | Learn walk attack interview fall sister. | Parent girl partner still reality. | 2025-04-30 | Escalated | 2026-05-23 | Robert Sanchez | Closeout | Design | Quality country help theory example executive people. | 3 | How television peace represent including able tough job. | 5 | 6 | Medium | 6 | Medium | 182160.97 | 56491.75 | 29884.7 | 12200.79 | 854391.33 | Supply Chain | Pre-Concept | Schedule | A | Technical | Interface | Primary | RBS-511 | 2025-05-13 | 2025-06-17 | Yes | Greene, Whitney and Floyd | PLAN-9575 | Brother argue street gun between cover first. | RESP-70258 | James Villarreal | Mitigation action 93 | In Progress | Outside person fine. Author discussion hour identify. | 2026-03-01 | 2026-05-20 | -79 | 2026-05-20 | 2026-05-23 | 2026-03-02 11:53 | 947450.71 | 772407.9 | 11.28
Project Risk | Central Development | Mountain Edge | Hospitality | PRJ-615 | SUB-15 | Davis-Williams | incentivize proactive platforms | Completed | RISK-1093 | 2025-07-10 | 2025-08-08 | Delay in foundation works | Participant foreign simple image by. Professor theory member research too. | Camera water none enter peace space. | Social discover agreement. | 2025-07-17 | Mitigating |  | Samuel Vaughn | Closeout | Technical Design | Night around open run or. | 2 | Film risk address manage defense evidence once. | 1 | 13 | High | 5 | High | 468960.94 | 47921.32 | 374190.79 | 110571.52 | 140089.97 | Design Change | Pre-Concept | Schedule | C | Technical | Interface | Primary | RBS-152 | 2025-08-29 | 2025-10-10 | No | Boone and Sons | PLAN-6796 | By own list responsibility person use whose. | RESP-91277 | Cassandra Osborne | Mitigation action 94 | Open | Them wife draw argue. | 2026-03-01 | 2026-04-23 | -52 | 2026-04-23 |  | 2026-03-02 11:53 | 360112.29 | 396130.82 | 46.53
Project Risk | Entertainment Zone | South Hub | Mixed Use | PRJ-958 | SUB-17 | Ford Group | monetize web-enabled e-services | On Hold | RISK-1094 | 2025-07-15 | 2025-07-20 | Delay in utility relocation | Turn should simple but account share cause. Until local education way eye professor. I Mr whom medical talk apply. | Debate activity body big capital. | Central really successful. | 2025-07-25 | Escalated |  | Miss Jennifer Dunlap | Design | Design | Dog its west away. | 2 | Any a ground full audience travel until. | 3 | 13 | High | 13 | Medium | 110219.98 | 136953.94 | 286161.49 | 185954.66 | 346405.73 | Funding | Pre-Concept | Procurement | B | Technical | Internal | Secondary | RBS-149 | 2025-07-26 | 2025-09-17 | No | Flores-Douglas | PLAN-5725 | Life health four guess interesting. | RESP-44413 | Mr. Zachary Andrews | Mitigation action 95 | Closed | Least build cause treat chair. May interesting business protect young identify range. | 2026-03-01 | 2026-04-16 | -45 | 2026-04-16 |  | 2026-03-02 11:53 | 713406.84 | 847681.89 | 34.32
Project Risk | Sports District | Mountain Edge | Hospitality | PRJ-545 | SUB-4 | Moses and Sons | re-intermediate mission-critical action-items | Completed | RISK-1095 | 2025-07-04 | 2025-09-24 | Delay in foundation works | Determine style shoulder civil manage building our. Seat approach success tonight home big. | Floor low moment describe money floor. | Unit several article. | 2025-07-20 | Escalated |  | Joseph Rios | Concept | Design | Article institution agent must dream do message. | 2 | Apply make right player life. | 3 | 18 | High | 17 | High | 422894.97 | 81170.26 | 215188.15 | 131335.88 | 110948.12 | Supply Chain | Concept | Stakeholder | A | Technical | Interface | Primary | RBS-545 | 2025-07-27 | 2025-10-07 | Yes | Crawford, Wright and Lewis | PLAN-5661 | Account outside rest next foot listen. | RESP-24945 | Barry Walton | Mitigation action 96 | Open | Body benefit technology long section performance. Account away media us well remember. | 2026-03-01 | 2026-03-31 | -29 | 2026-03-31 |  | 2026-03-02 11:53 | 3481758.34 | 2941149.45 | 7.02
Project Risk | Sports District | North Hub | Theme Park | PRJ-717 | SUB-5 | Adams Group | utilize mission-critical communities | Completed | RISK-1096 | 2025-08-21 | 2025-10-24 | Delay in foundation works | May week network area position people. Main step training nor when. Book might special once know good grow experience. | Lose central less road modern. | Investment forget most room practice new. | 2025-09-10 | Open | 2026-04-28 | Alicia Brown | Execution | Technical Design | College evening or leader condition. | 5 | Assume upon sign successful save daughter bag. | 1 | 11 | Low | 11 | Critical | 228727.12 | 5208.6 | 342022.52 | 69636.42 | 392553.26 | Contractor Delay | Pre-Concept | Stakeholder | A | Operational | External | Secondary | RBS-197 | 2025-09-08 | 2026-02-10 | No | Rodgers, White and Green | PLAN-5053 | Enter door whether person because. | RESP-13424 | Tyler Miller | Mitigation action 97 | In Progress | Difficult fact reflect analysis region teach wide. Professional wall mean strategy. | 2026-03-01 | 2026-04-25 | -54 | 2026-04-25 | 2026-04-28 | 2026-03-02 11:53 | 1140182.58 | 1192157.73 | 24.96
Project Risk | Central Development | South Hub | Infrastructure | PRJ-457 | SUB-13 | Mendoza Group | expedite global markets | On Hold | RISK-1097 | 2025-03-28 | 2025-04-21 | Delay in material delivery | Doctor probably general require better how. Job spend music contain less hope heavy. Specific citizen start matter writer white. | Instead will recently woman series. | Couple may whose same. | 2025-04-15 | Closed | 2026-06-21 | Amanda Coleman | Design | Concept | Rise successful friend read firm. | 3 | Region campaign for even. | 3 | 10 | Critical | 8 | Critical | 303203.28 | 10003.4 | 454686.32 | 74602.25 | 641355.41 | Funding | Concept | Schedule | A | Operational | Interface | Primary | RBS-767 | 2025-04-21 | 2025-07-05 | Yes | Stevenson-Ruiz | PLAN-4260 | Politics much both probably. | RESP-93336 | John Fernandez | Mitigation action 98 | Open | Military realize produce first partner ok. Enter food bill these available trip drug memory. | 2026-03-01 | 2026-06-15 | -105 | 2026-06-15 | 2026-06-21 | 2026-03-02 11:53 | 4599820.72 | 3981211.75 | 16.79
Project Risk | Central Development | Waterfront | Mixed Use | PRJ-919 | SUB-7 | Sanders Ltd | morph 24/365 systems | On Hold | RISK-1098 | 2025-11-30 | 2026-03-03 | Delay in foundation works | Treatment my kind voice news treat wait. Lead suggest others carry suffer player. Say whether wall life several democratic. | Change week interview deal. | Level where why until every deal think. | 2025-12-12 | Escalated |  | Larry Pacheco | Execution | Design | Cost down bit list none. | 5 | Help school nature even. | 3 | 22 | Low | 8 | High | 127631.59 | 31738.57 | 181364.38 | 184044.71 | 538109.93 | Supply Chain | Concept | Schedule | C | Operational | External | Primary | RBS-667 | 2025-12-16 | 2026-04-26 | No | Peterson-Garza | PLAN-3084 | Meeting as suddenly friend evening husband. | RESP-83373 | Amanda Gilbert | Mitigation action 99 | In Progress | Western shoulder success high fine no. | 2026-03-01 | 2026-06-26 | -116 | 2026-06-26 |  | 2026-03-02 11:53 | 4537792.85 | 4706035.49 | 66.84
Project Risk | Sports District | Mountain Edge | Hospitality | PRJ-427 | SUB-9 | Weaver-Sims | reinvent world-class communities | Completed | RISK-1099 | 2025-08-14 | 2025-12-12 | Delay in design approval | Off father join mean stay loss clear fact. My increase certain early accept born fish. | Again agent baby sport. | Manage include land recently campaign fire. | 2025-09-01 | Open | 2026-05-10 | Kayla Jones | Execution | Technical Design | Race nothing anything pay say. | 1 | Mother business rather condition amount whom. | 1 | 17 | Medium | 14 | Medium | 188933.47 | 90213.23 | 435352.87 | 61935.59 | 98870.5 | Supply Chain | Execution | Schedule | C | Commercial | Internal | Secondary | RBS-783 | 2025-08-29 | 2025-11-07 | Yes | Butler, Hess and Crawford | PLAN-9953 | Another community soldier good party a. | RESP-81113 | Samantha Vargas | Mitigation action 100 | In Progress | Run on traditional information recent situation. Agent people fact people Congress especially. | 2026-03-01 | 2026-05-07 | -66 | 2026-05-07 | 2026-05-10 | 2026-03-02 11:53 | 2565987.47 | 2604937.92 | 22.29