## IMS_Development_Time_Sample_v2
Activity ID | Project ID | Prog Version | Activity Name | Activity Type | Activity Status | District | Development | Class L1 ID | Class L2 ID | Asset | Project Status | Stage Gate L1 ID | Stage Gate L2 ID | Phase | Business Class | Precinct | Core Assets | Start Date | End Date | SG-Summary | QIC-BOD PC | QIC-BOD PC-Date | QIC-BOD-ML-ID | QIC-BOD-ML-DES | QIC-BOD-ML-Date
ACT-10000 | PRJ-691 | Baseline V3 | 5.06 - Superstructure | Procurement | In Progress | 194 | 1563 | 20 | 187 | 3571 | Delayed | 1 | 11 | 1 | 20 | 505 | 9026 | 2026-03-01 | 2026-08-16 | Gate Passed | 83.73 | 2026-05-17 | ML-5488 | Practical Completion Milestone | 2026-07-11
ACT-10001 | PRJ-230 | Baseline V4 | 3.08 - Fit-Out Works | Construction | Not Started | 162 | 1766 | 13 | 166 | 3450 | Active | 3 | 12 | 4 | 13 | 549 | 9034 | 2026-03-01 | 2027-05-06 | Pending Approval | 92.9 | 2026-04-30 | ML-9523 | Concept Design Approval | 2027-03-26
ACT-10002 | PRJ-656 | Baseline V2 | 2.08 - MEP Installation | Procurement | In Progress | 195 | 1027 | 10 | 174 | 3448 | Delayed | 3 | 20 | 4 | 28 | 543 | 9033 | 2026-03-01 | 2027-08-03 | Under Review | 10.05 | 2026-04-20 | ML-8196 | IFC Drawing Approval | 2027-06-07
ACT-10003 | PRJ-706 | Baseline V2 | 3.01 - Facade Installation | Testing & Commissioning | Completed | 169 | 1602 | 15 | 172 | 3611 | On Hold | 2 | 24 | 5 | 15 | 515 | 9000 | 2026-03-01 | 2026-09-27 | Under Review | 64.67 | 2026-05-15 | ML-8691 | Practical Completion Milestone | 2026-08-29
ACT-10004 | PRJ-513 | Baseline V4 | 3.09 - Substructure Works | Procurement | In Progress | 107 | 1134 | 20 | 141 | 3986 | Delayed | 3 | 30 | 4 | 24 | 511 | 9010 | 2026-03-01 | 2027-08-11 | Gate Passed | 72.14 | 2026-06-04 | ML-9093 | Concept Design Approval | 2027-07-16
ACT-10005 | PRJ-524 | Baseline V3 | 5.05 - Substructure Works | Engineering Design | In Progress | 193 | 1788 | 15 | 150 | 3944 | Completed | 3 | 22 | 3 | 15 | 531 | 9007 | 2026-03-01 | 2026-08-20 | Gate Passed | 79.95 | 2026-05-10 | ML-7805 | Concept Design Approval | 2026-07-29
ACT-10006 | PRJ-344 | Baseline V4 | 5.01 - MEP Installation | Engineering Design | Behind Schedule | 190 | 1679 | 15 | 141 | 3478 | On Hold | 2 | 14 | 1 | 26 | 528 | 9015 | 2026-03-01 | 2026-05-06 | Pending Approval | 99.19 | 2026-03-24 | ML-6023 | Practical Completion Milestone | 2026-03-07
ACT-10007 | PRJ-173 | Baseline V2 | 5.09 - Superstructure | Authority Approval | In Progress | 196 | 1428 | 19 | 189 | 3437 | Active | 1 | 29 | 3 | 13 | 502 | 9048 | 2026-03-01 | 2027-08-14 | Under Review | 96.96 | 2026-06-17 | ML-2666 | Practical Completion Milestone | 2027-07-19
ACT-10008 | PRJ-752 | Baseline V1 | 2.06 - Substructure Works | Construction | Completed | 154 | 1782 | 12 | 196 | 3816 | Active | 2 | 21 | 1 | 17 | 520 | 9040 | 2026-03-01 | 2027-05-23 | Gate Passed | 5.02 | 2026-04-08 | ML-6873 | Procurement Award | 2027-04-24
ACT-10009 | PRJ-869 | Baseline V3 | 1.05 - Facade Installation | Construction | In Progress | 145 | 1640 | 12 | 167 | 3617 | Active | 2 | 24 | 3 | 24 | 524 | 9046 | 2026-03-01 | 2026-06-18 | Gate Passed | 61.86 | 2026-04-30 | ML-2573 | Procurement Award | 2026-05-03
ACT-10010 | PRJ-593 | Baseline V3 | 3.07 - Fit-Out Works | Engineering Design | Behind Schedule | 122 | 1147 | 11 | 101 | 3798 | Delayed | 3 | 19 | 1 | 29 | 510 | 9025 | 2026-03-01 | 2026-09-21 | Pending Approval | 69.22 | 2026-06-18 | ML-6044 | Procurement Award | 2026-08-28
ACT-10011 | PRJ-578 | Baseline V2 | 2.06 - Fit-Out Works | Construction | In Progress | 164 | 1002 | 20 | 197 | 3503 | Active | 1 | 30 | 1 | 22 | 524 | 9008 | 2026-03-01 | 2026-07-20 | Gate Passed | 59.07 | 2026-04-14 | ML-1694 | IFC Drawing Approval | 2026-06-09
ACT-10012 | PRJ-483 | Baseline V1 | 1.08 - MEP Installation | Authority Approval | In Progress | 180 | 1716 | 10 | 174 | 3831 | Completed | 2 | 29 | 1 | 15 | 521 | 9044 | 2026-03-01 | 2027-02-23 | Gate Passed | 62.68 | 2026-03-26 | ML-1145 | IFC Drawing Approval | 2027-01-24
ACT-10013 | PRJ-303 | Baseline V2 | 2.09 - Fit-Out Works | Construction | In Progress | 140 | 1599 | 15 | 183 | 3685 | Delayed | 3 | 10 | 5 | 23 | 527 | 9048 | 2026-03-01 | 2026-10-31 | Under Review | 92.49 | 2026-05-01 | ML-4329 | Concept Design Approval | 2026-09-24
ACT-10014 | PRJ-432 | Baseline V4 | 1.09 - Substructure Works | Testing & Commissioning | In Progress | 119 | 1435 | 16 | 130 | 3379 | Active | 3 | 20 | 3 | 10 | 537 | 9030 | 2026-03-01 | 2026-08-01 | Pending Approval | 28.05 | 2026-03-16 | ML-7362 | Concept Design Approval | 2026-06-30
ACT-10015 | PRJ-815 | Baseline V1 | 1.06 - MEP Installation | Procurement | Behind Schedule | 107 | 1305 | 20 | 149 | 3092 | Active | 2 | 25 | 5 | 29 | 505 | 9030 | 2026-03-01 | 2026-08-24 | Pending Approval | 66.27 | 2026-06-05 | ML-1945 | Concept Design Approval | 2026-08-24
ACT-10016 | PRJ-448 | Baseline V4 | 5.07 - Superstructure | Testing & Commissioning | In Progress | 185 | 1365 | 20 | 166 | 3008 | Completed | 1 | 29 | 4 | 10 | 523 | 9026 | 2026-03-01 | 2027-01-05 | Pending Approval | 17.53 | 2026-06-18 | ML-4940 | Practical Completion Milestone | 2026-11-27
ACT-10017 | PRJ-950 | Baseline V4 | 1.05 - Fit-Out Works | Testing & Commissioning | In Progress | 129 | 1955 | 10 | 100 | 3283 | Active | 2 | 19 | 1 | 21 | 543 | 9011 | 2026-03-01 | 2027-08-02 | Under Review | 88.77 | 2026-06-29 | ML-8272 | IFC Drawing Approval | 2027-07-21
ACT-10018 | PRJ-799 | Baseline V1 | 3.05 - MEP Installation | Authority Approval | In Progress | 106 | 1689 | 12 | 159 | 3576 | Completed | 3 | 19 | 3 | 24 | 529 | 9001 | 2026-03-01 | 2027-06-22 | Pending Approval | 61.62 | 2026-05-07 | ML-5319 | Procurement Award | 2027-05-04
ACT-10019 | PRJ-219 | Baseline V4 | 3.04 - Fit-Out Works | Engineering Design | Behind Schedule | 198 | 1017 | 15 | 146 | 3920 | Completed | 3 | 14 | 1 | 10 | 533 | 9004 | 2026-03-01 | 2027-01-14 | Pending Approval | 55.09 | 2026-04-07 | ML-4139 | Procurement Award | 2026-11-20
ACT-10020 | PRJ-606 | Baseline V3 | 1.01 - Substructure Works | Procurement | Behind Schedule | 126 | 1140 | 14 | 121 | 3734 | Completed | 3 | 16 | 1 | 25 | 516 | 9050 | 2026-03-01 | 2026-11-16 | Gate Passed | 64.11 | 2026-05-26 | ML-8461 | Concept Design Approval | 2026-09-19
ACT-10021 | PRJ-365 | Baseline V1 | 3.04 - Substructure Works | Engineering Design | Completed | 139 | 1263 | 12 | 121 | 3554 | Completed | 2 | 24 | 4 | 20 | 516 | 9010 | 2026-03-01 | 2026-07-31 | Pending Approval | 38.11 | 2026-04-07 | ML-1588 | Concept Design Approval | 2026-07-31
ACT-10022 | PRJ-506 | Baseline V3 | 1.04 - Superstructure | Construction | Completed | 127 | 1211 | 12 | 115 | 3479 | Completed | 2 | 20 | 1 | 26 | 541 | 9029 | 2026-03-01 | 2026-12-07 | Under Review | 61.81 | 2026-03-25 | ML-5807 | Concept Design Approval | 2026-11-23
ACT-10023 | PRJ-269 | Baseline V3 | 4.03 - MEP Installation | Construction | In Progress | 131 | 1942 | 15 | 110 | 3649 | On Hold | 3 | 23 | 1 | 23 | 511 | 9013 | 2026-03-01 | 2026-11-30 | Gate Passed | 87.84 | 2026-03-16 | ML-9789 | IFC Drawing Approval | 2026-10-14
ACT-10024 | PRJ-604 | Baseline V2 | 2.08 - Facade Installation | Authority Approval | In Progress | 179 | 1268 | 12 | 197 | 3574 | On Hold | 1 | 18 | 3 | 23 | 523 | 9043 | 2026-03-01 | 2027-07-27 | Gate Passed | 0.33 | 2026-05-07 | ML-6015 | Concept Design Approval | 2027-07-02
ACT-10025 | PRJ-892 | Baseline V4 | 3.03 - Facade Installation | Construction | Not Started | 183 | 1745 | 11 | 145 | 3276 | Delayed | 2 | 30 | 1 | 13 | 524 | 9013 | 2026-03-01 | 2026-11-19 | Under Review | 20.56 | 2026-05-05 | ML-8439 | Procurement Award | 2026-11-05
ACT-10026 | PRJ-584 | Baseline V2 | 4.02 - Substructure Works | Authority Approval | In Progress | 153 | 1422 | 11 | 193 | 3253 | Completed | 1 | 18 | 5 | 30 | 507 | 9006 | 2026-03-01 | 2027-05-17 | Gate Passed | 53.54 | 2026-05-19 | ML-6768 | Practical Completion Milestone | 2027-05-11
ACT-10027 | PRJ-573 | Baseline V4 | 2.03 - MEP Installation | Engineering Design | Behind Schedule | 148 | 1937 | 18 | 162 | 3406 | Active | 3 | 18 | 3 | 10 | 501 | 9028 | 2026-03-01 | 2026-08-23 | Pending Approval | 14.14 | 2026-05-29 | ML-2316 | Procurement Award | 2026-08-07
ACT-10028 | PRJ-613 | Baseline V3 | 2.04 - MEP Installation | Procurement | In Progress | 113 | 1210 | 10 | 101 | 3015 | Completed | 2 | 27 | 2 | 26 | 532 | 9043 | 2026-03-01 | 2026-12-27 | Gate Passed | 43.34 | 2026-06-10 | ML-6538 | Procurement Award | 2026-11-26
ACT-10029 | PRJ-717 | Baseline V4 | 1.07 - Substructure Works | Procurement | Completed | 106 | 1231 | 19 | 116 | 3902 | Active | 3 | 11 | 5 | 23 | 543 | 9036 | 2026-03-01 | 2026-08-28 | Pending Approval | 78.34 | 2026-04-15 | ML-3095 | Practical Completion Milestone | 2026-08-01
ACT-10030 | PRJ-470 | Baseline V4 | 3.05 - MEP Installation | Testing & Commissioning | Not Started | 149 | 1318 | 10 | 150 | 3496 | Delayed | 1 | 24 | 2 | 15 | 533 | 9010 | 2026-03-01 | 2026-11-20 | Gate Passed | 57.38 | 2026-04-14 | ML-2206 | IFC Drawing Approval | 2026-10-30
ACT-10031 | PRJ-665 | Baseline V3 | 1.05 - Superstructure | Testing & Commissioning | Completed | 171 | 1340 | 20 | 129 | 3193 | Delayed | 2 | 14 | 4 | 23 | 541 | 9041 | 2026-03-01 | 2027-01-01 | Pending Approval | 92.04 | 2026-06-10 | ML-4583 | Practical Completion Milestone | 2026-11-12
ACT-10032 | PRJ-285 | Baseline V1 | 5.05 - Facade Installation | Authority Approval | Completed | 116 | 1854 | 20 | 106 | 3659 | On Hold | 1 | 21 | 3 | 29 | 534 | 9016 | 2026-03-01 | 2026-10-17 | Under Review | 53.04 | 2026-06-03 | ML-6628 | Practical Completion Milestone | 2026-10-02
ACT-10033 | PRJ-461 | Baseline V1 | 5.02 - MEP Installation | Engineering Design | In Progress | 133 | 1759 | 11 | 165 | 3442 | Active | 3 | 23 | 4 | 16 | 507 | 9030 | 2026-03-01 | 2026-08-20 | Gate Passed | 82.15 | 2026-05-27 | ML-9539 | IFC Drawing Approval | 2026-07-15
ACT-10034 | PRJ-666 | Baseline V2 | 1.03 - Superstructure | Procurement | In Progress | 199 | 1399 | 20 | 125 | 3434 | Completed | 3 | 24 | 1 | 10 | 518 | 9024 | 2026-03-01 | 2026-12-28 | Gate Passed | 75.57 | 2026-05-09 | ML-2735 | Concept Design Approval | 2026-11-23
ACT-10035 | PRJ-924 | Baseline V3 | 2.04 - Facade Installation | Testing & Commissioning | Not Started | 115 | 1195 | 16 | 144 | 3091 | Completed | 3 | 30 | 2 | 14 | 507 | 9007 | 2026-03-01 | 2026-08-09 | Pending Approval | 13.25 | 2026-04-04 | ML-7714 | Procurement Award | 2026-06-13
ACT-10036 | PRJ-557 | Baseline V3 | 3.02 - MEP Installation | Construction | Not Started | 108 | 1837 | 18 | 166 | 3246 | Delayed | 3 | 14 | 1 | 11 | 519 | 9043 | 2026-03-01 | 2027-02-12 | Gate Passed | 58.74 | 2026-04-10 | ML-9202 | Practical Completion Milestone | 2027-01-15
ACT-10037 | PRJ-647 | Baseline V3 | 3.03 - Facade Installation | Engineering Design | Completed | 155 | 1012 | 17 | 160 | 3187 | On Hold | 2 | 21 | 5 | 28 | 543 | 9049 | 2026-03-01 | 2026-07-26 | Pending Approval | 11.79 | 2026-05-02 | ML-1327 | Procurement Award | 2026-06-11
ACT-10038 | PRJ-923 | Baseline V4 | 4.01 - Facade Installation | Construction | Behind Schedule | 181 | 1376 | 14 | 107 | 3588 | On Hold | 1 | 22 | 4 | 16 | 527 | 9050 | 2026-03-01 | 2027-06-04 | Pending Approval | 34.59 | 2026-05-20 | ML-2511 | Practical Completion Milestone | 2027-05-15
ACT-10039 | PRJ-498 | Baseline V1 | 3.05 - Superstructure | Engineering Design | In Progress | 113 | 1457 | 13 | 149 | 3104 | Active | 2 | 24 | 1 | 26 | 515 | 9006 | 2026-03-01 | 2026-12-27 | Pending Approval | 3.95 | 2026-03-25 | ML-2881 | Practical Completion Milestone | 2026-12-22
ACT-10040 | PRJ-223 | Baseline V2 | 1.02 - Substructure Works | Construction | Completed | 188 | 1243 | 20 | 163 | 3576 | Completed | 2 | 14 | 2 | 27 | 546 | 9011 | 2026-03-01 | 2026-10-16 | Under Review | 32.57 | 2026-04-24 | ML-6179 | Procurement Award | 2026-10-06
ACT-10041 | PRJ-211 | Baseline V1 | 1.02 - MEP Installation | Procurement | Completed | 155 | 1831 | 13 | 178 | 3239 | Delayed | 3 | 29 | 4 | 12 | 540 | 9022 | 2026-03-01 | 2027-01-16 | Gate Passed | 51.21 | 2026-03-19 | ML-3805 | Practical Completion Milestone | 2026-11-26
ACT-10042 | PRJ-627 | Baseline V1 | 3.04 - Facade Installation | Authority Approval | In Progress | 188 | 1707 | 18 | 163 | 3725 | On Hold | 2 | 14 | 1 | 20 | 521 | 9023 | 2026-03-01 | 2027-01-30 | Pending Approval | 55 | 2026-04-20 | ML-4529 | Concept Design Approval | 2026-12-06
ACT-10043 | PRJ-531 | Baseline V2 | 1.08 - Substructure Works | Construction | In Progress | 155 | 1438 | 18 | 142 | 3603 | Active | 2 | 20 | 4 | 13 | 549 | 9023 | 2026-03-01 | 2026-12-29 | Gate Passed | 13.69 | 2026-05-13 | ML-3060 | IFC Drawing Approval | 2026-12-03
ACT-10044 | PRJ-588 | Baseline V4 | 3.03 - MEP Installation | Testing & Commissioning | Completed | 186 | 1420 | 13 | 147 | 3802 | Active | 1 | 12 | 5 | 18 | 521 | 9046 | 2026-03-01 | 2026-07-28 | Gate Passed | 93.63 | 2026-04-23 | ML-1845 | Concept Design Approval | 2026-06-25
ACT-10045 | PRJ-687 | Baseline V2 | 4.06 - MEP Installation | Procurement | Not Started | 130 | 1079 | 20 | 128 | 3656 | Completed | 3 | 29 | 4 | 23 | 512 | 9040 | 2026-03-01 | 2027-05-25 | Under Review | 90.62 | 2026-04-07 | ML-6332 | Practical Completion Milestone | 2027-04-13
ACT-10046 | PRJ-876 | Baseline V1 | 4.08 - Facade Installation | Testing & Commissioning | Completed | 167 | 1561 | 19 | 106 | 3670 | Active | 1 | 12 | 1 | 22 | 515 | 9017 | 2026-03-01 | 2026-05-05 | Under Review | 2.55 | 2026-04-07 | ML-5302 | IFC Drawing Approval | 2026-03-23
ACT-10047 | PRJ-734 | Baseline V2 | 5.02 - Superstructure | Construction | Completed | 175 | 1322 | 16 | 133 | 3519 | On Hold | 2 | 27 | 1 | 27 | 519 | 9004 | 2026-03-01 | 2027-03-09 | Gate Passed | 32.52 | 2026-05-28 | ML-8125 | Procurement Award | 2027-02-13
ACT-10048 | PRJ-973 | Baseline V2 | 4.03 - Substructure Works | Construction | Behind Schedule | 190 | 1162 | 16 | 139 | 3710 | Completed | 2 | 16 | 3 | 14 | 512 | 9003 | 2026-03-01 | 2027-02-06 | Gate Passed | 11.34 | 2026-06-01 | ML-9828 | Practical Completion Milestone | 2026-12-11
ACT-10049 | PRJ-546 | Baseline V1 | 5.02 - MEP Installation | Testing & Commissioning | Completed | 155 | 1064 | 17 | 133 | 3847 | Delayed | 1 | 28 | 5 | 27 | 501 | 9013 | 2026-03-01 | 2027-01-02 | Under Review | 35.08 | 2026-03-23 | ML-2561 | Procurement Award | 2026-11-16
ACT-10050 | PRJ-142 | Baseline V1 | 3.08 - Superstructure | Engineering Design | Not Started | 177 | 1106 | 14 | 143 | 3322 | Delayed | 2 | 25 | 4 | 15 | 529 | 9038 | 2026-03-01 | 2027-03-28 | Pending Approval | 33.19 | 2026-04-05 | ML-5457 | Procurement Award | 2027-02-11
ACT-10051 | PRJ-158 | Baseline V2 | 4.02 - Substructure Works | Construction | Completed | 133 | 1664 | 19 | 198 | 3250 | On Hold | 3 | 13 | 3 | 24 | 510 | 9031 | 2026-03-01 | 2026-09-03 | Pending Approval | 28.03 | 2026-06-20 | ML-4594 | Practical Completion Milestone | 2026-08-18
ACT-10052 | PRJ-685 | Baseline V4 | 1.05 - MEP Installation | Authority Approval | Not Started | 111 | 1116 | 13 | 132 | 3461 | Delayed | 2 | 24 | 1 | 22 | 538 | 9027 | 2026-03-01 | 2027-07-05 | Pending Approval | 50.6 | 2026-06-08 | ML-6469 | IFC Drawing Approval | 2027-05-13
ACT-10053 | PRJ-495 | Baseline V1 | 4.03 - Superstructure | Engineering Design | Completed | 197 | 1027 | 20 | 154 | 3668 | Completed | 3 | 14 | 4 | 26 | 502 | 9017 | 2026-03-01 | 2027-03-23 | Under Review | 87.27 | 2026-03-19 | ML-1693 | Practical Completion Milestone | 2027-03-11
ACT-10054 | PRJ-454 | Baseline V1 | 3.01 - Fit-Out Works | Construction | Completed | 111 | 1955 | 19 | 196 | 3425 | Delayed | 2 | 30 | 1 | 24 | 535 | 9012 | 2026-03-01 | 2026-12-06 | Pending Approval | 69.23 | 2026-05-27 | ML-4870 | Concept Design Approval | 2026-11-02
ACT-10055 | PRJ-640 | Baseline V1 | 4.07 - Superstructure | Procurement | Not Started | 161 | 1476 | 16 | 156 | 3043 | Delayed | 3 | 21 | 2 | 20 | 544 | 9038 | 2026-03-01 | 2027-07-31 | Under Review | 19.94 | 2026-06-07 | ML-7781 | Practical Completion Milestone | 2027-06-10
ACT-10056 | PRJ-528 | Baseline V4 | 2.09 - Substructure Works | Engineering Design | In Progress | 105 | 1787 | 16 | 128 | 3157 | Completed | 3 | 21 | 5 | 12 | 505 | 9007 | 2026-03-01 | 2027-02-15 | Under Review | 91.14 | 2026-04-26 | ML-2873 | IFC Drawing Approval | 2027-02-12
ACT-10057 | PRJ-456 | Baseline V4 | 5.02 - Facade Installation | Engineering Design | In Progress | 172 | 1988 | 19 | 151 | 3580 | Active | 3 | 18 | 5 | 29 | 533 | 9010 | 2026-03-01 | 2026-05-24 | Under Review | 93.98 | 2026-03-21 | ML-1355 | IFC Drawing Approval | 2026-05-13
ACT-10058 | PRJ-384 | Baseline V4 | 4.05 - MEP Installation | Engineering Design | Not Started | 164 | 1238 | 14 | 118 | 3669 | On Hold | 2 | 12 | 1 | 19 | 530 | 9037 | 2026-03-01 | 2027-07-18 | Gate Passed | 32.46 | 2026-06-08 | ML-2012 | Procurement Award | 2027-07-02
ACT-10059 | PRJ-982 | Baseline V1 | 3.01 - MEP Installation | Construction | Behind Schedule | 181 | 1192 | 18 | 130 | 3948 | Active | 3 | 24 | 1 | 25 | 518 | 9042 | 2026-03-01 | 2027-03-25 | Gate Passed | 19.26 | 2026-05-24 | ML-2312 | Concept Design Approval | 2027-02-18
ACT-10060 | PRJ-351 | Baseline V3 | 4.04 - Facade Installation | Procurement | Behind Schedule | 106 | 1915 | 14 | 125 | 3773 | On Hold | 1 | 26 | 3 | 13 | 535 | 9043 | 2026-03-01 | 2027-04-14 | Gate Passed | 28.57 | 2026-04-11 | ML-1418 | Procurement Award | 2027-03-23
ACT-10061 | PRJ-246 | Baseline V4 | 3.06 - MEP Installation | Testing & Commissioning | Not Started | 118 | 1192 | 19 | 167 | 3916 | On Hold | 2 | 19 | 1 | 28 | 549 | 9048 | 2026-03-01 | 2026-06-29 | Under Review | 59.31 | 2026-04-21 | ML-1227 | Practical Completion Milestone | 2026-05-30
ACT-10062 | PRJ-945 | Baseline V3 | 5.08 - Substructure Works | Construction | Behind Schedule | 138 | 1229 | 16 | 184 | 3828 | Delayed | 3 | 15 | 4 | 15 | 521 | 9032 | 2026-03-01 | 2026-12-31 | Pending Approval | 90.82 | 2026-06-17 | ML-9646 | IFC Drawing Approval | 2026-12-13
ACT-10063 | PRJ-923 | Baseline V2 | 4.09 - Facade Installation | Procurement | Behind Schedule | 179 | 1569 | 16 | 166 | 3729 | On Hold | 1 | 26 | 4 | 27 | 526 | 9013 | 2026-03-01 | 2026-08-06 | Pending Approval | 12.57 | 2026-05-08 | ML-6904 | Practical Completion Milestone | 2026-06-23
ACT-10064 | PRJ-404 | Baseline V2 | 4.03 - Fit-Out Works | Procurement | Completed | 142 | 1034 | 14 | 136 | 3095 | On Hold | 2 | 25 | 4 | 26 | 530 | 9032 | 2026-03-01 | 2027-01-15 | Pending Approval | 15.98 | 2026-05-31 | ML-5090 | IFC Drawing Approval | 2027-01-15
ACT-10065 | PRJ-369 | Baseline V3 | 1.09 - MEP Installation | Testing & Commissioning | Completed | 100 | 1139 | 12 | 120 | 3190 | Active | 1 | 23 | 1 | 17 | 508 | 9032 | 2026-03-01 | 2027-01-12 | Pending Approval | 70.77 | 2026-04-30 | ML-6580 | Procurement Award | 2027-01-07
ACT-10066 | PRJ-887 | Baseline V1 | 3.04 - Fit-Out Works | Construction | In Progress | 152 | 1304 | 18 | 112 | 3046 | Active | 1 | 18 | 2 | 13 | 542 | 9048 | 2026-03-01 | 2027-04-25 | Under Review | 54.79 | 2026-04-26 | ML-2574 | IFC Drawing Approval | 2027-03-24
ACT-10067 | PRJ-167 | Baseline V1 | 3.09 - Superstructure | Construction | In Progress | 103 | 1598 | 18 | 107 | 3050 | Delayed | 2 | 21 | 2 | 27 | 540 | 9032 | 2026-03-01 | 2026-06-20 | Gate Passed | 79.84 | 2026-05-05 | ML-4654 | Practical Completion Milestone | 2026-05-06
ACT-10068 | PRJ-102 | Baseline V3 | 5.09 - Fit-Out Works | Authority Approval | In Progress | 189 | 1629 | 14 | 124 | 3713 | Delayed | 1 | 29 | 1 | 10 | 513 | 9010 | 2026-03-01 | 2027-03-08 | Gate Passed | 52.73 | 2026-05-04 | ML-2785 | Concept Design Approval | 2027-02-02
ACT-10069 | PRJ-385 | Baseline V1 | 2.05 - Facade Installation | Engineering Design | In Progress | 114 | 1521 | 20 | 164 | 3390 | On Hold | 2 | 26 | 3 | 24 | 545 | 9048 | 2026-03-01 | 2027-03-25 | Gate Passed | 38.31 | 2026-06-07 | ML-5665 | IFC Drawing Approval | 2027-03-08
ACT-10070 | PRJ-827 | Baseline V1 | 2.04 - MEP Installation | Construction | In Progress | 107 | 1167 | 20 | 144 | 3899 | Completed | 1 | 28 | 2 | 12 | 535 | 9014 | 2026-03-01 | 2026-08-26 | Pending Approval | 58.7 | 2026-06-07 | ML-3229 | IFC Drawing Approval | 2026-07-11
ACT-10071 | PRJ-201 | Baseline V3 | 5.01 - Fit-Out Works | Engineering Design | Behind Schedule | 121 | 1086 | 16 | 106 | 3232 | Active | 1 | 21 | 2 | 27 | 547 | 9029 | 2026-03-01 | 2027-06-29 | Under Review | 60.9 | 2026-03-26 | ML-9831 | Concept Design Approval | 2027-05-23
ACT-10072 | PRJ-531 | Baseline V2 | 1.06 - Fit-Out Works | Testing & Commissioning | Completed | 177 | 1666 | 15 | 174 | 3267 | On Hold | 3 | 18 | 3 | 22 | 510 | 9015 | 2026-03-01 | 2027-03-24 | Gate Passed | 93.08 | 2026-05-27 | ML-6955 | Practical Completion Milestone | 2027-02-11
ACT-10073 | PRJ-758 | Baseline V4 | 3.07 - Facade Installation | Construction | In Progress | 179 | 1971 | 14 | 101 | 3756 | Delayed | 3 | 22 | 5 | 11 | 546 | 9019 | 2026-03-01 | 2026-06-10 | Gate Passed | 0.22 | 2026-03-20 | ML-3234 | IFC Drawing Approval | 2026-05-17
ACT-10074 | PRJ-683 | Baseline V4 | 1.07 - MEP Installation | Testing & Commissioning | Behind Schedule | 105 | 1376 | 16 | 124 | 3565 | Active | 1 | 30 | 4 | 10 | 530 | 9021 | 2026-03-01 | 2026-10-30 | Pending Approval | 17.83 | 2026-06-19 | ML-9286 | Practical Completion Milestone | 2026-09-22
ACT-10075 | PRJ-770 | Baseline V2 | 3.03 - Superstructure | Engineering Design | Completed | 166 | 1246 | 19 | 138 | 3473 | Completed | 2 | 12 | 3 | 14 | 508 | 9049 | 2026-03-01 | 2027-08-04 | Gate Passed | 95.92 | 2026-05-24 | ML-7315 | IFC Drawing Approval | 2027-07-22
ACT-10076 | PRJ-861 | Baseline V2 | 1.05 - Facade Installation | Construction | Behind Schedule | 121 | 1584 | 16 | 113 | 3174 | On Hold | 1 | 29 | 1 | 23 | 544 | 9030 | 2026-03-01 | 2026-05-10 | Gate Passed | 92.3 | 2026-05-31 | ML-3773 | Procurement Award | 2026-04-19
ACT-10077 | PRJ-104 | Baseline V3 | 2.06 - Fit-Out Works | Authority Approval | In Progress | 183 | 1394 | 12 | 147 | 3738 | On Hold | 2 | 27 | 4 | 27 | 515 | 9040 | 2026-03-01 | 2026-09-15 | Pending Approval | 84.36 | 2026-03-18 | ML-4998 | Procurement Award | 2026-09-10
ACT-10078 | PRJ-283 | Baseline V4 | 4.03 - Substructure Works | Construction | Completed | 127 | 1214 | 12 | 165 | 3506 | On Hold | 1 | 21 | 1 | 14 | 535 | 9028 | 2026-03-01 | 2026-09-05 | Under Review | 46.89 | 2026-03-18 | ML-7557 | IFC Drawing Approval | 2026-07-28
ACT-10079 | PRJ-468 | Baseline V3 | 2.06 - Facade Installation | Construction | Completed | 101 | 1712 | 16 | 165 | 3986 | On Hold | 1 | 29 | 5 | 29 | 527 | 9029 | 2026-03-01 | 2027-06-27 | Gate Passed | 28.91 | 2026-03-31 | ML-9428 | Practical Completion Milestone | 2027-06-12
ACT-10080 | PRJ-639 | Baseline V4 | 4.07 - Substructure Works | Testing & Commissioning | Not Started | 135 | 1706 | 14 | 147 | 3978 | Completed | 3 | 15 | 5 | 22 | 522 | 9016 | 2026-03-01 | 2026-06-03 | Gate Passed | 7.07 | 2026-06-16 | ML-1542 | Practical Completion Milestone | 2026-06-01
ACT-10081 | PRJ-157 | Baseline V1 | 3.03 - MEP Installation | Testing & Commissioning | In Progress | 111 | 1599 | 12 | 138 | 3080 | Active | 3 | 15 | 3 | 21 | 537 | 9023 | 2026-03-01 | 2027-04-26 | Under Review | 63.58 | 2026-05-31 | ML-1979 | Procurement Award | 2027-04-07
ACT-10082 | PRJ-593 | Baseline V1 | 4.07 - Superstructure | Testing & Commissioning | Not Started | 106 | 1791 | 15 | 122 | 3736 | Active | 3 | 26 | 3 | 21 | 514 | 9044 | 2026-03-01 | 2026-05-15 | Pending Approval | 90.69 | 2026-05-19 | ML-7462 | Procurement Award | 2026-04-12
ACT-10083 | PRJ-953 | Baseline V4 | 2.04 - Fit-Out Works | Engineering Design | Completed | 199 | 1730 | 15 | 104 | 3770 | Delayed | 1 | 15 | 1 | 18 | 542 | 9039 | 2026-03-01 | 2026-12-23 | Under Review | 2.28 | 2026-06-12 | ML-7403 | Practical Completion Milestone | 2026-11-26
ACT-10084 | PRJ-283 | Baseline V2 | 1.04 - Substructure Works | Authority Approval | Not Started | 174 | 1280 | 10 | 147 | 3635 | Delayed | 2 | 12 | 4 | 15 | 545 | 9018 | 2026-03-01 | 2027-06-13 | Pending Approval | 49.46 | 2026-05-06 | ML-2147 | Practical Completion Milestone | 2027-05-09
ACT-10085 | PRJ-751 | Baseline V1 | 5.06 - Substructure Works | Testing & Commissioning | Completed | 141 | 1423 | 20 | 155 | 3363 | Completed | 3 | 30 | 3 | 17 | 515 | 9024 | 2026-03-01 | 2026-09-04 | Gate Passed | 45.35 | 2026-04-20 | ML-1599 | Practical Completion Milestone | 2026-07-20
ACT-10086 | PRJ-991 | Baseline V3 | 5.05 - MEP Installation | Construction | Behind Schedule | 122 | 1875 | 18 | 172 | 3165 | Completed | 1 | 11 | 2 | 14 | 522 | 9000 | 2026-03-01 | 2026-10-04 | Gate Passed | 75.51 | 2026-03-31 | ML-7037 | Practical Completion Milestone | 2026-09-22
ACT-10087 | PRJ-765 | Baseline V1 | 2.09 - Fit-Out Works | Testing & Commissioning | Completed | 192 | 1423 | 11 | 181 | 3218 | Completed | 1 | 26 | 4 | 22 | 534 | 9021 | 2026-03-01 | 2026-06-01 | Pending Approval | 52.3 | 2026-06-28 | ML-9619 | Procurement Award | 2026-04-13
ACT-10088 | PRJ-947 | Baseline V4 | 2.08 - Substructure Works | Construction | Behind Schedule | 172 | 1625 | 14 | 172 | 3400 | Active | 1 | 12 | 5 | 27 | 530 | 9032 | 2026-03-01 | 2026-08-09 | Under Review | 89.68 | 2026-06-10 | ML-1903 | IFC Drawing Approval | 2026-07-03
ACT-10089 | PRJ-724 | Baseline V1 | 5.02 - Superstructure | Authority Approval | In Progress | 173 | 1972 | 14 | 103 | 3414 | Completed | 2 | 17 | 5 | 18 | 508 | 9013 | 2026-03-01 | 2027-04-06 | Under Review | 11.79 | 2026-05-25 | ML-9728 | IFC Drawing Approval | 2027-02-21
ACT-10090 | PRJ-780 | Baseline V3 | 1.08 - Fit-Out Works | Testing & Commissioning | Not Started | 104 | 1952 | 18 | 199 | 3444 | On Hold | 1 | 25 | 2 | 13 | 512 | 9007 | 2026-03-01 | 2027-03-28 | Gate Passed | 9.3 | 2026-05-15 | ML-2360 | Practical Completion Milestone | 2027-03-11
ACT-10091 | PRJ-773 | Baseline V3 | 3.01 - MEP Installation | Testing & Commissioning | Not Started | 189 | 1510 | 10 | 154 | 3931 | Active | 1 | 25 | 4 | 28 | 534 | 9023 | 2026-03-01 | 2027-02-20 | Pending Approval | 45.92 | 2026-06-18 | ML-2499 | Procurement Award | 2027-02-19
ACT-10092 | PRJ-488 | Baseline V4 | 4.09 - Substructure Works | Engineering Design | Completed | 176 | 1275 | 17 | 151 | 3809 | Completed | 2 | 11 | 1 | 25 | 515 | 9039 | 2026-03-01 | 2026-08-20 | Pending Approval | 23.31 | 2026-05-18 | ML-6827 | Concept Design Approval | 2026-07-17
ACT-10093 | PRJ-900 | Baseline V4 | 5.02 - Substructure Works | Procurement | Not Started | 167 | 1095 | 11 | 161 | 3580 | Completed | 2 | 23 | 5 | 26 | 500 | 9041 | 2026-03-01 | 2026-07-30 | Under Review | 67.63 | 2026-06-04 | ML-5964 | Concept Design Approval | 2026-07-02
ACT-10094 | PRJ-253 | Baseline V2 | 4.02 - Facade Installation | Procurement | Not Started | 174 | 1691 | 14 | 129 | 3938 | Delayed | 1 | 19 | 2 | 12 | 509 | 9034 | 2026-03-01 | 2027-08-19 | Gate Passed | 76.53 | 2026-05-01 | ML-3995 | Practical Completion Milestone | 2027-06-25
ACT-10095 | PRJ-625 | Baseline V2 | 2.03 - Facade Installation | Authority Approval | Behind Schedule | 109 | 1799 | 16 | 194 | 3838 | Active | 1 | 21 | 1 | 12 | 539 | 9043 | 2026-03-01 | 2027-02-10 | Under Review | 42.79 | 2026-03-29 | ML-4643 | Concept Design Approval | 2027-01-13
ACT-10096 | PRJ-152 | Baseline V1 | 2.07 - MEP Installation | Authority Approval | Completed | 184 | 1954 | 17 | 144 | 3747 | Active | 2 | 21 | 1 | 18 | 548 | 9006 | 2026-03-01 | 2027-03-16 | Gate Passed | 93.27 | 2026-05-16 | ML-9069 | Concept Design Approval | 2027-03-06
ACT-10097 | PRJ-262 | Baseline V1 | 3.09 - MEP Installation | Procurement | Not Started | 187 | 1783 | 20 | 115 | 3324 | On Hold | 3 | 23 | 4 | 29 | 520 | 9013 | 2026-03-01 | 2026-12-22 | Pending Approval | 91.74 | 2026-04-21 | ML-9883 | Practical Completion Milestone | 2026-12-19
ACT-10098 | PRJ-516 | Baseline V3 | 3.02 - Superstructure | Engineering Design | Behind Schedule | 130 | 1072 | 18 | 177 | 3730 | On Hold | 3 | 20 | 3 | 12 | 516 | 9027 | 2026-03-01 | 2026-12-25 | Pending Approval | 12.74 | 2026-03-30 | ML-1407 | Procurement Award | 2026-11-18
ACT-10099 | PRJ-866 | Baseline V2 | 1.02 - Fit-Out Works | Authority Approval | Behind Schedule | 124 | 1612 | 17 | 189 | 3458 | Active | 2 | 22 | 2 | 22 | 509 | 9016 | 2026-03-01 | 2027-06-29 | Gate Passed | 29.09 | 2026-06-15 | ML-7968 | Practical Completion Milestone | 2027-05-16
ACT-10100 | PRJ-204 | Baseline V1 | 3.02 - Facade Installation | Testing & Commissioning | In Progress | 167 | 1517 | 19 | 184 | 3024 | On Hold | 1 | 13 | 5 | 21 | 533 | 9036 | 2026-03-01 | 2027-07-06 | Under Review | 46.8 | 2026-06-23 | ML-5462 | Concept Design Approval | 2027-06-25
ACT-10101 | PRJ-142 | Baseline V4 | 2.05 - MEP Installation | Testing & Commissioning | Not Started | 158 | 1076 | 20 | 161 | 3145 | Delayed | 1 | 20 | 2 | 23 | 500 | 9025 | 2026-03-01 | 2026-10-27 | Under Review | 17.65 | 2026-03-21 | ML-8356 | IFC Drawing Approval | 2026-10-25
ACT-10102 | PRJ-650 | Baseline V4 | 1.02 - MEP Installation | Procurement | Behind Schedule | 159 | 1312 | 17 | 144 | 3392 | Delayed | 2 | 20 | 4 | 21 | 502 | 9003 | 2026-03-01 | 2027-01-24 | Under Review | 7.82 | 2026-06-25 | ML-9253 | Concept Design Approval | 2026-12-17
ACT-10103 | PRJ-543 | Baseline V1 | 4.09 - Superstructure | Authority Approval | Not Started | 130 | 1602 | 12 | 154 | 3172 | Completed | 1 | 17 | 4 | 14 | 547 | 9005 | 2026-03-01 | 2027-04-11 | Gate Passed | 0.53 | 2026-04-10 | ML-8647 | Concept Design Approval | 2027-04-07
ACT-10104 | PRJ-421 | Baseline V3 | 3.01 - Fit-Out Works | Authority Approval | In Progress | 174 | 1144 | 16 | 195 | 3539 | Delayed | 2 | 25 | 2 | 23 | 506 | 9026 | 2026-03-01 | 2026-10-20 | Pending Approval | 96.5 | 2026-03-29 | ML-5973 | Practical Completion Milestone | 2026-09-26
ACT-10105 | PRJ-262 | Baseline V1 | 4.03 - MEP Installation | Testing & Commissioning | Behind Schedule | 159 | 1220 | 17 | 200 | 3341 | Active | 1 | 15 | 4 | 17 | 541 | 9025 | 2026-03-01 | 2027-04-15 | Gate Passed | 32.86 | 2026-03-19 | ML-6318 | IFC Drawing Approval | 2027-02-20
ACT-10106 | PRJ-664 | Baseline V2 | 2.06 - Superstructure | Testing & Commissioning | Completed | 146 | 1113 | 12 | 177 | 3997 | Completed | 3 | 16 | 5 | 29 | 531 | 9003 | 2026-03-01 | 2026-07-02 | Gate Passed | 57.75 | 2026-03-28 | ML-9214 | Concept Design Approval | 2026-05-25
ACT-10107 | PRJ-701 | Baseline V4 | 4.08 - MEP Installation | Testing & Commissioning | In Progress | 156 | 1178 | 18 | 150 | 3138 | Delayed | 2 | 22 | 3 | 28 | 532 | 9034 | 2026-03-01 | 2026-10-26 | Gate Passed | 48.75 | 2026-04-08 | ML-5600 | Practical Completion Milestone | 2026-09-23
ACT-10108 | PRJ-892 | Baseline V1 | 4.03 - Facade Installation | Engineering Design | Behind Schedule | 159 | 1500 | 14 | 179 | 3396 | Completed | 1 | 13 | 1 | 20 | 517 | 9050 | 2026-03-01 | 2026-11-14 | Pending Approval | 3.69 | 2026-06-22 | ML-6841 | Practical Completion Milestone | 2026-09-23
ACT-10109 | PRJ-940 | Baseline V1 | 2.09 - Substructure Works | Engineering Design | Behind Schedule | 198 | 1959 | 17 | 122 | 3289 | Active | 1 | 13 | 1 | 25 | 536 | 9018 | 2026-03-01 | 2027-02-28 | Gate Passed | 71.52 | 2026-04-18 | ML-1689 | IFC Drawing Approval | 2027-01-28
ACT-10110 | PRJ-955 | Baseline V1 | 4.09 - Facade Installation | Procurement | Behind Schedule | 128 | 1473 | 13 | 166 | 3395 | Delayed | 2 | 19 | 3 | 20 | 529 | 9045 | 2026-03-01 | 2026-09-07 | Under Review | 89.54 | 2026-05-26 | ML-7504 | Concept Design Approval | 2026-07-29
ACT-10111 | PRJ-614 | Baseline V4 | 4.05 - Fit-Out Works | Testing & Commissioning | Completed | 158 | 1075 | 11 | 112 | 3440 | On Hold | 2 | 26 | 3 | 26 | 506 | 9014 | 2026-03-01 | 2027-07-06 | Gate Passed | 73.89 | 2026-03-24 | ML-4634 | Practical Completion Milestone | 2027-05-17
ACT-10112 | PRJ-118 | Baseline V4 | 4.01 - MEP Installation | Engineering Design | Not Started | 155 | 1850 | 15 | 109 | 3401 | On Hold | 1 | 11 | 5 | 28 | 541 | 9013 | 2026-03-01 | 2027-06-19 | Under Review | 4.98 | 2026-05-25 | ML-4554 | Practical Completion Milestone | 2027-05-28
ACT-10113 | PRJ-478 | Baseline V4 | 1.05 - Superstructure | Authority Approval | Not Started | 107 | 1463 | 19 | 150 | 3704 | On Hold | 2 | 11 | 5 | 19 | 532 | 9042 | 2026-03-01 | 2027-08-16 | Pending Approval | 40.62 | 2026-05-02 | ML-4070 | Procurement Award | 2027-07-28
ACT-10114 | PRJ-960 | Baseline V2 | 5.08 - Superstructure | Procurement | Not Started | 159 | 1191 | 18 | 110 | 3044 | Completed | 2 | 17 | 2 | 10 | 544 | 9046 | 2026-03-01 | 2026-10-18 | Pending Approval | 79.11 | 2026-03-31 | ML-5143 | Procurement Award | 2026-08-31
ACT-10115 | PRJ-437 | Baseline V1 | 2.06 - Substructure Works | Procurement | Behind Schedule | 181 | 1764 | 17 | 195 | 3166 | Delayed | 3 | 16 | 5 | 17 | 525 | 9039 | 2026-03-01 | 2027-02-27 | Under Review | 70.9 | 2026-05-25 | ML-7942 | Concept Design Approval | 2027-02-05
ACT-10116 | PRJ-111 | Baseline V3 | 3.02 - MEP Installation | Testing & Commissioning | Not Started | 119 | 1905 | 19 | 154 | 3405 | Active | 2 | 12 | 4 | 12 | 522 | 9008 | 2026-03-01 | 2026-07-13 | Gate Passed | 3.55 | 2026-04-26 | ML-4129 | Procurement Award | 2026-06-27
ACT-10117 | PRJ-722 | Baseline V3 | 5.06 - Fit-Out Works | Construction | In Progress | 104 | 1047 | 14 | 114 | 3991 | On Hold | 1 | 13 | 2 | 16 | 542 | 9025 | 2026-03-01 | 2026-07-31 | Pending Approval | 18.96 | 2026-06-13 | ML-4786 | Concept Design Approval | 2026-06-05
ACT-10118 | PRJ-102 | Baseline V4 | 1.04 - Fit-Out Works | Procurement | In Progress | 110 | 1453 | 16 | 123 | 3304 | Delayed | 3 | 14 | 5 | 17 | 523 | 9034 | 2026-03-01 | 2027-04-15 | Under Review | 57.19 | 2026-06-13 | ML-1576 | Procurement Award | 2027-03-01
ACT-10119 | PRJ-841 | Baseline V3 | 1.02 - Superstructure | Engineering Design | Not Started | 145 | 1478 | 10 | 131 | 3032 | On Hold | 1 | 23 | 3 | 15 | 529 | 9050 | 2026-03-01 | 2027-04-16 | Under Review | 1.36 | 2026-04-12 | ML-1001 | Concept Design Approval | 2027-03-18