## l1_risk_regenerated
Record Type | District | Sub-District | Portfolio | Project | Sub-Project | Project Name | BU Attributes | Project Status | Risk ID | Date Raised | Last Review | Risk Title | Risk Description | Cause | Effect | Approval Date | Risk Status | Closed Date | Risk Owner | Progress Stage | RIBA Phase | Current Rationale | Current Probability | Target Rationale | Target Probability | Current Risk Score | Current Risk Level | Target Risk Score | Target Risk Level | Current EMV | Target EMV | Current ETV | Target ETV | Exposure | Driver | Stage | Category 1 | Current Band | Category 2 | Category 3 | Category 4 | RBS | Exposure Start | Exposure End | escalation | Project Name1 | Plan ID | High level Description | Response ID | Response Owner | title | status | description | Start Date | Due Date | Days from Due | Response Due | Completed_Closed | Last updated | Planned Cost | Actual Cost | Percent Complete | Related Risk ID | Risk Title | Risk Status
Risk | Entertainment District | Evansport | Entertainment | PRJ-2001 | SUB-15 | Retail Boulevard Development | Development | Delayed | RISK-1000 | 2026-03-01 | 2026-05-19 | Delay in Authority Clearance | Regulatory approvals are not received within planned timelines. | Incomplete documentation submission and compliance gaps. | Construction start delay and milestone impact. | 2026-03-16 | Closed | 2026-05-22 | Michael Green | Handover | RIBA 3 | Limited visibility on contractor performance metrics. | 27 | Authority approvals streamlined via early engagement plan. | 22 | 108 | High | 88 | Critical | 5012741.21 | 4084455.8 | 362 | 294 | Minor | Time | Execution | Commercial | Band 2 | Procurement | Authority | Commercial | RBS-452.9 | 2026-04-19 | 2026-09-16 | Yes | Project 4 | PLAN-6612 | Implement proactive procurement strategy for long lead items. | RESP-23179 | Kelsey Murphy | Early Procurement Planning | Not Started | Identify long-lead materials during early design stages and issue advance purchase orders with supplier performance monitoring. | 2026-03-01 | 2026-05-09 | 68 | 2026-05-09 | Yes | 2026-03-02 | 1222389.9 | 1140782.69 | 93.32 | RISK-1028 | Related Risk Title 0 | Closed
Risk | Sports District | South Paula | Sports | PRJ-2002 | SUB-10 | Retail Boulevard Development | Development | Completed | RISK-1001 | 2026-03-01 | 2026-05-12 | Utility Connection Delay | Permanent power or water connections are delayed. | Coordination gaps with utility authorities. | Testing & commissioning activities postponed. | 2026-03-23 | Closed | 2026-06-11 | Matthew Ross | Execution | RIBA 2 | Dependency on external stakeholders limits immediate risk reduction. | 29 | Risk exposure reduced to acceptable levels through proactive mitigation execution. | 22 | 29 | Moderate | 22 | High | 6218505.43 | 4717486.88 | 265 | 201 | Minor | Reputation | Design | Design | Band 3 | Procurement | Procurement | Procurement | RBS-373.6 | 2026-04-26 | 2026-09-25 | Yes | Project 17 | PLAN-5035 | Improve quality assurance controls. | RESP-26365 | Kathleen Washington | QA/QC Enhancement Plan | Completed | Deploy inspection test plans (ITPs), third-party audits, and real-time quality reporting dashboards. | 2026-03-01 | 2026-05-12 | 71 | 2026-05-12 | No | 2026-03-02 | 1480665.23 | 942484.74 | 63.65 | RISK-1059 | Related Risk Title 1 | Closed
Risk | Retail District | East Marytown | Retail | PRJ-2003 | SUB-5 | Stadium Main Structure Build | Delivery | Active | RISK-1002 | 2026-03-01 | 2026-05-09 | Delay in Material Delivery | Critical construction materials are not delivered as per approved schedule. | Supplier production backlog and late procurement planning. | Schedule slippage impacting structural and finishing activities. | 2026-03-08 | Closed | 2026-05-23 | Brian Garcia DDS | Execution | RIBA 3 | Budget constraints are restricting full implementation of mitigation measures. | 79 | Quality and compliance risks controlled through strengthened QA/QC systems. | 57 | 316 | Critical | 228 | High | 3704558.77 | 2672909.49 | 72 | 51 | Minor | Time | Concept | Construction | Band 3 | Procurement | Authority | Authority | RBS-444.8 | 2026-03-13 | 2026-04-25 | Yes | Project 9 | PLAN-6377 | Enhance structured design approval workflow. | RESP-25287 | Alicia Scott | Design Review Governance | In Progress | Implement formal design review cycles with defined SLAs, digital tracking tools, and consolidated stakeholder feedback. | 2026-03-01 | 2026-04-21 | 50 | 2026-04-21 | Yes | 2026-03-02 | 598802.81 | 313141.47 | 52.29 | RISK-1036 | Related Risk Title 2 | Closed
Risk | Hospitality District | Edwardsborough | Hospitality | PRJ-2004 | SUB-10 | Retail Boulevard Development | Commercial | Active | RISK-1003 | 2026-03-01 | 2026-04-13 | Design Coordination Conflict | Clashes identified between architectural and MEP drawings. | Lack of BIM coordination prior to IFC issuance. | On-site rework and additional construction costs. | 2026-03-25 | Mitigating |  | Julie Bryant | Concept | RIBA 2 | Risk impact remains moderate due to incomplete coordination. | 65 | Residual risk maintained within approved risk appetite thresholds. | 43 | 260 | Low | 172 | Moderate | 662171.63 | 438052 | 225 | 148 | Threat | Quality | Concept | Design | Band 2 | Design | Authority | Design | RBS-380.1 | 2026-04-27 | 2026-09-10 | Yes | Project 6 | PLAN-6503 | Proactively coordinate with utility providers. | RESP-92997 | Robyn Mccarthy | Utility Early Engagement | Not Started | Initiate early application submissions and track utility connection milestones within master schedule. | 2026-03-01 | 2026-04-18 | 47 | 2026-04-18 | Yes | 2026-03-02 | 484001.35 | 378701.63 | 78.24 | RISK-1078 | Related Risk Title 3 | Mitigating
Risk | Hospitality District | North Sharonhaven | Hospitality | PRJ-2004 | SUB-14 | Retail Boulevard Development | Commercial | On Hold | RISK-1004 | 2026-03-01 | 2026-05-08 | Delay in Design Approval | IFC drawings are pending approval beyond agreed review period. | Multiple stakeholder review cycles and late consultant updates. | Contractor mobilization delay and rework risk. | 2026-03-17 | Open |  | Debra James | Design | RIBA 5 | Limited visibility on contractor performance metrics. | 56 | Financial and schedule buffers adequately protecting project milestones. | 1 | 168 | Low | 3 | High | 4790233.6 | 85539.89 | 359 | 6 | Threat | Cost | Concept | Construction | Band 1 | Authority | Authority | Construction | RBS-580.4 | 2026-03-21 | 2026-04-30 | No | Project 6 | PLAN-5529 | Strengthen interdisciplinary design coordination. | RESP-16425 | Jennifer Simpson | BIM Coordination Process | Not Started | Conduct mandatory BIM clash detection workshops before IFC issuance to eliminate on-site conflicts. | 2026-03-01 | 2026-06-07 | 97 | 2026-06-07 | Yes | 2026-03-02 | 1122517.34 | 737844.96 | 65.73 | RISK-1006 | Related Risk Title 4 | Open
Risk | Entertainment District | New Elizabethstad | Entertainment | PRJ-2006 | SUB-18 | Luxury Resort Construction | Delivery | Completed | RISK-1005 | 2026-03-01 | 2026-04-16 | Contractor Underperformance | Main contractor fails to achieve planned progress targets. | Insufficient manpower allocation and weak supervision. | Extended project duration and cost overrun risk. | 2026-03-09 | Closed | 2026-05-14 | Steve Lopez | Execution | RIBA 3 | Monitoring is reactive rather than proactive, increasing schedule uncertainty. | 33 | Authority approvals streamlined via early engagement plan. | 9 | 165 | High | 45 | High | 952764.75 | 259844.93 | 356 | 97 | Threat | Quality | Design | Commercial | Band 1 | Construction | Authority | Commercial | RBS-100.1 | 2026-05-07 | 2026-07-27 | No | Project 5 | PLAN-6546 | Improve quality assurance controls. | RESP-14996 | Walter Ramirez | QA/QC Enhancement Plan | In Progress | Deploy inspection test plans (ITPs), third-party audits, and real-time quality reporting dashboards. | 2026-03-01 | 2026-04-23 | 52 | 2026-04-23 | Yes | 2026-03-02 | 559735.3 | 448314.46 | 80.09 | RISK-1050 | Related Risk Title 5 | Closed
Risk | Entertainment District | Debramouth | Entertainment | PRJ-2007 | SUB-10 | Retail Boulevard Development | Commercial | Completed | RISK-1006 | 2026-03-01 | 2026-05-30 | Delay in Authority Clearance | Regulatory approvals are not received within planned timelines. | Incomplete documentation submission and compliance gaps. | Construction start delay and milestone impact. | 2026-03-31 | Open |  | Samuel Lowe | Execution | RIBA 3 | Interim controls reduce impact but do not eliminate root cause. | 40 | Quality and compliance risks controlled through strengthened QA/QC systems. | 14 | 80 | High | 28 | Moderate | 6456199.95 | 2259669.98 | 115 | 40 | Threat | Time | Handover | Procurement | Band 1 | Procurement | Construction | Construction | RBS-754.9 | 2026-04-21 | 2026-07-08 | Yes | Project 6 | PLAN-2501 | Ensure timely payment and cash flow management. | RESP-49466 | Ashlee Love | Financial Control Framework | Completed | Automate payment certification workflow and maintain contingency reserves to prevent site cash flow disruption. | 2026-03-01 | 2026-06-29 | 119 | 2026-06-29 | No | 2026-03-02 | 367542.64 | 336286.12 | 91.5 | RISK-1056 | Related Risk Title 6 | Open
Risk | Hospitality District | North Andrew | Hospitality | PRJ-2008 | SUB-9 | Theme Park Expansion Phase 1 | Commercial | On Hold | RISK-1007 | 2026-03-01 | 2026-06-23 | Delay in Design Approval | IFC drawings are pending approval beyond agreed review period. | Multiple stakeholder review cycles and late consultant updates. | Contractor mobilization delay and rework risk. | 2026-03-29 | Open |  | Amanda Davis | Execution | RIBA 3 | Dependency on external stakeholders limits immediate risk reduction. | 77 | Contractor performance stabilized through structured governance framework. | 29 | 231 | Critical | 87 | Low | 6945155.12 | 2615707.77 | 153 | 57 | Minor | Time | Execution | Design | Band 3 | Procurement | Design | Commercial | RBS-770.1 | 2026-04-13 | 2026-08-24 | Yes | Project 19 | PLAN-7319 | Ensure timely payment and cash flow management. | RESP-98202 | Sarah Reed | Financial Control Framework | In Progress | Automate payment certification workflow and maintain contingency reserves to prevent site cash flow disruption. | 2026-03-01 | 2026-06-17 | 107 | 2026-06-17 | No | 2026-03-02 | 1650355.71 | 832066.04 | 50.42 | RISK-1032 | Related Risk Title 7 | Open
Risk | Retail District | New Ronald | Retail | PRJ-2009 | SUB-2 | Luxury Resort Construction | Commercial | Delayed | RISK-1008 | 2026-03-01 | 2026-06-01 | Delay in Material Delivery | Critical construction materials are not delivered as per approved schedule. | Supplier production backlog and late procurement planning. | Schedule slippage impacting structural and finishing activities. | 2026-03-04 | Open |  | Gabriel Nguyen | Concept | RIBA 5 | Risk impact remains moderate due to incomplete coordination. | 33 | Residual risk maintained within approved risk appetite thresholds. | 27 | 165 | Moderate | 135 | Critical | 3897709.85 | 3189035.33 | 332 | 271 | Threat | Reputation | Design | Construction | Band 3 | Design | Design | Design | RBS-685.3 | 2026-04-11 | 2026-07-20 | No | Project 11 | PLAN-6956 | Enhance structured design approval workflow. | RESP-49439 | Connie Chang | Design Review Governance | In Progress | Implement formal design review cycles with defined SLAs, digital tracking tools, and consolidated stakeholder feedback. | 2026-03-01 | 2026-03-31 | 29 | 2026-03-31 | No | 2026-03-02 | 1889825.69 | 976508.82 | 51.67 | RISK-1093 | Related Risk Title 8 | Open
Risk | Retail District | East Denise | Retail | PRJ-2010 | SUB-5 | Stadium Main Structure Build | Commercial | Active | RISK-1009 | 2026-03-01 | 2026-04-26 | Delay in Design Approval | IFC drawings are pending approval beyond agreed review period. | Multiple stakeholder review cycles and late consultant updates. | Contractor mobilization delay and rework risk. | 2026-03-18 | Open |  | Casey Hardin | Handover | RIBA 2 | Risk exposure remains high due to ongoing delays and limited mitigation effectiveness. | 71 | Improved stakeholder coordination ensures timely approvals and execution. | 31 | 355 | Moderate | 155 | High | 9653219.07 | 4214785.79 | 62 | 27 | Opportunity | Time | Execution | Construction | Band 2 | Commercial | Construction | Commercial | RBS-265.8 | 2026-05-16 | 2026-08-25 | No | Project 1 | PLAN-1252 | Implement proactive procurement strategy for long lead items. | RESP-93865 | Kyle Raymond | Early Procurement Planning | Completed | Identify long-lead materials during early design stages and issue advance purchase orders with supplier performance monitoring. | 2026-03-01 | 2026-04-21 | 50 | 2026-04-21 | Yes | 2026-03-02 | 1056966.9 | 626201.45 | 59.25 | RISK-1037 | Related Risk Title 9 | Open
Risk | Sports District | South Donaldville | Sports | PRJ-2011 | SUB-14 | Luxury Resort Construction | Commercial | Delayed | RISK-1010 | 2026-03-01 | 2026-03-19 | Quality Non-Compliance | Constructed works fail quality inspection standards. | Weak QA/QC monitoring and supervision. | Rework, material wastage, and cost increase. | 2026-03-06 | Closed | 2026-04-01 | John Brown MD | Handover | RIBA 5 | Budget constraints are restricting full implementation of mitigation measures. | 33 | Operational readiness achieved without impacting project handover. | 29 | 165 | High | 145 | Low | 4955651.74 | 4354966.68 | 274 | 240 | Opportunity | Quality | Design | Construction | Band 1 | Commercial | Authority | Construction | RBS-799.5 | 2026-04-13 | 2026-09-14 | Yes | Project 18 | PLAN-4802 | Improve quality assurance controls. | RESP-95608 | Nicole Mora | QA/QC Enhancement Plan | Completed | Deploy inspection test plans (ITPs), third-party audits, and real-time quality reporting dashboards. | 2026-03-01 | 2026-05-30 | 89 | 2026-05-30 | No | 2026-03-02 | 891377.36 | 581046.63 | 65.19 | RISK-1076 | Related Risk Title 10 | Closed
Risk | Entertainment District | Stevensstad | Entertainment | PRJ-2012 | SUB-2 | Retail Boulevard Development | Delivery | On Hold | RISK-1011 | 2026-03-01 | 2026-05-04 | Delay in Design Approval | IFC drawings are pending approval beyond agreed review period. | Multiple stakeholder review cycles and late consultant updates. | Contractor mobilization delay and rework risk. | 2026-03-21 | Mitigating |  | Charles Sanchez | Concept | RIBA 2 | Limited visibility on contractor performance metrics. | 10 | All mitigation actions fully implemented and monitored via KPIs. | 3 | 30 | Critical | 9 | High | 1740022.88 | 522006.86 | 292 | 87 | Opportunity | Reputation | Concept | Commercial | Band 3 | Design | Design | Procurement | RBS-516.9 | 2026-05-19 | 2026-06-26 | No | Project 14 | PLAN-7242 | Strengthen site health and safety practices. | RESP-12741 | Daniel Velasquez | HSE Reinforcement Program | Not Started | Conduct mandatory safety training, periodic audits, and enforce zero-tolerance safety compliance policies. | 2026-03-01 | 2026-05-03 | 62 | 2026-05-03 | Yes | 2026-03-02 | 1265293.4 | 773536.39 | 61.13 | RISK-1045 | Related Risk Title 11 | Mitigating
Risk | Sports District | Lake Michaelborough | Sports | PRJ-2013 | SUB-11 | Retail Boulevard Development | Commercial | Completed | RISK-1012 | 2026-03-01 | 2026-04-19 | Scope Creep | Additional requirements introduced after contract award. | Uncontrolled change management process. | Budget overrun and timeline extension. | 2026-03-10 | Open |  | Jennifer Wells | Concept | RIBA 5 | Escalation mechanisms are not consistently applied across packages. | 54 | Authority approvals streamlined via early engagement plan. | 18 | 162 | High | 54 | High | 5327948.95 | 1775982.98 | 285 | 95 | Minor | Quality | Handover | Commercial | Band 2 | Design | Procurement | Authority | RBS-606.7 | 2026-03-26 | 2026-09-06 | Yes | Project 15 | PLAN-6689 | Proactively coordinate with utility providers. | RESP-60815 | Tina Williams | Utility Early Engagement | In Progress | Initiate early application submissions and track utility connection milestones within master schedule. | 2026-03-01 | 2026-06-10 | 100 | 2026-06-10 | No | 2026-03-02 | 1571239.07 | 1622849.99 | 100 | RISK-1058 | Related Risk Title 12 | Open
Risk | Entertainment District | Baileymouth | Entertainment | PRJ-2014 | SUB-13 | Retail Boulevard Development | Commercial | Completed | RISK-1013 | 2026-03-01 | 2026-06-25 | Delay in Authority Clearance | Regulatory approvals are not received within planned timelines. | Incomplete documentation submission and compliance gaps. | Construction start delay and milestone impact. | 2026-03-27 | Open |  | Annette Bryant | Concept | RIBA 1 | Current controls are partially implemented and require strengthening. | 38 | Residual risk maintained within approved risk appetite thresholds. | 24 | 190 | High | 120 | High | 8321839.25 | 5255898.47 | 101 | 63 | Opportunity | Time | Concept | Procurement | Band 1 | Procurement | Design | Construction | RBS-770.9 | 2026-04-12 | 2026-05-23 | Yes | Project 18 | PLAN-7866 | Proactively coordinate with utility providers. | RESP-17113 | Jonathan King | Utility Early Engagement | Not Started | Initiate early application submissions and track utility connection milestones within master schedule. | 2026-03-01 | 2026-06-03 | 93 | 2026-06-03 | Yes | 2026-03-02 | 643406.31 | 682807.6 | 100 | RISK-1094 | Related Risk Title 13 | Open
Risk | Entertainment District | West Chelsea | Entertainment | PRJ-2015 | SUB-15 | Theme Park Expansion Phase 1 | Development | Delayed | RISK-1014 | 2026-03-01 | 2026-06-15 | Delay in Authority Clearance | Regulatory approvals are not received within planned timelines. | Incomplete documentation submission and compliance gaps. | Construction start delay and milestone impact. | 2026-03-19 | Closed | 2026-07-01 | Sean Lambert | Execution | RIBA 5 | Mitigation actions are in progress but not yet fully embedded. | 67 | Residual risk maintained within approved risk appetite thresholds. | 53 | 268 | Critical | 212 | Moderate | 8569818.31 | 6779110.01 | 120 | 94 | Opportunity | Cost | Design | Procurement | Band 2 | Authority | Design | Construction | RBS-895.1 | 2026-03-28 | 2026-07-01 | No | Project 5 | PLAN-4345 | Strengthen coordination with approving authorities. | RESP-97233 | Gail Garza | Regulatory Engagement Plan | Completed | Establish early submission schedules, conduct pre-submission meetings, and assign a dedicated authority liaison to track approvals. | 2026-03-01 | 2026-06-10 | 100 | 2026-06-10 | No | 2026-03-02 | 1520734.2 | 1444898.55 | 95.01 | RISK-1062 | Related Risk Title 14 | Closed
Risk | Sports District | Wuside | Sports | PRJ-2016 | SUB-6 | Stadium Main Structure Build | Commercial | On Hold | RISK-1015 | 2026-03-01 | 2026-04-16 | Quality Non-Compliance | Constructed works fail quality inspection standards. | Weak QA/QC monitoring and supervision. | Rework, material wastage, and cost increase. | 2026-03-30 | Mitigating |  | Sandra Castillo | Execution | RIBA 3 | Budget constraints are restricting full implementation of mitigation measures. | 21 | Proactive monitoring system established with early warning indicators. | 18 | 63 | Moderate | 54 | Critical | 9386924.31 | 8045935.12 | 288 | 246 | Minor | Quality | Execution | Authority | Band 3 | Authority | Construction | Construction | RBS-776.3 | 2026-05-20 | 2026-09-14 | Yes | Project 7 | PLAN-7551 | Strengthen coordination with approving authorities. | RESP-85074 | Alicia Carroll | Regulatory Engagement Plan | Completed | Establish early submission schedules, conduct pre-submission meetings, and assign a dedicated authority liaison to track approvals. | 2026-03-01 | 2026-04-02 | 31 | 2026-04-02 | No | 2026-03-02 | 304080.06 | 251282.56 | 82.64 | RISK-1099 | Related Risk Title 15 | Mitigating
Risk | Retail District | Vasquezborough | Retail | PRJ-2015 | SUB-1 | Theme Park Expansion Phase 1 | Commercial | Completed | RISK-1016 | 2026-03-01 | 2026-04-09 | Utility Connection Delay | Permanent power or water connections are delayed. | Coordination gaps with utility authorities. | Testing & commissioning activities postponed. | 2026-03-06 | Open |  | Theresa Green MD | Concept | RIBA 4 | Budget constraints are restricting full implementation of mitigation measures. | 55 | Risk exposure reduced to acceptable levels through proactive mitigation execution. | 28 | 110 | Critical | 56 | Moderate | 9729995.37 | 4953452.19 | 31 | 15 | Opportunity | Cost | Execution | Authority | Band 3 | Commercial | Construction | Procurement | RBS-993.6 | 2026-04-15 | 2026-06-24 | Yes | Project 7 | PLAN-1086 | Control scope variations effectively. | RESP-21110 | Brian Miller | Change Management Framework | Not Started | Establish formal change approval committee and maintain variation impact assessment before approval. | 2026-03-01 | 2026-04-16 | 45 | 2026-04-16 | Yes | 2026-03-02 | 763618.09 | 698747.03 | 91.5 | RISK-1006 | Related Risk Title 16 | Open
Risk | Entertainment District | Lake Timothy | Entertainment | PRJ-2018 | SUB-14 | Theme Park Expansion Phase 1 | Delivery | Delayed | RISK-1017 | 2026-03-01 | 2026-05-28 | Design Coordination Conflict | Clashes identified between architectural and MEP drawings. | Lack of BIM coordination prior to IFC issuance. | On-site rework and additional construction costs. | 2026-03-22 | Open |  | Benjamin Johnson | Execution | RIBA 4 | Risk exposure remains high due to ongoing delays and limited mitigation effectiveness. | 21 | Residual risk maintained within approved risk appetite thresholds. | 10 | 21 | Low | 10 | Moderate | 1008825.58 | 480393.13 | 125 | 59 | Minor | Cost | Execution | Procurement | Band 2 | Design | Procurement | Design | RBS-564.2 | 2026-05-12 | 2026-09-13 | Yes | Project 13 | PLAN-2246 | Improve quality assurance controls. | RESP-35978 | Mr. Michael Martinez | QA/QC Enhancement Plan | Not Started | Deploy inspection test plans (ITPs), third-party audits, and real-time quality reporting dashboards. | 2026-03-01 | 2026-06-05 | 95 | 2026-06-05 | No | 2026-03-02 | 1309385.83 | 690341.35 | 52.72 | RISK-1017 | Related Risk Title 17 | Open
Risk | Sports District | North Angela | Sports | PRJ-2019 | SUB-6 | Retail Boulevard Development | Commercial | Delayed | RISK-1018 | 2026-03-01 | 2026-05-25 | Utility Connection Delay | Permanent power or water connections are delayed. | Coordination gaps with utility authorities. | Testing & commissioning activities postponed. | 2026-03-23 | Open |  | Janice Rosales | Design | RIBA 1 | Limited visibility on contractor performance metrics. | 13 | Residual risk maintained within approved risk appetite thresholds. | 7 | 65 | Critical | 35 | Moderate | 7814172.32 | 4207631.25 | 23 | 12 | Minor | Cost | Design | Commercial | Band 2 | Construction | Design | Procurement | RBS-625.9 | 2026-03-24 | 2026-06-22 | Yes | Project 5 | PLAN-5906 | Ensure timely payment and cash flow management. | RESP-85376 | Kristin Shea | Financial Control Framework | In Progress | Automate payment certification workflow and maintain contingency reserves to prevent site cash flow disruption. | 2026-03-01 | 2026-04-01 | 30 | 2026-04-01 | Yes | 2026-03-02 | 1246007.68 | 811772.48 | 65.15 | RISK-1090 | Related Risk Title 18 | Open
Risk | Retail District | Lake Richardton | Retail | PRJ-2020 | SUB-6 | Stadium Main Structure Build | Commercial | Active | RISK-1019 | 2026-03-01 | 2026-06-12 | Delay in Design Approval | IFC drawings are pending approval beyond agreed review period. | Multiple stakeholder review cycles and late consultant updates. | Contractor mobilization delay and rework risk. | 2026-03-24 | Closed | 2026-06-25 | Juan Cruz | Concept | RIBA 2 | Mitigation actions are in progress but not yet fully embedded. | 27 | Risk exposure reduced to acceptable levels through proactive mitigation execution. | 26 | 54 | Critical | 52 | Critical | 1704171.88 | 1641054.4 | 234 | 225 | Threat | Quality | Handover | Procurement | Band 3 | Procurement | Construction | Commercial | RBS-606.2 | 2026-05-04 | 2026-08-27 | Yes | Project 20 | PLAN-6819 | Proactively coordinate with utility providers. | RESP-14844 | Matthew Greer | Utility Early Engagement | Completed | Initiate early application submissions and track utility connection milestones within master schedule. | 2026-03-01 | 2026-04-16 | 45 | 2026-04-16 | Yes | 2026-03-02 | 473125.36 | 471960.62 | 99.75 | RISK-1039 | Related Risk Title 19 | Closed
Risk | Entertainment District | Berryborough | Entertainment | PRJ-2021 | SUB-18 | Water Park Infrastructure Upgrade | Delivery | Completed | RISK-1020 | 2026-03-01 | 2026-05-17 | Health & Safety Incident | Major safety incident occurs on construction site. | Non-compliance with safety procedures. | Work suspension and reputational damage. | 2026-03-26 | Closed | 2026-05-27 | Erin Spencer | Handover | RIBA 3 | Interim controls reduce impact but do not eliminate root cause. | 67 | Improved stakeholder coordination ensures timely approvals and execution. | 19 | 134 | High | 38 | High | 2049341.78 | 581156.62 | 154 | 43 | Minor | Quality | Design | Authority | Band 3 | Authority | Construction | Procurement | RBS-543.7 | 2026-03-30 | 2026-05-18 | No | Project 10 | PLAN-8860 | Proactively coordinate with utility providers. | RESP-82958 | Mary Reese | Utility Early Engagement | Completed | Initiate early application submissions and track utility connection milestones within master schedule. | 2026-03-01 | 2026-05-23 | 82 | 2026-05-23 | No | 2026-03-02 | 1263118.22 | 1253088.07 | 99.21 | RISK-1098 | Related Risk Title 20 | Closed
Risk | Entertainment District | South Miguelborough | Entertainment | PRJ-2022 | SUB-19 | Luxury Resort Construction | Delivery | Completed | RISK-1021 | 2026-03-01 | 2026-03-27 | Utility Connection Delay | Permanent power or water connections are delayed. | Coordination gaps with utility authorities. | Testing & commissioning activities postponed. | 2026-03-08 | Open |  | Alexandria Peters | Concept | RIBA 3 | Risk exposure remains high due to ongoing delays and limited mitigation effectiveness. | 13 | Financial and schedule buffers adequately protecting project milestones. | 11 | 13 | Moderate | 11 | Moderate | 1092194.81 | 924164.84 | 39 | 33 | Opportunity | Quality | Handover | Commercial | Band 3 | Procurement | Commercial | Procurement | RBS-213.3 | 2026-04-29 | 2026-10-02 | No | Project 19 | PLAN-6588 | Improve quality assurance controls. | RESP-39977 | Mr. Mark Sawyer | QA/QC Enhancement Plan | Not Started | Deploy inspection test plans (ITPs), third-party audits, and real-time quality reporting dashboards. | 2026-03-01 | 2026-04-10 | 39 | 2026-04-10 | Yes | 2026-03-02 | 573679.94 | 537690.64 | 93.73 | RISK-1071 | Related Risk Title 21 | Open
Risk | Retail District | North Roger | Retail | PRJ-2023 | SUB-1 | Luxury Resort Construction | Delivery | Delayed | RISK-1022 | 2026-03-01 | 2026-05-17 | Delay in Material Delivery | Critical construction materials are not delivered as per approved schedule. | Supplier production backlog and late procurement planning. | Schedule slippage impacting structural and finishing activities. | 2026-03-25 | Closed | 2026-05-21 | Jeffrey Fisher | Handover | RIBA 3 | Interim controls reduce impact but do not eliminate root cause. | 19 | Contractor performance stabilized through structured governance framework. | 5 | 38 | Critical | 10 | Low | 1005924.11 | 264716.87 | 305 | 80 | Minor | Cost | Concept | Commercial | Band 2 | Commercial | Procurement | Authority | RBS-497.2 | 2026-04-07 | 2026-06-21 | No | Project 9 | PLAN-6564 | Ensure timely payment and cash flow management. | RESP-54471 | Anthony Harris | Financial Control Framework | Not Started | Automate payment certification workflow and maintain contingency reserves to prevent site cash flow disruption. | 2026-03-01 | 2026-06-29 | 119 | 2026-06-29 | Yes | 2026-03-02 | 1466973.71 | 1063596.59 | 72.5 | RISK-1018 | Related Risk Title 22 | Closed
Risk | Retail District | New Kristin | Retail | PRJ-2024 | SUB-20 | Stadium Main Structure Build | Commercial | Delayed | RISK-1023 | 2026-03-01 | 2026-04-12 | Design Coordination Conflict | Clashes identified between architectural and MEP drawings. | Lack of BIM coordination prior to IFC issuance. | On-site rework and additional construction costs. | 2026-03-02 | Mitigating |  | James Gentry | Execution | RIBA 4 | Budget constraints are restricting full implementation of mitigation measures. | 69 | Quality and compliance risks controlled through strengthened QA/QC systems. | 2 | 69 | Low | 2 | Moderate | 9080900.86 | 263214.52 | 313 | 9 | Minor | Reputation | Concept | Construction | Band 2 | Procurement | Authority | Commercial | RBS-859.7 | 2026-03-14 | 2026-06-16 | Yes | Project 14 | PLAN-3916 | Proactively coordinate with utility providers. | RESP-35472 | John Campbell | Utility Early Engagement | In Progress | Initiate early application submissions and track utility connection milestones within master schedule. | 2026-03-01 | 2026-04-05 | 34 | 2026-04-05 | Yes | 2026-03-02 | 1875188.52 | 1714947.96 | 91.45 | RISK-1002 | Related Risk Title 23 | Mitigating
Risk | Hospitality District | Fitzgeraldhaven | Hospitality | PRJ-2025 | SUB-15 | Theme Park Expansion Phase 1 | Commercial | Active | RISK-1024 | 2026-03-01 | 2026-04-11 | Delay in Design Approval | IFC drawings are pending approval beyond agreed review period. | Multiple stakeholder review cycles and late consultant updates. | Contractor mobilization delay and rework risk. | 2026-03-04 | Closed | 2026-04-19 | Thomas Peterson | Concept | RIBA 5 | Escalation mechanisms are not consistently applied across packages. | 69 | Contractor performance stabilized through structured governance framework. | 26 | 138 | Low | 52 | Low | 2975531.37 | 1121214.72 | 40 | 15 | Opportunity | Reputation | Concept | Procurement | Band 1 | Design | Commercial | Design | RBS-651.9 | 2026-04-18 | 2026-06-16 | Yes | Project 9 | PLAN-6840 | Strengthen interdisciplinary design coordination. | RESP-41831 | Jeffrey Munoz | BIM Coordination Process | In Progress | Conduct mandatory BIM clash detection workshops before IFC issuance to eliminate on-site conflicts. | 2026-03-01 | 2026-06-12 | 102 | 2026-06-12 | Yes | 2026-03-02 | 861964.26 | 897149.28 | 100 | RISK-1003 | Related Risk Title 24 | Closed
Risk | Sports District | North Lisashire | Sports | PRJ-2026 | SUB-14 | Theme Park Expansion Phase 1 | Delivery | On Hold | RISK-1025 | 2026-03-01 | 2026-04-22 | Delay in Design Approval | IFC drawings are pending approval beyond agreed review period. | Multiple stakeholder review cycles and late consultant updates. | Contractor mobilization delay and rework risk. | 2026-03-11 | Open |  | Gregory Schneider | Execution | RIBA 2 | Escalation mechanisms are not consistently applied across packages. | 63 | Quality and compliance risks controlled through strengthened QA/QC systems. | 60 | 126 | Critical | 120 | High | 3365586.34 | 3205320.32 | 152 | 144 | Threat | Quality | Execution | Design | Band 3 | Commercial | Procurement | Procurement | RBS-875.7 | 2026-05-08 | 2026-09-08 | Yes | Project 20 | PLAN-3745 | Ensure timely payment and cash flow management. | RESP-48197 | Dr. Eric Flores | Financial Control Framework | Completed | Automate payment certification workflow and maintain contingency reserves to prevent site cash flow disruption. | 2026-03-01 | 2026-06-17 | 107 | 2026-06-17 | Yes | 2026-03-02 | 868226.78 | 988989.77 | 100 | RISK-1069 | Related Risk Title 25 | Open
Risk | Entertainment District | Stevenchester | Entertainment | PRJ-2027 | SUB-10 | Luxury Resort Construction | Development | Delayed | RISK-1026 | 2026-03-01 | 2026-05-15 | Health & Safety Incident | Major safety incident occurs on construction site. | Non-compliance with safety procedures. | Work suspension and reputational damage. | 2026-03-18 | Mitigating |  | Christine Schwartz | Execution | RIBA 5 | Risk exposure remains high due to ongoing delays and limited mitigation effectiveness. | 68 | All mitigation actions fully implemented and monitored via KPIs. | 62 | 68 | Moderate | 62 | Moderate | 5013521.15 | 4571151.64 | 75 | 68 | Threat | Quality | Design | Commercial | Band 1 | Procurement | Procurement | Construction | RBS-652.7 | 2026-04-15 | 2026-09-22 | Yes | Project 8 | PLAN-7373 | Strengthen site health and safety practices. | RESP-92817 | Kristin Jennings | HSE Reinforcement Program | In Progress | Conduct mandatory safety training, periodic audits, and enforce zero-tolerance safety compliance policies. | 2026-03-01 | 2026-04-18 | 47 | 2026-04-18 | No | 2026-03-02 | 1958062.98 | 1328078.08 | 67.83 | RISK-1002 | Related Risk Title 26 | Mitigating
Risk | Hospitality District | Port Michael | Hospitality | PRJ-2028 | SUB-2 | Luxury Resort Construction | Delivery | On Hold | RISK-1027 | 2026-03-01 | 2026-04-23 | Contractor Underperformance | Main contractor fails to achieve planned progress targets. | Insufficient manpower allocation and weak supervision. | Extended project duration and cost overrun risk. | 2026-03-21 | Mitigating |  | Jason Lawrence | Execution | RIBA 4 | Mitigation actions are in progress but not yet fully embedded. | 78 | Financial and schedule buffers adequately protecting project milestones. | 47 | 390 | High | 235 | High | 673802.67 | 406009.3 | 88 | 53 | Minor | Quality | Design | Authority | Band 1 | Design | Procurement | Construction | RBS-621.4 | 2026-04-07 | 2026-06-06 | No | Project 2 | PLAN-4997 | Improve quality assurance controls. | RESP-62857 | Melissa Lopez | QA/QC Enhancement Plan | Not Started | Deploy inspection test plans (ITPs), third-party audits, and real-time quality reporting dashboards. | 2026-03-01 | 2026-05-01 | 60 | 2026-05-01 | Yes | 2026-03-02 | 1924005.22 | 1311178.86 | 68.15 | RISK-1016 | Related Risk Title 27 | Mitigating
Risk | Hospitality District | Lake Gregoryhaven | Hospitality | PRJ-2029 | SUB-17 | Water Park Infrastructure Upgrade | Delivery | Delayed | RISK-1028 | 2026-03-01 | 2026-06-19 | Health & Safety Incident | Major safety incident occurs on construction site. | Non-compliance with safety procedures. | Work suspension and reputational damage. | 2026-03-22 | Mitigating |  | Angel Horton | Execution | RIBA 5 | Monitoring is reactive rather than proactive, increasing schedule uncertainty. | 44 | Authority approvals streamlined via early engagement plan. | 33 | 132 | Moderate | 99 | Critical | 4779668.3 | 3584751.22 | 158 | 118 | Threat | Cost | Execution | Construction | Band 2 | Procurement | Authority | Construction | RBS-903.8 | 2026-05-08 | 2026-06-13 | Yes | Project 4 | PLAN-3014 | Proactively coordinate with utility providers. | RESP-54716 | John Vargas | Utility Early Engagement | Not Started | Initiate early application submissions and track utility connection milestones within master schedule. | 2026-03-01 | 2026-04-19 | 48 | 2026-04-19 | No | 2026-03-02 | 1288869.83 | 1141027.71 | 88.53 | RISK-1035 | Related Risk Title 28 | Mitigating
Risk | Entertainment District | Finleystad | Entertainment | PRJ-2030 | SUB-9 | Retail Boulevard Development | Development | Delayed | RISK-1029 | 2026-03-01 | 2026-06-23 | Scope Creep | Additional requirements introduced after contract award. | Uncontrolled change management process. | Budget overrun and timeline extension. | 2026-03-31 | Closed | 2026-06-25 | Robert Sullivan | Handover | RIBA 5 | Dependency on external stakeholders limits immediate risk reduction. | 15 | Operational readiness achieved without impacting project handover. | 8 | 60 | Moderate | 32 | Low | 2157557.68 | 1150697.43 | 178 | 94 | Minor | Reputation | Handover | Authority | Band 2 | Construction | Procurement | Authority | RBS-470.5 | 2026-04-23 | 2026-07-04 | Yes | Project 9 | PLAN-8545 | Strengthen interdisciplinary design coordination. | RESP-69366 | Karen Hernandez | BIM Coordination Process | In Progress | Conduct mandatory BIM clash detection workshops before IFC issuance to eliminate on-site conflicts. | 2026-03-01 | 2026-05-10 | 69 | 2026-05-10 | Yes | 2026-03-02 | 485445.61 | 482916.61 | 99.48 | RISK-1097 | Related Risk Title 29 | Closed
Risk | Sports District | New Autumnmouth | Sports | PRJ-2031 | SUB-14 | Stadium Main Structure Build | Development | Active | RISK-1030 | 2026-03-01 | 2026-05-22 | Quality Non-Compliance | Constructed works fail quality inspection standards. | Weak QA/QC monitoring and supervision. | Rework, material wastage, and cost increase. | 2026-03-12 | Open |  | Michele Hudson | Design | RIBA 3 | Budget constraints are restricting full implementation of mitigation measures. | 45 | Improved stakeholder coordination ensures timely approvals and execution. | 8 | 180 | Low | 32 | Critical | 2179114.59 | 387398.15 | 149 | 26 | Threat | Reputation | Design | Procurement | Band 2 | Authority | Construction | Construction | RBS-701.8 | 2026-03-14 | 2026-07-25 | No | Project 19 | PLAN-7235 | Implement proactive procurement strategy for long lead items. | RESP-76668 | Chad Perry | Early Procurement Planning | In Progress | Identify long-lead materials during early design stages and issue advance purchase orders with supplier performance monitoring. | 2026-03-01 | 2026-04-18 | 47 | 2026-04-18 | No | 2026-03-02 | 465857.23 | 343107.51 | 73.65 | RISK-1061 | Related Risk Title 30 | Open
Risk | Hospitality District | Coffeyshire | Hospitality | PRJ-2032 | SUB-10 | Theme Park Expansion Phase 1 | Development | Active | RISK-1031 | 2026-03-01 | 2026-06-19 | Delay in Material Delivery | Critical construction materials are not delivered as per approved schedule. | Supplier production backlog and late procurement planning. | Schedule slippage impacting structural and finishing activities. | 2026-03-21 | Mitigating |  | Victoria Wood | Execution | RIBA 1 | Monitoring is reactive rather than proactive, increasing schedule uncertainty. | 26 | Improved stakeholder coordination ensures timely approvals and execution. | 10 | 104 | Low | 40 | High | 7679511.8 | 2953658.38 | 137 | 52 | Threat | Time | Design | Procurement | Band 3 | Procurement | Authority | Commercial | RBS-113.5 | 2026-05-10 | 2026-11-05 | Yes | Project 16 | PLAN-7138 | Strengthen site health and safety practices. | RESP-44651 | Louis Peterson | HSE Reinforcement Program | In Progress | Conduct mandatory safety training, periodic audits, and enforce zero-tolerance safety compliance policies. | 2026-03-01 | 2026-06-29 | 119 | 2026-06-29 | No | 2026-03-02 | 696363.66 | 484598.14 | 69.59 | RISK-1012 | Related Risk Title 31 | Mitigating
Risk | Retail District | Port Blakeside | Retail | PRJ-2033 | SUB-5 | Retail Boulevard Development | Development | Completed | RISK-1032 | 2026-03-01 | 2026-04-29 | Scope Creep | Additional requirements introduced after contract award. | Uncontrolled change management process. | Budget overrun and timeline extension. | 2026-03-09 | Closed | 2026-05-17 | Angela Black | Concept | RIBA 1 | Mitigation actions are in progress but not yet fully embedded. | 19 | Operational readiness achieved without impacting project handover. | 1 | 38 | Moderate | 2 | Low | 6325981.48 | 332946.39 | 297 | 15 | Minor | Quality | Concept | Procurement | Band 2 | Design | Commercial | Construction | RBS-202.6 | 2026-04-11 | 2026-07-04 | Yes | Project 7 | PLAN-6598 | Enhance structured design approval workflow. | RESP-41632 | William Rogers | Design Review Governance | Not Started | Implement formal design review cycles with defined SLAs, digital tracking tools, and consolidated stakeholder feedback. | 2026-03-01 | 2026-05-05 | 64 | 2026-05-05 | Yes | 2026-03-02 | 976512.35 | 1149123.98 | 100 | RISK-1020 | Related Risk Title 32 | Closed
Risk | Sports District | Washingtonborough | Sports | PRJ-2034 | SUB-3 | Luxury Resort Construction | Commercial | On Hold | RISK-1033 | 2026-03-01 | 2026-06-09 | Quality Non-Compliance | Constructed works fail quality inspection standards. | Weak QA/QC monitoring and supervision. | Rework, material wastage, and cost increase. | 2026-03-13 | Closed | 2026-06-16 | Sarah Collins | Execution | RIBA 2 | Dependency on external stakeholders limits immediate risk reduction. | 10 | Quality and compliance risks controlled through strengthened QA/QC systems. | 1 | 50 | Low | 5 | Moderate | 6645258.14 | 664525.81 | 55 | 5 | Threat | Time | Handover | Construction | Band 2 | Commercial | Construction | Authority | RBS-470.1 | 2026-03-27 | 2026-07-05 | Yes | Project 3 | PLAN-4267 | Strengthen coordination with approving authorities. | RESP-82543 | Jennifer Wiley | Regulatory Engagement Plan | In Progress | Establish early submission schedules, conduct pre-submission meetings, and assign a dedicated authority liaison to track approvals. | 2026-03-01 | 2026-04-02 | 31 | 2026-04-02 | Yes | 2026-03-02 | 974137.91 | 1008393.44 | 100 | RISK-1076 | Related Risk Title 33 | Closed
Risk | Entertainment District | West Jasmineview | Entertainment | PRJ-2031 | SUB-7 | Stadium Main Structure Build | Development | On Hold | RISK-1034 | 2026-03-01 | 2026-04-13 | Health & Safety Incident | Major safety incident occurs on construction site. | Non-compliance with safety procedures. | Work suspension and reputational damage. | 2026-03-29 | Open |  | Amanda Meyer | Handover | RIBA 1 | Mitigation actions are in progress but not yet fully embedded. | 56 | Improved stakeholder coordination ensures timely approvals and execution. | 53 | 280 | High | 265 | High | 3764620.98 | 3562944.86 | 255 | 241 | Opportunity | Quality | Handover | Procurement | Band 3 | Procurement | Construction | Procurement | RBS-714.2 | 2026-05-02 | 2026-08-13 | Yes | Project 12 | PLAN-8058 | Strengthen coordination with approving authorities. | RESP-45107 | Robert Robinson | Regulatory Engagement Plan | Not Started | Establish early submission schedules, conduct pre-submission meetings, and assign a dedicated authority liaison to track approvals. | 2026-03-01 | 2026-04-26 | 55 | 2026-04-26 | No | 2026-03-02 | 1681926.11 | 1826728.65 | 100 | RISK-1088 | Related Risk Title 34 | Open
Risk | Hospitality District | Martinfurt | Hospitality | PRJ-2036 | SUB-1 | Luxury Resort Construction | Commercial | On Hold | RISK-1035 | 2026-03-01 | 2026-04-16 | Delay in Design Approval | IFC drawings are pending approval beyond agreed review period. | Multiple stakeholder review cycles and late consultant updates. | Contractor mobilization delay and rework risk. | 2026-03-03 | Open |  | Angela Morris | Handover | RIBA 3 | Budget constraints are restricting full implementation of mitigation measures. | 25 | Risk exposure reduced to acceptable levels through proactive mitigation execution. | 19 | 25 | Moderate | 19 | Low | 4611222.4 | 3504529.02 | 78 | 59 | Minor | Reputation | Concept | Construction | Band 2 | Authority | Authority | Construction | RBS-761.6 | 2026-03-10 | 2026-05-12 | Yes | Project 9 | PLAN-6883 | Control scope variations effectively. | RESP-23008 | Gregory Baker | Change Management Framework | In Progress | Establish formal change approval committee and maintain variation impact assessment before approval. | 2026-03-01 | 2026-05-15 | 74 | 2026-05-15 | No | 2026-03-02 | 725077.06 | 382519.47 | 52.76 | RISK-1000 | Related Risk Title 35 | Open
Risk | Sports District | Lambfort | Sports | PRJ-2037 | SUB-1 | Luxury Resort Construction | Development | Completed | RISK-1036 | 2026-03-01 | 2026-05-01 | Utility Connection Delay | Permanent power or water connections are delayed. | Coordination gaps with utility authorities. | Testing & commissioning activities postponed. | 2026-03-16 | Closed | 2026-05-03 | Daniel Brown | Execution | RIBA 5 | Interim controls reduce impact but do not eliminate root cause. | 13 | Contractor performance stabilized through structured governance framework. | 11 | 52 | Moderate | 44 | Moderate | 9768201.37 | 8265401.16 | 85 | 71 | Opportunity | Time | Design | Construction | Band 1 | Commercial | Construction | Design | RBS-399.3 | 2026-03-18 | 2026-04-20 | Yes | Project 2 | PLAN-7092 | Improve quality assurance controls. | RESP-30086 | Michelle Kramer | QA/QC Enhancement Plan | Not Started | Deploy inspection test plans (ITPs), third-party audits, and real-time quality reporting dashboards. | 2026-03-01 | 2026-04-08 | 37 | 2026-04-08 | No | 2026-03-02 | 735211.54 | 399225.42 | 54.3 | RISK-1034 | Related Risk Title 36 | Closed
Risk | Entertainment District | Howardstad | Entertainment | PRJ-2031 | SUB-20 | Stadium Main Structure Build | Commercial | Delayed | RISK-1037 | 2026-03-01 | 2026-05-03 | Cash Flow Constraint | Delayed contractor payments affecting site progress. | Slow approval of interim payment certificates. | Reduced workforce productivity and possible work suspension. | 2026-03-18 | Open |  | Jamie Johnson | Design | RIBA 3 | Escalation mechanisms are not consistently applied across packages. | 72 | Authority approvals streamlined via early engagement plan. | 33 | 144 | Low | 66 | Low | 2162957.12 | 991355.35 | 29 | 13 | Opportunity | Cost | Design | Commercial | Band 1 | Design | Commercial | Procurement | RBS-270.5 | 2026-05-07 | 2026-09-11 | No | Project 4 | PLAN-1130 | Enhance structured design approval workflow. | RESP-73379 | Glen Simpson DVM | Design Review Governance | Completed | Implement formal design review cycles with defined SLAs, digital tracking tools, and consolidated stakeholder feedback. | 2026-03-01 | 2026-04-28 | 57 | 2026-04-28 | Yes | 2026-03-02 | 1331979.38 | 671296.2 | 50.4 | RISK-1052 | Related Risk Title 37 | Open
Risk | Hospitality District | Smithstad | Hospitality | PRJ-2039 | SUB-5 | Theme Park Expansion Phase 1 | Delivery | Delayed | RISK-1038 | 2026-03-01 | 2026-05-29 | Design Coordination Conflict | Clashes identified between architectural and MEP drawings. | Lack of BIM coordination prior to IFC issuance. | On-site rework and additional construction costs. | 2026-03-21 | Mitigating |  | Nancy Allen | Design | RIBA 4 | Interim controls reduce impact but do not eliminate root cause. | 59 | Contractor performance stabilized through structured governance framework. | 19 | 118 | Low | 38 | Critical | 6921758.31 | 2229040.81 | 266 | 85 | Opportunity | Reputation | Design | Procurement | Band 1 | Commercial | Procurement | Construction | RBS-425.3 | 2026-04-23 | 2026-07-23 | Yes | Project 1 | PLAN-6416 | Improve contractor productivity tracking. | RESP-42939 | Kristopher Mcpherson | Contractor Performance Monitoring | Completed | Introduce weekly progress dashboards, KPI monitoring, and corrective action plans for underperforming packages. | 2026-03-01 | 2026-05-21 | 80 | 2026-05-21 | No | 2026-03-02 | 1364315.33 | 1116646.18 | 81.85 | RISK-1020 | Related Risk Title 38 | Mitigating
Risk | Retail District | North Dylanborough | Retail | PRJ-2040 | SUB-13 | Retail Boulevard Development | Delivery | Completed | RISK-1039 | 2026-03-01 | 2026-05-25 | Health & Safety Incident | Major safety incident occurs on construction site. | Non-compliance with safety procedures. | Work suspension and reputational damage. | 2026-03-08 | Mitigating |  | Dana Peterson | Execution | RIBA 3 | Dependency on external stakeholders limits immediate risk reduction. | 64 | Financial and schedule buffers adequately protecting project milestones. | 47 | 256 | Low | 188 | Low | 4625744.55 | 3397031.15 | 330 | 242 | Opportunity | Quality | Handover | Authority | Band 3 | Commercial | Design | Authority | RBS-248.7 | 2026-03-31 | 2026-05-21 | No | Project 9 | PLAN-3386 | Control scope variations effectively. | RESP-13054 | Patricia Ramirez | Change Management Framework | Completed | Establish formal change approval committee and maintain variation impact assessment before approval. | 2026-03-01 | 2026-04-26 | 55 | 2026-04-26 | No | 2026-03-02 | 1097131.03 | 1213167.63 | 100 | RISK-1049 | Related Risk Title 39 | Mitigating
Risk | Retail District | New Johnchester | Retail | PRJ-2041 | SUB-17 | Theme Park Expansion Phase 1 | Commercial | Delayed | RISK-1040 | 2026-03-01 | 2026-05-03 | Delay in Material Delivery | Critical construction materials are not delivered as per approved schedule. | Supplier production backlog and late procurement planning. | Schedule slippage impacting structural and finishing activities. | 2026-03-16 | Closed | 2026-05-29 | Laura Phillips | Execution | RIBA 4 | Dependency on external stakeholders limits immediate risk reduction. | 45 | Residual risk maintained within approved risk appetite thresholds. | 13 | 90 | High | 26 | High | 2315933.55 | 669047.47 | 48 | 13 | Threat | Time | Design | Commercial | Band 3 | Procurement | Procurement | Commercial | RBS-212.5 | 2026-04-14 | 2026-08-09 | No | Project 7 | PLAN-6917 | Ensure timely payment and cash flow management. | RESP-27930 | Becky Jordan | Financial Control Framework | Completed | Automate payment certification workflow and maintain contingency reserves to prevent site cash flow disruption. | 2026-03-01 | 2026-04-07 | 36 | 2026-04-07 | No | 2026-03-02 | 1573924.26 | 1542113.64 | 97.98 | RISK-1013 | Related Risk Title 40 | Closed
Risk | Retail District | Robertton | Retail | PRJ-2042 | SUB-9 | Stadium Main Structure Build | Development | On Hold | RISK-1041 | 2026-03-01 | 2026-06-14 | Design Coordination Conflict | Clashes identified between architectural and MEP drawings. | Lack of BIM coordination prior to IFC issuance. | On-site rework and additional construction costs. | 2026-03-21 | Mitigating |  | Adam Wu | Handover | RIBA 2 | Mitigation actions are in progress but not yet fully embedded. | 15 | Authority approvals streamlined via early engagement plan. | 7 | 60 | Low | 28 | Low | 3053451.45 | 1424944.01 | 19 | 8 | Opportunity | Quality | Concept | Procurement | Band 3 | Procurement | Commercial | Authority | RBS-459.5 | 2026-04-12 | 2026-06-06 | Yes | Project 15 | PLAN-7734 | Proactively coordinate with utility providers. | RESP-89025 | Linda Estes | Utility Early Engagement | In Progress | Initiate early application submissions and track utility connection milestones within master schedule. | 2026-03-01 | 2026-05-10 | 69 | 2026-05-10 | No | 2026-03-02 | 917431.26 | 693834.7 | 75.63 | RISK-1082 | Related Risk Title 41 | Mitigating
Risk | Entertainment District | Ryanborough | Entertainment | PRJ-2043 | SUB-18 | Stadium Main Structure Build | Delivery | Active | RISK-1042 | 2026-03-01 | 2026-06-28 | Design Coordination Conflict | Clashes identified between architectural and MEP drawings. | Lack of BIM coordination prior to IFC issuance. | On-site rework and additional construction costs. | 2026-03-31 | Mitigating |  | Elizabeth Pearson | Execution | RIBA 3 | Mitigation actions are in progress but not yet fully embedded. | 20 | Risk exposure reduced to acceptable levels through proactive mitigation execution. | 9 | 80 | High | 36 | Low | 3276842.04 | 1474578.92 | 147 | 66 | Threat | Time | Concept | Design | Band 3 | Authority | Construction | Procurement | RBS-420.3 | 2026-04-16 | 2026-07-18 | Yes | Project 11 | PLAN-2998 | Proactively coordinate with utility providers. | RESP-43532 | Susan Martinez | Utility Early Engagement | Not Started | Initiate early application submissions and track utility connection milestones within master schedule. | 2026-03-01 | 2026-05-24 | 83 | 2026-05-24 | Yes | 2026-03-02 | 1444270.7 | 1118361.65 | 77.43 | RISK-1026 | Related Risk Title 42 | Mitigating
Risk | Sports District | North Loribury | Sports | PRJ-2044 | SUB-15 | Retail Boulevard Development | Commercial | Completed | RISK-1043 | 2026-03-01 | 2026-06-08 | Contractor Underperformance | Main contractor fails to achieve planned progress targets. | Insufficient manpower allocation and weak supervision. | Extended project duration and cost overrun risk. | 2026-03-16 | Open |  | Nicole Smith | Design | RIBA 3 | Monitoring is reactive rather than proactive, increasing schedule uncertainty. | 39 | Improved stakeholder coordination ensures timely approvals and execution. | 31 | 39 | Moderate | 31 | Low | 3512736.6 | 2792175.25 | 264 | 209 | Threat | Quality | Design | Authority | Band 1 | Authority | Construction | Design | RBS-999.5 | 2026-03-27 | 2026-06-19 | Yes | Project 13 | PLAN-8084 | Ensure timely payment and cash flow management. | RESP-41063 | Matthew Barron | Financial Control Framework | Completed | Automate payment certification workflow and maintain contingency reserves to prevent site cash flow disruption. | 2026-03-01 | 2026-06-05 | 95 | 2026-06-05 | No | 2026-03-02 | 854592.15 | 747972.03 | 87.52 | RISK-1039 | Related Risk Title 43 | Open
Risk | Hospitality District | Jenkinshaven | Hospitality | PRJ-2045 | SUB-7 | Water Park Infrastructure Upgrade | Commercial | Completed | RISK-1044 | 2026-03-01 | 2026-04-16 | Design Coordination Conflict | Clashes identified between architectural and MEP drawings. | Lack of BIM coordination prior to IFC issuance. | On-site rework and additional construction costs. | 2026-03-28 | Closed | 2026-04-29 | Bryan Franco | Design | RIBA 3 | Escalation mechanisms are not consistently applied across packages. | 28 | Proactive monitoring system established with early warning indicators. | 22 | 28 | Low | 22 | High | 2320489.34 | 1823241.62 | 264 | 207 | Threat | Reputation | Design | Commercial | Band 3 | Authority | Commercial | Procurement | RBS-424.5 | 2026-05-15 | 2026-10-30 | No | Project 7 | PLAN-3440 | Strengthen interdisciplinary design coordination. | RESP-69263 | Ashley Barker | BIM Coordination Process | Completed | Conduct mandatory BIM clash detection workshops before IFC issuance to eliminate on-site conflicts. | 2026-03-01 | 2026-04-29 | 58 | 2026-04-29 | No | 2026-03-02 | 75181.62 | 74809.58 | 99.51 | RISK-1032 | Related Risk Title 44 | Closed
Risk | Sports District | Diazburgh | Sports | PRJ-2046 | SUB-3 | Luxury Resort Construction | Commercial | Delayed | RISK-1045 | 2026-03-01 | 2026-05-25 | Health & Safety Incident | Major safety incident occurs on construction site. | Non-compliance with safety procedures. | Work suspension and reputational damage. | 2026-03-27 | Open |  | Nathan Peck | Execution | RIBA 1 | Budget constraints are restricting full implementation of mitigation measures. | 58 | Risk exposure reduced to acceptable levels through proactive mitigation execution. | 24 | 58 | High | 24 | Critical | 6067034.71 | 2510497.12 | 192 | 79 | Opportunity | Quality | Concept | Procurement | Band 2 | Design | Commercial | Design | RBS-620.9 | 2026-03-31 | 2026-05-11 | Yes | Project 7 | PLAN-2007 | Strengthen interdisciplinary design coordination. | RESP-55712 | Sarah Huff | BIM Coordination Process | Completed | Conduct mandatory BIM clash detection workshops before IFC issuance to eliminate on-site conflicts. | 2026-03-01 | 2026-05-21 | 80 | 2026-05-21 | No | 2026-03-02 | 1063702.85 | 618934.81 | 58.19 | RISK-1100 | Related Risk Title 45 | Open
Risk | Retail District | Kellyton | Retail | PRJ-2047 | SUB-16 | Water Park Infrastructure Upgrade | Development | Completed | RISK-1046 | 2026-03-01 | 2026-04-27 | Design Coordination Conflict | Clashes identified between architectural and MEP drawings. | Lack of BIM coordination prior to IFC issuance. | On-site rework and additional construction costs. | 2026-03-17 | Open |  | Dr. Shelly Martinez | Design | RIBA 5 | Monitoring is reactive rather than proactive, increasing schedule uncertainty. | 79 | Residual risk maintained within approved risk appetite thresholds. | 35 | 395 | Moderate | 175 | High | 8782702.42 | 3891070.69 | 304 | 134 | Threat | Quality | Handover | Construction | Band 1 | Construction | Construction | Construction | RBS-125.5 | 2026-03-21 | 2026-09-17 | No | Project 10 | PLAN-6484 | Control scope variations effectively. | RESP-37002 | Jennifer Yoder PhD | Change Management Framework | In Progress | Establish formal change approval committee and maintain variation impact assessment before approval. | 2026-03-01 | 2026-04-02 | 31 | 2026-04-02 | No | 2026-03-02 | 1544714.77 | 1449350.25 | 93.83 | RISK-1060 | Related Risk Title 46 | Open
Risk | Hospitality District | South Nicholasland | Hospitality | PRJ-2048 | SUB-12 | Luxury Resort Construction | Commercial | Delayed | RISK-1047 | 2026-03-01 | 2026-03-24 | Delay in Design Approval | IFC drawings are pending approval beyond agreed review period. | Multiple stakeholder review cycles and late consultant updates. | Contractor mobilization delay and rework risk. | 2026-03-09 | Closed | 2026-04-21 | Paige Macdonald | Design | RIBA 2 | Monitoring is reactive rather than proactive, increasing schedule uncertainty. | 49 | Authority approvals streamlined via early engagement plan. | 30 | 49 | Moderate | 30 | Low | 4915296.06 | 3009364.93 | 79 | 48 | Minor | Quality | Design | Authority | Band 3 | Commercial | Commercial | Authority | RBS-217.9 | 2026-04-17 | 2026-05-31 | No | Project 5 | PLAN-7336 | Improve quality assurance controls. | RESP-29425 | Jill Cook | QA/QC Enhancement Plan | Completed | Deploy inspection test plans (ITPs), third-party audits, and real-time quality reporting dashboards. | 2026-03-01 | 2026-05-12 | 71 | 2026-05-12 | Yes | 2026-03-02 | 377848.17 | 384015.45 | 100 | RISK-1032 | Related Risk Title 47 | Closed
Risk | Hospitality District | East Sarahville | Hospitality | PRJ-2049 | SUB-20 | Retail Boulevard Development | Commercial | Completed | RISK-1048 | 2026-03-01 | 2026-04-18 | Delay in Authority Clearance | Regulatory approvals are not received within planned timelines. | Incomplete documentation submission and compliance gaps. | Construction start delay and milestone impact. | 2026-03-03 | Open |  | Kimberly Pierce | Handover | RIBA 3 | Current controls are partially implemented and require strengthening. | 64 | Risk exposure reduced to acceptable levels through proactive mitigation execution. | 9 | 256 | Critical | 36 | Moderate | 8124850.45 | 1142557.09 | 19 | 2 | Minor | Reputation | Execution | Design | Band 2 | Construction | Construction | Commercial | RBS-628.6 | 2026-03-19 | 2026-07-11 | Yes | Project 3 | PLAN-5624 | Implement proactive procurement strategy for long lead items. | RESP-83583 | Heather Park | Early Procurement Planning | In Progress | Identify long-lead materials during early design stages and issue advance purchase orders with supplier performance monitoring. | 2026-03-01 | 2026-05-26 | 85 | 2026-05-26 | No | 2026-03-02 | 317056.08 | 267231.86 | 84.29 | RISK-1011 | Related Risk Title 48 | Open
Risk | Entertainment District | West Ralphmouth | Entertainment | PRJ-2050 | SUB-8 | Water Park Infrastructure Upgrade | Commercial | Active | RISK-1049 | 2026-03-01 | 2026-04-24 | Delay in Authority Clearance | Regulatory approvals are not received within planned timelines. | Incomplete documentation submission and compliance gaps. | Construction start delay and milestone impact. | 2026-03-26 | Closed | 2026-05-15 | John Graham | Execution | RIBA 1 | Monitoring is reactive rather than proactive, increasing schedule uncertainty. | 53 | Operational readiness achieved without impacting project handover. | 21 | 212 | Low | 84 | Moderate | 5983938.82 | 2370994.63 | 17 | 6 | Opportunity | Time | Design | Authority | Band 1 | Procurement | Design | Procurement | RBS-280.4 | 2026-04-19 | 2026-07-10 | Yes | Project 17 | PLAN-4744 | Implement proactive procurement strategy for long lead items. | RESP-96473 | Sarah Peck | Early Procurement Planning | Not Started | Identify long-lead materials during early design stages and issue advance purchase orders with supplier performance monitoring. | 2026-03-01 | 2026-05-07 | 66 | 2026-05-07 | No | 2026-03-02 | 714525.88 | 690196.77 | 96.6 | RISK-1012 | Related Risk Title 49 | Closed
Risk | Retail District | Port Rachael | Retail | PRJ-2051 | SUB-4 | Luxury Resort Construction | Delivery | Completed | RISK-1050 | 2026-03-01 | 2026-05-21 | Scope Creep | Additional requirements introduced after contract award. | Uncontrolled change management process. | Budget overrun and timeline extension. | 2026-03-08 | Closed | 2026-06-07 | Tonya Henson | Execution | RIBA 3 | Risk exposure remains high due to ongoing delays and limited mitigation effectiveness. | 33 | Risk exposure reduced to acceptable levels through proactive mitigation execution. | 22 | 165 | Critical | 110 | High | 3266970.6 | 2177980.4 | 277 | 184 | Opportunity | Time | Concept | Procurement | Band 1 | Authority | Authority | Design | RBS-843.5 | 2026-04-24 | 2026-08-22 | Yes | Project 13 | PLAN-1543 | Proactively coordinate with utility providers. | RESP-15260 | Melissa Cole | Utility Early Engagement | Not Started | Initiate early application submissions and track utility connection milestones within master schedule. | 2026-03-01 | 2026-06-16 | 106 | 2026-06-16 | No | 2026-03-02 | 1439805.88 | 1206459.44 | 83.79 | RISK-1001 | Related Risk Title 50 | Closed
Risk | Entertainment District | East Rachelmouth | Entertainment | PRJ-2052 | SUB-14 | Stadium Main Structure Build | Commercial | Delayed | RISK-1051 | 2026-03-01 | 2026-03-18 | Scope Creep | Additional requirements introduced after contract award. | Uncontrolled change management process. | Budget overrun and timeline extension. | 2026-03-07 | Open |  | Yvonne Morris | Handover | RIBA 4 | Escalation mechanisms are not consistently applied across packages. | 11 | Contractor performance stabilized through structured governance framework. | 11 | 33 | Critical | 33 | Moderate | 9870408.82 | 9870408.82 | 308 | 308 | Opportunity | Reputation | Concept | Authority | Band 2 | Procurement | Construction | Construction | RBS-228.8 | 2026-03-24 | 2026-09-18 | Yes | Project 13 | PLAN-4637 | Strengthen interdisciplinary design coordination. | RESP-92714 | Andrew Gutierrez | BIM Coordination Process | In Progress | Conduct mandatory BIM clash detection workshops before IFC issuance to eliminate on-site conflicts. | 2026-03-01 | 2026-05-31 | 90 | 2026-05-31 | Yes | 2026-03-02 | 975709.04 | 755629.2 | 77.44 | RISK-1094 | Related Risk Title 51 | Open
Risk | Hospitality District | Loganburgh | Hospitality | PRJ-2053 | SUB-11 | Luxury Resort Construction | Delivery | Delayed | RISK-1052 | 2026-03-01 | 2026-04-26 | Contractor Underperformance | Main contractor fails to achieve planned progress targets. | Insufficient manpower allocation and weak supervision. | Extended project duration and cost overrun risk. | 2026-03-08 | Open |  | Dawn Ramos | Design | RIBA 2 | Mitigation actions are in progress but not yet fully embedded. | 75 | Operational readiness achieved without impacting project handover. | 4 | 150 | Critical | 8 | Moderate | 7971587.64 | 425151.34 | 175 | 9 | Threat | Time | Design | Procurement | Band 2 | Procurement | Construction | Procurement | RBS-991.7 | 2026-05-02 | 2026-06-22 | No | Project 20 | PLAN-3950 | Strengthen site health and safety practices. | RESP-42625 | Mark Brown | HSE Reinforcement Program | Completed | Conduct mandatory safety training, periodic audits, and enforce zero-tolerance safety compliance policies. | 2026-03-01 | 2026-05-09 | 68 | 2026-05-09 | No | 2026-03-02 | 1949319.71 | 1468101.37 | 75.31 | RISK-1096 | Related Risk Title 52 | Open
Risk | Entertainment District | Tapiaport | Entertainment | PRJ-2054 | SUB-8 | Luxury Resort Construction | Delivery | Completed | RISK-1053 | 2026-03-01 | 2026-05-01 | Scope Creep | Additional requirements introduced after contract award. | Uncontrolled change management process. | Budget overrun and timeline extension. | 2026-03-13 | Closed | 2026-05-23 | William Wise | Handover | RIBA 3 | Limited visibility on contractor performance metrics. | 72 | Residual risk maintained within approved risk appetite thresholds. | 18 | 72 | Moderate | 18 | Critical | 4802178.05 | 1200544.51 | 221 | 55 | Threat | Time | Handover | Construction | Band 3 | Authority | Authority | Procurement | RBS-264.4 | 2026-03-20 | 2026-08-09 | No | Project 15 | PLAN-2848 | Improve quality assurance controls. | RESP-37812 | Phillip Collins | QA/QC Enhancement Plan | In Progress | Deploy inspection test plans (ITPs), third-party audits, and real-time quality reporting dashboards. | 2026-03-01 | 2026-06-19 | 109 | 2026-06-19 | Yes | 2026-03-02 | 1802262.12 | 1104030.51 | 61.26 | RISK-1026 | Related Risk Title 53 | Closed
Risk | Hospitality District | South Sarahhaven | Hospitality | PRJ-2055 | SUB-9 | Water Park Infrastructure Upgrade | Development | Completed | RISK-1054 | 2026-03-01 | 2026-05-27 | Delay in Material Delivery | Critical construction materials are not delivered as per approved schedule. | Supplier production backlog and late procurement planning. | Schedule slippage impacting structural and finishing activities. | 2026-03-05 | Closed | 2026-06-05 | Michelle Tucker | Design | RIBA 1 | Risk impact remains moderate due to incomplete coordination. | 16 | Operational readiness achieved without impacting project handover. | 3 | 16 | Low | 3 | Critical | 1572576.36 | 294858.07 | 14 | 2 | Opportunity | Cost | Handover | Authority | Band 1 | Design | Commercial | Authority | RBS-223.6 | 2026-03-25 | 2026-05-12 | No | Project 20 | PLAN-5348 | Enhance structured design approval workflow. | RESP-45543 | Rodney Mcintyre | Design Review Governance | Completed | Implement formal design review cycles with defined SLAs, digital tracking tools, and consolidated stakeholder feedback. | 2026-03-01 | 2026-05-10 | 69 | 2026-05-10 | No | 2026-03-02 | 1156710.25 | 700309.61 | 60.54 | RISK-1041 | Related Risk Title 54 | Closed
Risk | Entertainment District | Marytown | Entertainment | PRJ-2056 | SUB-2 | Retail Boulevard Development | Development | Completed | RISK-1055 | 2026-03-01 | 2026-04-24 | Delay in Authority Clearance | Regulatory approvals are not received within planned timelines. | Incomplete documentation submission and compliance gaps. | Construction start delay and milestone impact. | 2026-03-08 | Open |  | Amanda Smith | Execution | RIBA 1 | Dependency on external stakeholders limits immediate risk reduction. | 57 | Financial and schedule buffers adequately protecting project milestones. | 54 | 114 | Moderate | 108 | Low | 5858193.69 | 5549867.71 | 51 | 48 | Threat | Quality | Handover | Design | Band 3 | Design | Construction | Construction | RBS-607.6 | 2026-04-22 | 2026-08-01 | Yes | Project 14 | PLAN-6109 | Ensure timely payment and cash flow management. | RESP-21820 | Kayla Wilcox | Financial Control Framework | Completed | Automate payment certification workflow and maintain contingency reserves to prevent site cash flow disruption. | 2026-03-01 | 2026-04-07 | 36 | 2026-04-07 | Yes | 2026-03-02 | 1209875.85 | 1180669.38 | 97.59 | RISK-1010 | Related Risk Title 55 | Open
Risk | Entertainment District | Lake Sharon | Entertainment | PRJ-2057 | SUB-7 | Retail Boulevard Development | Development | Completed | RISK-1056 | 2026-03-01 | 2026-04-19 | Cash Flow Constraint | Delayed contractor payments affecting site progress. | Slow approval of interim payment certificates. | Reduced workforce productivity and possible work suspension. | 2026-03-27 | Open |  | Brittney Richardson | Execution | RIBA 5 | Limited visibility on contractor performance metrics. | 32 | Financial and schedule buffers adequately protecting project milestones. | 1 | 96 | High | 3 | Critical | 1612079.51 | 50377.48 | 189 | 5 | Opportunity | Reputation | Execution | Procurement | Band 3 | Authority | Procurement | Authority | RBS-227.7 | 2026-04-03 | 2026-09-24 | Yes | Project 19 | PLAN-5451 | Strengthen coordination with approving authorities. | RESP-76835 | Kathryn Cruz | Regulatory Engagement Plan | In Progress | Establish early submission schedules, conduct pre-submission meetings, and assign a dedicated authority liaison to track approvals. | 2026-03-01 | 2026-05-04 | 63 | 2026-05-04 | Yes | 2026-03-02 | 1204327.82 | 678713.38 | 56.36 | RISK-1044 | Related Risk Title 56 | Open
Risk | Hospitality District | New Elizabeth | Hospitality | PRJ-2058 | SUB-6 | Stadium Main Structure Build | Development | Completed | RISK-1057 | 2026-03-01 | 2026-04-15 | Utility Connection Delay | Permanent power or water connections are delayed. | Coordination gaps with utility authorities. | Testing & commissioning activities postponed. | 2026-03-06 | Mitigating |  | Mark Fisher | Concept | RIBA 2 | Risk exposure remains high due to ongoing delays and limited mitigation effectiveness. | 58 | Operational readiness achieved without impacting project handover. | 26 | 290 | Moderate | 130 | Critical | 8542810.87 | 3829535.91 | 213 | 95 | Opportunity | Cost | Handover | Design | Band 1 | Commercial | Commercial | Commercial | RBS-515.8 | 2026-04-18 | 2026-06-09 | Yes | Project 11 | PLAN-1222 | Ensure timely payment and cash flow management. | RESP-73359 | Nicholas Morris | Financial Control Framework | Completed | Automate payment certification workflow and maintain contingency reserves to prevent site cash flow disruption. | 2026-03-01 | 2026-05-16 | 75 | 2026-05-16 | No | 2026-03-02 | 1875935.32 | 1395394.59 | 74.38 | RISK-1008 | Related Risk Title 57 | Mitigating
Risk | Retail District | Jimmyville | Retail | PRJ-2059 | SUB-13 | Luxury Resort Construction | Commercial | Delayed | RISK-1058 | 2026-03-01 | 2026-06-09 | Delay in Material Delivery | Critical construction materials are not delivered as per approved schedule. | Supplier production backlog and late procurement planning. | Schedule slippage impacting structural and finishing activities. | 2026-03-24 | Closed | 2026-06-14 | William Sanders | Execution | RIBA 4 | Mitigation actions are in progress but not yet fully embedded. | 16 | All mitigation actions fully implemented and monitored via KPIs. | 15 | 64 | High | 60 | High | 6900017.46 | 6468766.37 | 324 | 303 | Threat | Cost | Handover | Design | Band 2 | Commercial | Procurement | Design | RBS-271.5 | 2026-05-19 | 2026-09-20 | No | Project 7 | PLAN-3617 | Control scope variations effectively. | RESP-80140 | Joan Moore | Change Management Framework | In Progress | Establish formal change approval committee and maintain variation impact assessment before approval. | 2026-03-01 | 2026-06-07 | 97 | 2026-06-07 | Yes | 2026-03-02 | 1486705.05 | 1556373.01 | 100 | RISK-1053 | Related Risk Title 58 | Closed
Risk | Entertainment District | North David | Entertainment | PRJ-2060 | SUB-18 | Retail Boulevard Development | Development | Delayed | RISK-1059 | 2026-03-01 | 2026-05-25 | Utility Connection Delay | Permanent power or water connections are delayed. | Coordination gaps with utility authorities. | Testing & commissioning activities postponed. | 2026-03-30 | Open |  | Ian Russell | Design | RIBA 5 | Dependency on external stakeholders limits immediate risk reduction. | 19 | Residual risk maintained within approved risk appetite thresholds. | 3 | 76 | High | 12 | Critical | 4467690.52 | 705424.82 | 129 | 20 | Opportunity | Time | Execution | Authority | Band 2 | Procurement | Construction | Authority | RBS-706.7 | 2026-04-24 | 2026-08-05 | No | Project 13 | PLAN-8128 | Strengthen coordination with approving authorities. | RESP-20452 | Kim Brown | Regulatory Engagement Plan | Not Started | Establish early submission schedules, conduct pre-submission meetings, and assign a dedicated authority liaison to track approvals. | 2026-03-01 | 2026-04-09 | 38 | 2026-04-09 | No | 2026-03-02 | 1747918.06 | 1003905.53 | 57.43 | RISK-1099 | Related Risk Title 59 | Open
Risk | Retail District | West Jennifer | Retail | PRJ-2061 | SUB-14 | Luxury Resort Construction | Delivery | Completed | RISK-1060 | 2026-03-01 | 2026-05-25 | Scope Creep | Additional requirements introduced after contract award. | Uncontrolled change management process. | Budget overrun and timeline extension. | 2026-03-05 | Mitigating |  | Andrea Harris | Handover | RIBA 2 | Interim controls reduce impact but do not eliminate root cause. | 50 | Operational readiness achieved without impacting project handover. | 6 | 150 | Moderate | 18 | Moderate | 920495.74 | 110459.49 | 218 | 26 | Opportunity | Quality | Handover | Design | Band 2 | Construction | Design | Design | RBS-424.7 | 2026-03-25 | 2026-07-16 | No | Project 18 | PLAN-1556 | Strengthen site health and safety practices. | RESP-93019 | Edward Tapia | HSE Reinforcement Program | Not Started | Conduct mandatory safety training, periodic audits, and enforce zero-tolerance safety compliance policies. | 2026-03-01 | 2026-04-17 | 46 | 2026-04-17 | No | 2026-03-02 | 1126298.86 | 1226496.41 | 100 | RISK-1085 | Related Risk Title 60 | Mitigating
Risk | Hospitality District | Samanthastad | Hospitality | PRJ-2062 | SUB-13 | Retail Boulevard Development | Commercial | Active | RISK-1061 | 2026-03-01 | 2026-05-18 | Delay in Design Approval | IFC drawings are pending approval beyond agreed review period. | Multiple stakeholder review cycles and late consultant updates. | Contractor mobilization delay and rework risk. | 2026-03-19 | Mitigating |  | Mathew Macias | Handover | RIBA 3 | Escalation mechanisms are not consistently applied across packages. | 15 | All mitigation actions fully implemented and monitored via KPIs. | 5 | 30 | Low | 10 | Moderate | 1889362.47 | 629787.49 | 257 | 85 | Opportunity | Cost | Concept | Authority | Band 1 | Authority | Commercial | Design | RBS-835.8 | 2026-04-19 | 2026-05-30 | No | Project 20 | PLAN-6814 | Control scope variations effectively. | RESP-65599 | Patricia Russell | Change Management Framework | In Progress | Establish formal change approval committee and maintain variation impact assessment before approval. | 2026-03-01 | 2026-04-15 | 44 | 2026-04-15 | Yes | 2026-03-02 | 836619.79 | 584397.27 | 69.85 | RISK-1097 | Related Risk Title 61 | Mitigating
Risk | Entertainment District | Lake Crystal | Entertainment | PRJ-2063 | SUB-17 | Stadium Main Structure Build | Development | Completed | RISK-1062 | 2026-03-01 | 2026-05-16 | Scope Creep | Additional requirements introduced after contract award. | Uncontrolled change management process. | Budget overrun and timeline extension. | 2026-03-04 | Open |  | Heather Warren | Concept | RIBA 2 | Risk exposure remains high due to ongoing delays and limited mitigation effectiveness. | 62 | Risk exposure reduced to acceptable levels through proactive mitigation execution. | 28 | 62 | Low | 28 | Critical | 3072669.1 | 1387657.01 | 41 | 18 | Opportunity | Reputation | Execution | Design | Band 2 | Commercial | Commercial | Construction | RBS-756.6 | 2026-04-25 | 2026-08-09 | No | Project 10 | PLAN-4641 | Control scope variations effectively. | RESP-25988 | Nicholas Turner | Change Management Framework | In Progress | Establish formal change approval committee and maintain variation impact assessment before approval. | 2026-03-01 | 2026-04-05 | 34 | 2026-04-05 | No | 2026-03-02 | 1501839.79 | 1436359.22 | 95.64 | RISK-1017 | Related Risk Title 62 | Open
Risk | Hospitality District | Williamsborough | Hospitality | PRJ-2064 | SUB-7 | Water Park Infrastructure Upgrade | Delivery | Delayed | RISK-1063 | 2026-03-01 | 2026-05-23 | Quality Non-Compliance | Constructed works fail quality inspection standards. | Weak QA/QC monitoring and supervision. | Rework, material wastage, and cost increase. | 2026-03-12 | Mitigating |  | Kristin Smith | Concept | RIBA 4 | Risk impact remains moderate due to incomplete coordination. | 33 | Contractor performance stabilized through structured governance framework. | 16 | 33 | High | 16 | High | 9832140.61 | 4767098.48 | 314 | 152 | Opportunity | Reputation | Concept | Design | Band 2 | Design | Construction | Authority | RBS-396.4 | 2026-04-05 | 2026-06-30 | No | Project 20 | PLAN-8890 | Control scope variations effectively. | RESP-72968 | Kristin Lewis | Change Management Framework | Completed | Establish formal change approval committee and maintain variation impact assessment before approval. | 2026-03-01 | 2026-05-25 | 84 | 2026-05-25 | No | 2026-03-02 | 79368.06 | 63948.52 | 80.57 | RISK-1082 | Related Risk Title 63 | Mitigating
Risk | Entertainment District | East Hector | Entertainment | PRJ-2065 | SUB-1 | Retail Boulevard Development | Development | Active | RISK-1064 | 2026-03-01 | 2026-06-09 | Scope Creep | Additional requirements introduced after contract award. | Uncontrolled change management process. | Budget overrun and timeline extension. | 2026-03-14 | Closed | 2026-06-22 | Debra Rodriguez | Execution | RIBA 4 | Risk exposure remains high due to ongoing delays and limited mitigation effectiveness. | 27 | Residual risk maintained within approved risk appetite thresholds. | 16 | 81 | Low | 48 | Low | 7615364.69 | 4512808.71 | 216 | 128 | Opportunity | Time | Handover | Commercial | Band 2 | Authority | Authority | Commercial | RBS-818.2 | 2026-04-13 | 2026-08-27 | No | Project 17 | PLAN-4112 | Ensure timely payment and cash flow management. | RESP-35467 | Sarah Howard | Financial Control Framework | Completed | Automate payment certification workflow and maintain contingency reserves to prevent site cash flow disruption. | 2026-03-01 | 2026-04-12 | 41 | 2026-04-12 | Yes | 2026-03-02 | 422886.01 | 429446.4 | 100 | RISK-1071 | Related Risk Title 64 | Closed
Risk | Retail District | East Tammyville | Retail | PRJ-2066 | SUB-17 | Luxury Resort Construction | Development | On Hold | RISK-1065 | 2026-03-01 | 2026-04-23 | Contractor Underperformance | Main contractor fails to achieve planned progress targets. | Insufficient manpower allocation and weak supervision. | Extended project duration and cost overrun risk. | 2026-03-26 | Closed | 2026-05-12 | Robert Gutierrez | Execution | RIBA 2 | Risk impact remains moderate due to incomplete coordination. | 22 | Authority approvals streamlined via early engagement plan. | 3 | 66 | Low | 9 | Critical | 4458243.48 | 607942.29 | 322 | 43 | Threat | Time | Design | Design | Band 3 | Authority | Commercial | Commercial | RBS-965.3 | 2026-05-19 | 2026-09-20 | Yes | Project 3 | PLAN-7829 | Strengthen site health and safety practices. | RESP-48705 | Angela Nelson | HSE Reinforcement Program | Not Started | Conduct mandatory safety training, periodic audits, and enforce zero-tolerance safety compliance policies. | 2026-03-01 | 2026-06-07 | 97 | 2026-06-07 | No | 2026-03-02 | 1688675.47 | 1175378.18 | 69.6 | RISK-1044 | Related Risk Title 65 | Closed
Risk | Hospitality District | East James | Hospitality | PRJ-2067 | SUB-9 | Luxury Resort Construction | Commercial | Active | RISK-1066 | 2026-03-01 | 2026-03-31 | Health & Safety Incident | Major safety incident occurs on construction site. | Non-compliance with safety procedures. | Work suspension and reputational damage. | 2026-03-13 | Open |  | Janet Hall | Handover | RIBA 5 | Escalation mechanisms are not consistently applied across packages. | 42 | All mitigation actions fully implemented and monitored via KPIs. | 13 | 42 | Low | 13 | Critical | 333702.75 | 103288.95 | 294 | 91 | Minor | Reputation | Concept | Construction | Band 3 | Design | Authority | Procurement | RBS-444.4 | 2026-04-25 | 2026-06-24 | No | Project 20 | PLAN-1977 | Improve quality assurance controls. | RESP-37859 | Courtney Lopez | QA/QC Enhancement Plan | Not Started | Deploy inspection test plans (ITPs), third-party audits, and real-time quality reporting dashboards. | 2026-03-01 | 2026-05-26 | 85 | 2026-05-26 | Yes | 2026-03-02 | 62138.03 | 74514.53 | 100 | RISK-1086 | Related Risk Title 66 | Open
Risk | Sports District | East Staceyburgh | Sports | PRJ-2068 | SUB-15 | Stadium Main Structure Build | Commercial | On Hold | RISK-1067 | 2026-03-01 | 2026-04-18 | Design Coordination Conflict | Clashes identified between architectural and MEP drawings. | Lack of BIM coordination prior to IFC issuance. | On-site rework and additional construction costs. | 2026-03-24 | Mitigating |  | Paul Padilla | Concept | RIBA 2 | Budget constraints are restricting full implementation of mitigation measures. | 71 | Quality and compliance risks controlled through strengthened QA/QC systems. | 68 | 355 | Moderate | 340 | Critical | 3906292.77 | 3741238.15 | 116 | 111 | Opportunity | Time | Concept | Procurement | Band 3 | Authority | Design | Procurement | RBS-490.5 | 2026-04-30 | 2026-06-04 | No | Project 18 | PLAN-3478 | Control scope variations effectively. | RESP-11022 | Dustin Bass | Change Management Framework | In Progress | Establish formal change approval committee and maintain variation impact assessment before approval. | 2026-03-01 | 2026-04-07 | 36 | 2026-04-07 | No | 2026-03-02 | 1091517.61 | 717686.53 | 65.75 | RISK-1056 | Related Risk Title 67 | Mitigating
Risk | Sports District | Andrewsville | Sports | PRJ-2069 | SUB-10 | Stadium Main Structure Build | Development | Active | RISK-1068 | 2026-03-01 | 2026-05-26 | Utility Connection Delay | Permanent power or water connections are delayed. | Coordination gaps with utility authorities. | Testing & commissioning activities postponed. | 2026-03-16 | Open |  | Alicia Espinoza | Design | RIBA 4 | Interim controls reduce impact but do not eliminate root cause. | 72 | Risk exposure reduced to acceptable levels through proactive mitigation execution. | 39 | 288 | Low | 156 | High | 5051005.2 | 2735961.15 | 298 | 161 | Threat | Reputation | Execution | Procurement | Band 2 | Design | Design | Design | RBS-826.8 | 2026-05-07 | 2026-07-21 | Yes | Project 2 | PLAN-1051 | Proactively coordinate with utility providers. | RESP-52901 | Donna Jackson | Utility Early Engagement | Not Started | Initiate early application submissions and track utility connection milestones within master schedule. | 2026-03-01 | 2026-04-30 | 59 | 2026-04-30 | Yes | 2026-03-02 | 1172195.75 | 903460.42 | 77.07 | RISK-1031 | Related Risk Title 68 | Open
Risk | Hospitality District | Lake Amanda | Hospitality | PRJ-2070 | SUB-7 | Water Park Infrastructure Upgrade | Delivery | Active | RISK-1069 | 2026-03-01 | 2026-05-07 | Quality Non-Compliance | Constructed works fail quality inspection standards. | Weak QA/QC monitoring and supervision. | Rework, material wastage, and cost increase. | 2026-03-17 | Closed | 2026-05-21 | Richard Williams | Design | RIBA 4 | Monitoring is reactive rather than proactive, increasing schedule uncertainty. | 19 | Residual risk maintained within approved risk appetite thresholds. | 14 | 57 | High | 42 | Low | 7592288.58 | 5594317.9 | 176 | 129 | Opportunity | Cost | Handover | Commercial | Band 3 | Procurement | Authority | Authority | RBS-666.5 | 2026-04-10 | 2026-08-21 | Yes | Project 3 | PLAN-4613 | Ensure timely payment and cash flow management. | RESP-64006 | Kelly Ramos | Financial Control Framework | Not Started | Automate payment certification workflow and maintain contingency reserves to prevent site cash flow disruption. | 2026-03-01 | 2026-05-13 | 72 | 2026-05-13 | No | 2026-03-02 | 1420267.48 | 1612472.15 | 100 | RISK-1042 | Related Risk Title 69 | Closed
Risk | Entertainment District | Christopherfort | Entertainment | PRJ-2071 | SUB-18 | Stadium Main Structure Build | Commercial | On Hold | RISK-1070 | 2026-03-01 | 2026-05-05 | Design Coordination Conflict | Clashes identified between architectural and MEP drawings. | Lack of BIM coordination prior to IFC issuance. | On-site rework and additional construction costs. | 2026-03-09 | Closed | 2026-05-17 | Mark Esparza | Handover | RIBA 1 | Current controls are partially implemented and require strengthening. | 18 | Quality and compliance risks controlled through strengthened QA/QC systems. | 9 | 36 | Low | 18 | Moderate | 2535692.06 | 1267846.03 | 353 | 176 | Minor | Reputation | Execution | Design | Band 2 | Commercial | Construction | Construction | RBS-976.2 | 2026-04-18 | 2026-10-06 | No | Project 18 | PLAN-5506 | Proactively coordinate with utility providers. | RESP-74572 | David Wilkinson | Utility Early Engagement | Completed | Initiate early application submissions and track utility connection milestones within master schedule. | 2026-03-01 | 2026-05-27 | 86 | 2026-05-27 | No | 2026-03-02 | 1931235.7 | 1596593.15 | 82.67 | RISK-1015 | Related Risk Title 70 | Closed
Risk | Sports District | Perryborough | Sports | PRJ-2072 | SUB-19 | Retail Boulevard Development | Commercial | Active | RISK-1071 | 2026-03-01 | 2026-06-21 | Quality Non-Compliance | Constructed works fail quality inspection standards. | Weak QA/QC monitoring and supervision. | Rework, material wastage, and cost increase. | 2026-03-23 | Mitigating |  | Jenny Wagner | Execution | RIBA 4 | Budget constraints are restricting full implementation of mitigation measures. | 63 | Financial and schedule buffers adequately protecting project milestones. | 19 | 126 | Moderate | 38 | Critical | 3046503.38 | 918786.73 | 171 | 51 | Opportunity | Time | Handover | Procurement | Band 3 | Commercial | Procurement | Design | RBS-567.2 | 2026-04-29 | 2026-08-27 | No | Project 16 | PLAN-7580 | Enhance structured design approval workflow. | RESP-21882 | Amanda Howell | Design Review Governance | Completed | Implement formal design review cycles with defined SLAs, digital tracking tools, and consolidated stakeholder feedback. | 2026-03-01 | 2026-04-25 | 54 | 2026-04-25 | No | 2026-03-02 | 1113535.65 | 930079.46 | 83.52 | RISK-1031 | Related Risk Title 71 | Mitigating
Risk | Retail District | Port Carlos | Retail | PRJ-2073 | SUB-1 | Luxury Resort Construction | Development | Completed | RISK-1072 | 2026-03-01 | 2026-04-22 | Cash Flow Constraint | Delayed contractor payments affecting site progress. | Slow approval of interim payment certificates. | Reduced workforce productivity and possible work suspension. | 2026-03-21 | Closed | 2026-05-22 | Henry Byrd | Handover | RIBA 2 | Limited visibility on contractor performance metrics. | 64 | Risk exposure reduced to acceptable levels through proactive mitigation execution. | 15 | 320 | Low | 75 | Low | 6478080.59 | 1518300.14 | 353 | 82 | Threat | Reputation | Design | Procurement | Band 2 | Commercial | Procurement | Procurement | RBS-191.4 | 2026-04-19 | 2026-08-07 | No | Project 12 | PLAN-3044 | Strengthen site health and safety practices. | RESP-67674 | Shelby Choi | HSE Reinforcement Program | Completed | Conduct mandatory safety training, periodic audits, and enforce zero-tolerance safety compliance policies. | 2026-03-01 | 2026-04-03 | 32 | 2026-04-03 | Yes | 2026-03-02 | 243879.64 | 240764.89 | 98.72 | RISK-1005 | Related Risk Title 72 | Closed
Risk | Sports District | Lisaville | Sports | PRJ-2074 | SUB-16 | Water Park Infrastructure Upgrade | Development | Active | RISK-1073 | 2026-03-01 | 2026-05-06 | Design Coordination Conflict | Clashes identified between architectural and MEP drawings. | Lack of BIM coordination prior to IFC issuance. | On-site rework and additional construction costs. | 2026-03-06 | Mitigating |  | Mark Anderson | Concept | RIBA 5 | Risk impact remains moderate due to incomplete coordination. | 54 | All mitigation actions fully implemented and monitored via KPIs. | 33 | 270 | Critical | 165 | Moderate | 5988294.47 | 3659513.29 | 245 | 149 | Minor | Quality | Concept | Procurement | Band 3 | Procurement | Design | Construction | RBS-165.9 | 2026-03-22 | 2026-06-20 | No | Project 11 | PLAN-4419 | Control scope variations effectively. | RESP-96868 | Kathleen Murray | Change Management Framework | Not Started | Establish formal change approval committee and maintain variation impact assessment before approval. | 2026-03-01 | 2026-05-29 | 88 | 2026-05-29 | Yes | 2026-03-02 | 1483190.29 | 1593206.77 | 100 | RISK-1030 | Related Risk Title 73 | Mitigating
Risk | Retail District | South Ashleyfort | Retail | PRJ-2075 | SUB-8 | Retail Boulevard Development | Commercial | Completed | RISK-1074 | 2026-03-01 | 2026-04-25 | Utility Connection Delay | Permanent power or water connections are delayed. | Coordination gaps with utility authorities. | Testing & commissioning activities postponed. | 2026-03-27 | Closed | 2026-05-13 | Keith Baker | Design | RIBA 5 | Mitigation actions are in progress but not yet fully embedded. | 21 | Residual risk maintained within approved risk appetite thresholds. | 19 | 63 | Critical | 57 | Critical | 1421057.91 | 1285719.06 | 59 | 53 | Threat | Reputation | Handover | Procurement | Band 3 | Commercial | Commercial | Design | RBS-727.5 | 2026-04-05 | 2026-08-08 | No | Project 8 | PLAN-1391 | Enhance structured design approval workflow. | RESP-45468 | Tyler Johnson | Design Review Governance | Not Started | Implement formal design review cycles with defined SLAs, digital tracking tools, and consolidated stakeholder feedback. | 2026-03-01 | 2026-06-07 | 97 | 2026-06-07 | No | 2026-03-02 | 516405.16 | 578925.74 | 100 | RISK-1048 | Related Risk Title 74 | Closed
Risk | Sports District | North Samanthafurt | Sports | PRJ-2076 | SUB-12 | Stadium Main Structure Build | Commercial | Completed | RISK-1075 | 2026-03-01 | 2026-06-03 | Scope Creep | Additional requirements introduced after contract award. | Uncontrolled change management process. | Budget overrun and timeline extension. | 2026-03-26 | Closed | 2026-06-22 | John Davis | Handover | RIBA 2 | Escalation mechanisms are not consistently applied across packages. | 28 | Residual risk maintained within approved risk appetite thresholds. | 27 | 112 | Moderate | 108 | High | 9814123.31 | 9463618.91 | 68 | 65 | Minor | Cost | Handover | Commercial | Band 1 | Commercial | Authority | Design | RBS-815.2 | 2026-04-17 | 2026-09-07 | No | Project 19 | PLAN-2453 | Strengthen interdisciplinary design coordination. | RESP-16549 | William Phillips | BIM Coordination Process | In Progress | Conduct mandatory BIM clash detection workshops before IFC issuance to eliminate on-site conflicts. | 2026-03-01 | 2026-04-18 | 47 | 2026-04-18 | Yes | 2026-03-02 | 1292820.43 | 1306607.67 | 100 | RISK-1089 | Related Risk Title 75 | Closed
Risk | Entertainment District | Smithside | Entertainment | PRJ-2077 | SUB-1 | Water Park Infrastructure Upgrade | Commercial | Completed | RISK-1076 | 2026-03-01 | 2026-05-08 | Delay in Authority Clearance | Regulatory approvals are not received within planned timelines. | Incomplete documentation submission and compliance gaps. | Construction start delay and milestone impact. | 2026-03-14 | Open |  | Mr. Nathan Richardson | Execution | RIBA 5 | Dependency on external stakeholders limits immediate risk reduction. | 11 | Improved stakeholder coordination ensures timely approvals and execution. | 4 | 55 | High | 20 | High | 9627916.39 | 3501060.51 | 46 | 16 | Opportunity | Time | Handover | Construction | Band 1 | Construction | Authority | Procurement | RBS-924.7 | 2026-04-29 | 2026-07-18 | No | Project 11 | PLAN-4610 | Strengthen interdisciplinary design coordination. | RESP-14368 | Jane Williams | BIM Coordination Process | Completed | Conduct mandatory BIM clash detection workshops before IFC issuance to eliminate on-site conflicts. | 2026-03-01 | 2026-06-21 | 111 | 2026-06-21 | No | 2026-03-02 | 658240.29 | 485895.09 | 73.82 | RISK-1023 | Related Risk Title 76 | Open
Risk | Retail District | West Chelseyport | Retail | PRJ-2078 | SUB-3 | Luxury Resort Construction | Commercial | Delayed | RISK-1077 | 2026-03-01 | 2026-05-23 | Contractor Underperformance | Main contractor fails to achieve planned progress targets. | Insufficient manpower allocation and weak supervision. | Extended project duration and cost overrun risk. | 2026-03-24 | Mitigating |  | Kayla Ortega | Handover | RIBA 2 | Dependency on external stakeholders limits immediate risk reduction. | 17 | Contractor performance stabilized through structured governance framework. | 3 | 51 | Low | 9 | Moderate | 7435015.08 | 1312061.48 | 22 | 3 | Opportunity | Quality | Concept | Design | Band 3 | Authority | Construction | Procurement | RBS-191.1 | 2026-05-23 | 2026-09-24 | No | Project 9 | PLAN-5204 | Implement proactive procurement strategy for long lead items. | RESP-42538 | Amanda Snow | Early Procurement Planning | Completed | Identify long-lead materials during early design stages and issue advance purchase orders with supplier performance monitoring. | 2026-03-01 | 2026-04-18 | 47 | 2026-04-18 | No | 2026-03-02 | 922709.45 | 727500.35 | 78.84 | RISK-1067 | Related Risk Title 77 | Mitigating
Risk | Entertainment District | Riverastad | Entertainment | PRJ-2079 | SUB-2 | Stadium Main Structure Build | Development | Completed | RISK-1078 | 2026-03-01 | 2026-05-11 | Contractor Underperformance | Main contractor fails to achieve planned progress targets. | Insufficient manpower allocation and weak supervision. | Extended project duration and cost overrun risk. | 2026-03-02 | Open |  | Jaime Blake | Execution | RIBA 2 | Budget constraints are restricting full implementation of mitigation measures. | 57 | Risk exposure reduced to acceptable levels through proactive mitigation execution. | 27 | 114 | Moderate | 54 | Low | 393029.98 | 186172.1 | 61 | 28 | Opportunity | Cost | Execution | Procurement | Band 2 | Commercial | Procurement | Construction | RBS-419.2 | 2026-03-31 | 2026-08-02 | Yes | Project 7 | PLAN-7833 | Strengthen site health and safety practices. | RESP-90524 | Michael Henson | HSE Reinforcement Program | In Progress | Conduct mandatory safety training, periodic audits, and enforce zero-tolerance safety compliance policies. | 2026-03-01 | 2026-06-28 | 118 | 2026-06-28 | Yes | 2026-03-02 | 1394630.82 | 1146442.71 | 82.2 | RISK-1037 | Related Risk Title 78 | Open
Risk | Retail District | Donaldtown | Retail | PRJ-2080 | SUB-17 | Luxury Resort Construction | Development | On Hold | RISK-1079 | 2026-03-01 | 2026-05-22 | Cash Flow Constraint | Delayed contractor payments affecting site progress. | Slow approval of interim payment certificates. | Reduced workforce productivity and possible work suspension. | 2026-03-17 | Closed | 2026-06-06 | Ronald Long | Design | RIBA 4 | Limited visibility on contractor performance metrics. | 22 | Financial and schedule buffers adequately protecting project milestones. | 4 | 44 | Low | 8 | Low | 2140364.03 | 389157.1 | 206 | 37 | Minor | Time | Handover | Authority | Band 1 | Construction | Construction | Procurement | RBS-423.8 | 2026-04-02 | 2026-05-24 | No | Project 5 | PLAN-7992 | Ensure timely payment and cash flow management. | RESP-37360 | Timothy Smith | Financial Control Framework | In Progress | Automate payment certification workflow and maintain contingency reserves to prevent site cash flow disruption. | 2026-03-01 | 2026-06-22 | 112 | 2026-06-22 | Yes | 2026-03-02 | 591488.42 | 503266.98 | 85.08 | RISK-1000 | Related Risk Title 79 | Closed
Risk | Retail District | New Ericchester | Retail | PRJ-2081 | SUB-15 | Luxury Resort Construction | Delivery | Active | RISK-1080 | 2026-03-01 | 2026-05-28 | Health & Safety Incident | Major safety incident occurs on construction site. | Non-compliance with safety procedures. | Work suspension and reputational damage. | 2026-03-30 | Mitigating |  | Thomas Hale | Design | RIBA 4 | Escalation mechanisms are not consistently applied across packages. | 11 | Risk exposure reduced to acceptable levels through proactive mitigation execution. | 6 | 11 | Critical | 6 | High | 1587389.13 | 865848.62 | 191 | 104 | Opportunity | Reputation | Execution | Authority | Band 2 | Construction | Commercial | Commercial | RBS-162.6 | 2026-04-11 | 2026-10-03 | Yes | Project 3 | PLAN-3321 | Implement proactive procurement strategy for long lead items. | RESP-91448 | Elizabeth Short | Early Procurement Planning | In Progress | Identify long-lead materials during early design stages and issue advance purchase orders with supplier performance monitoring. | 2026-03-01 | 2026-06-16 | 106 | 2026-06-16 | No | 2026-03-02 | 806157.37 | 448152.75 | 55.59 | RISK-1097 | Related Risk Title 80 | Mitigating
Risk | Entertainment District | Port Dillon | Entertainment | PRJ-2082 | SUB-15 | Luxury Resort Construction | Delivery | Delayed | RISK-1081 | 2026-03-01 | 2026-04-22 | Utility Connection Delay | Permanent power or water connections are delayed. | Coordination gaps with utility authorities. | Testing & commissioning activities postponed. | 2026-03-25 | Closed | 2026-05-21 | Michael Jackson | Execution | RIBA 5 | Dependency on external stakeholders limits immediate risk reduction. | 54 | All mitigation actions fully implemented and monitored via KPIs. | 12 | 54 | Moderate | 12 | Critical | 9639329.57 | 2142073.24 | 91 | 20 | Threat | Cost | Execution | Procurement | Band 3 | Design | Design | Procurement | RBS-545.8 | 2026-05-06 | 2026-10-03 | Yes | Project 8 | PLAN-4310 | Strengthen site health and safety practices. | RESP-75190 | Mitchell Morton | HSE Reinforcement Program | Not Started | Conduct mandatory safety training, periodic audits, and enforce zero-tolerance safety compliance policies. | 2026-03-01 | 2026-05-14 | 73 | 2026-05-14 | Yes | 2026-03-02 | 851701.86 | 593728.41 | 69.71 | RISK-1085 | Related Risk Title 81 | Closed
Risk | Retail District | Port Jose | Retail | PRJ-2083 | SUB-2 | Theme Park Expansion Phase 1 | Development | On Hold | RISK-1082 | 2026-03-01 | 2026-05-13 | Cash Flow Constraint | Delayed contractor payments affecting site progress. | Slow approval of interim payment certificates. | Reduced workforce productivity and possible work suspension. | 2026-03-07 | Closed | 2026-06-09 | Margaret Mcmahon | Execution | RIBA 2 | Limited visibility on contractor performance metrics. | 38 | Improved stakeholder coordination ensures timely approvals and execution. | 2 | 190 | Moderate | 10 | Low | 188367.93 | 9914.1 | 283 | 14 | Minor | Quality | Concept | Design | Band 3 | Authority | Commercial | Commercial | RBS-192.4 | 2026-03-27 | 2026-05-07 | Yes | Project 5 | PLAN-4593 | Improve contractor productivity tracking. | RESP-50101 | Patrick Cervantes | Contractor Performance Monitoring | In Progress | Introduce weekly progress dashboards, KPI monitoring, and corrective action plans for underperforming packages. | 2026-03-01 | 2026-05-27 | 86 | 2026-05-27 | Yes | 2026-03-02 | 1883638.33 | 1677942.16 | 89.08 | RISK-1040 | Related Risk Title 82 | Closed
Risk | Entertainment District | Norrisside | Entertainment | PRJ-2084 | SUB-5 | Retail Boulevard Development | Development | On Hold | RISK-1083 | 2026-03-01 | 2026-05-21 | Delay in Material Delivery | Critical construction materials are not delivered as per approved schedule. | Supplier production backlog and late procurement planning. | Schedule slippage impacting structural and finishing activities. | 2026-03-13 | Mitigating |  | Isaac Black | Design | RIBA 5 | Risk exposure remains high due to ongoing delays and limited mitigation effectiveness. | 44 | Contractor performance stabilized through structured governance framework. | 31 | 176 | Critical | 124 | Low | 4503506.04 | 3172924.71 | 113 | 79 | Minor | Time | Design | Authority | Band 2 | Procurement | Authority | Authority | RBS-626.2 | 2026-04-02 | 2026-08-07 | Yes | Project 12 | PLAN-3035 | Control scope variations effectively. | RESP-43247 | Kathryn Singh MD | Change Management Framework | In Progress | Establish formal change approval committee and maintain variation impact assessment before approval. | 2026-03-01 | 2026-04-05 | 34 | 2026-04-05 | Yes | 2026-03-02 | 1470686.12 | 1650260.23 | 100 | RISK-1098 | Related Risk Title 83 | Mitigating
Risk | Entertainment District | New Scottmouth | Entertainment | PRJ-2085 | SUB-3 | Luxury Resort Construction | Delivery | Delayed | RISK-1084 | 2026-03-01 | 2026-05-03 | Contractor Underperformance | Main contractor fails to achieve planned progress targets. | Insufficient manpower allocation and weak supervision. | Extended project duration and cost overrun risk. | 2026-03-14 | Open |  | Gregory Flores | Design | RIBA 2 | Current controls are partially implemented and require strengthening. | 25 | Improved stakeholder coordination ensures timely approvals and execution. | 18 | 100 | Moderate | 72 | High | 4224179.13 | 3041408.97 | 355 | 255 | Threat | Time | Execution | Construction | Band 1 | Authority | Commercial | Authority | RBS-185.3 | 2026-04-06 | 2026-06-19 | Yes | Project 6 | PLAN-1336 | Strengthen coordination with approving authorities. | RESP-76514 | Joseph Rodriguez | Regulatory Engagement Plan | In Progress | Establish early submission schedules, conduct pre-submission meetings, and assign a dedicated authority liaison to track approvals. | 2026-03-01 | 2026-05-31 | 90 | 2026-05-31 | Yes | 2026-03-02 | 320211.15 | 221984.48 | 69.32 | RISK-1037 | Related Risk Title 84 | Open
Risk | Sports District | New Robertmouth | Sports | PRJ-2086 | SUB-9 | Luxury Resort Construction | Development | On Hold | RISK-1085 | 2026-03-01 | 2026-05-01 | Contractor Underperformance | Main contractor fails to achieve planned progress targets. | Insufficient manpower allocation and weak supervision. | Extended project duration and cost overrun risk. | 2026-03-06 | Closed | 2026-05-13 | Rachel Gill | Execution | RIBA 2 | Monitoring is reactive rather than proactive, increasing schedule uncertainty. | 20 | Contractor performance stabilized through structured governance framework. | 1 | 80 | Critical | 4 | High | 8446459.74 | 422322.99 | 16 | 0 | Opportunity | Quality | Handover | Authority | Band 2 | Design | Design | Design | RBS-583.5 | 2026-03-12 | 2026-06-22 | No | Project 16 | PLAN-2647 | Ensure timely payment and cash flow management. | RESP-50889 | Anthony Escobar | Financial Control Framework | Completed | Automate payment certification workflow and maintain contingency reserves to prevent site cash flow disruption. | 2026-03-01 | 2026-05-03 | 62 | 2026-05-03 | No | 2026-03-02 | 585039.06 | 559756.12 | 95.68 | RISK-1002 | Related Risk Title 85 | Closed
Risk | Hospitality District | Lisaland | Hospitality | PRJ-2087 | SUB-5 | Theme Park Expansion Phase 1 | Delivery | Completed | RISK-1086 | 2026-03-01 | 2026-03-16 | Utility Connection Delay | Permanent power or water connections are delayed. | Coordination gaps with utility authorities. | Testing & commissioning activities postponed. | 2026-03-02 | Mitigating |  | Jerry Wood | Design | RIBA 3 | Risk impact remains moderate due to incomplete coordination. | 46 | Proactive monitoring system established with early warning indicators. | 25 | 92 | Moderate | 50 | High | 3234899.72 | 1758097.67 | 264 | 143 | Threat | Time | Design | Construction | Band 3 | Procurement | Procurement | Procurement | RBS-821.8 | 2026-03-27 | 2026-08-23 | Yes | Project 8 | PLAN-7764 | Ensure timely payment and cash flow management. | RESP-89796 | Felicia Bowman | Financial Control Framework | Not Started | Automate payment certification workflow and maintain contingency reserves to prevent site cash flow disruption. | 2026-03-01 | 2026-05-29 | 88 | 2026-05-29 | Yes | 2026-03-02 | 1901705.09 | 1864488.3 | 98.04 | RISK-1023 | Related Risk Title 86 | Mitigating
Risk | Hospitality District | South Mary | Hospitality | PRJ-2088 | SUB-7 | Retail Boulevard Development | Commercial | Delayed | RISK-1087 | 2026-03-01 | 2026-03-28 | Scope Creep | Additional requirements introduced after contract award. | Uncontrolled change management process. | Budget overrun and timeline extension. | 2026-03-14 | Closed | 2026-03-31 | Kevin Gutierrez | Concept | RIBA 2 | Budget constraints are restricting full implementation of mitigation measures. | 34 | Risk exposure reduced to acceptable levels through proactive mitigation execution. | 11 | 68 | Low | 22 | High | 8746605.75 | 2829784.21 | 124 | 40 | Minor | Cost | Execution | Commercial | Band 3 | Authority | Authority | Procurement | RBS-693.7 | 2026-03-17 | 2026-05-24 | Yes | Project 9 | PLAN-9355 | Strengthen site health and safety practices. | RESP-76002 | Jonathan Jackson | HSE Reinforcement Program | Not Started | Conduct mandatory safety training, periodic audits, and enforce zero-tolerance safety compliance policies. | 2026-03-01 | 2026-05-26 | 85 | 2026-05-26 | Yes | 2026-03-02 | 1376235.51 | 1333644.8 | 96.91 | RISK-1027 | Related Risk Title 87 | Closed
Risk | Retail District | Robinsonton | Retail | PRJ-2089 | SUB-19 | Theme Park Expansion Phase 1 | Delivery | Completed | RISK-1088 | 2026-03-01 | 2026-03-30 | Quality Non-Compliance | Constructed works fail quality inspection standards. | Weak QA/QC monitoring and supervision. | Rework, material wastage, and cost increase. | 2026-03-03 | Open |  | William Oconnell | Execution | RIBA 3 | Monitoring is reactive rather than proactive, increasing schedule uncertainty. | 40 | Risk exposure reduced to acceptable levels through proactive mitigation execution. | 35 | 200 | Critical | 175 | High | 764983.97 | 669360.97 | 152 | 133 | Opportunity | Reputation | Design | Construction | Band 1 | Design | Procurement | Construction | RBS-402.3 | 2026-03-08 | 2026-05-31 | Yes | Project 13 | PLAN-9713 | Enhance structured design approval workflow. | RESP-83363 | Karen Chavez | Design Review Governance | Completed | Implement formal design review cycles with defined SLAs, digital tracking tools, and consolidated stakeholder feedback. | 2026-03-01 | 2026-06-25 | 115 | 2026-06-25 | No | 2026-03-02 | 1743483.44 | 1337337.68 | 76.7 | RISK-1063 | Related Risk Title 88 | Open
Risk | Hospitality District | West Robertborough | Hospitality | PRJ-2090 | SUB-20 | Theme Park Expansion Phase 1 | Development | Completed | RISK-1089 | 2026-03-01 | 2026-04-19 | Contractor Underperformance | Main contractor fails to achieve planned progress targets. | Insufficient manpower allocation and weak supervision. | Extended project duration and cost overrun risk. | 2026-03-08 | Mitigating |  | Brittany Patterson | Handover | RIBA 5 | Limited visibility on contractor performance metrics. | 58 | Authority approvals streamlined via early engagement plan. | 28 | 174 | High | 84 | High | 3077579 | 1485727.79 | 129 | 62 | Threat | Quality | Concept | Design | Band 2 | Construction | Authority | Authority | RBS-507.2 | 2026-04-28 | 2026-07-23 | No | Project 15 | PLAN-9269 | Strengthen site health and safety practices. | RESP-14849 | Carla Levy | HSE Reinforcement Program | Completed | Conduct mandatory safety training, periodic audits, and enforce zero-tolerance safety compliance policies. | 2026-03-01 | 2026-05-09 | 68 | 2026-05-09 | No | 2026-03-02 | 1956552.36 | 1515983.49 | 77.48 | RISK-1060 | Related Risk Title 89 | Mitigating
Risk | Retail District | New Johntown | Retail | PRJ-2091 | SUB-6 | Stadium Main Structure Build | Delivery | On Hold | RISK-1090 | 2026-03-01 | 2026-06-17 | Design Coordination Conflict | Clashes identified between architectural and MEP drawings. | Lack of BIM coordination prior to IFC issuance. | On-site rework and additional construction costs. | 2026-03-30 | Open |  | James Rodriguez | Concept | RIBA 2 | Risk impact remains moderate due to incomplete coordination. | 64 | Authority approvals streamlined via early engagement plan. | 7 | 256 | Moderate | 28 | Moderate | 5557360.02 | 607836.25 | 34 | 3 | Threat | Reputation | Execution | Procurement | Band 2 | Commercial | Authority | Procurement | RBS-606.8 | 2026-04-21 | 2026-07-16 | No | Project 19 | PLAN-5924 | Strengthen interdisciplinary design coordination. | RESP-93232 | Charles Banks | BIM Coordination Process | Not Started | Conduct mandatory BIM clash detection workshops before IFC issuance to eliminate on-site conflicts. | 2026-03-01 | 2026-06-16 | 106 | 2026-06-16 | No | 2026-03-02 | 550175.83 | 555967.27 | 100 | RISK-1028 | Related Risk Title 90 | Open
Risk | Entertainment District | Amyberg | Entertainment | PRJ-2092 | SUB-10 | Retail Boulevard Development | Commercial | Delayed | RISK-1091 | 2026-03-01 | 2026-04-14 | Contractor Underperformance | Main contractor fails to achieve planned progress targets. | Insufficient manpower allocation and weak supervision. | Extended project duration and cost overrun risk. | 2026-03-02 | Closed | 2026-05-14 | Kristin Ingram | Design | RIBA 1 | Budget constraints are restricting full implementation of mitigation measures. | 76 | Risk exposure reduced to acceptable levels through proactive mitigation execution. | 32 | 228 | High | 96 | Critical | 6488550.89 | 2732021.43 | 24 | 10 | Threat | Reputation | Execution | Commercial | Band 1 | Construction | Authority | Procurement | RBS-176.1 | 2026-03-05 | 2026-06-28 | Yes | Project 5 | PLAN-5917 | Strengthen interdisciplinary design coordination. | RESP-20230 | Matthew Johnson | BIM Coordination Process | In Progress | Conduct mandatory BIM clash detection workshops before IFC issuance to eliminate on-site conflicts. | 2026-03-01 | 2026-04-09 | 38 | 2026-04-09 | No | 2026-03-02 | 810945.77 | 408315.06 | 50.35 | RISK-1049 | Related Risk Title 91 | Closed
Risk | Entertainment District | North Nathanielchester | Entertainment | PRJ-2093 | SUB-10 | Luxury Resort Construction | Commercial | On Hold | RISK-1092 | 2026-03-01 | 2026-05-16 | Health & Safety Incident | Major safety incident occurs on construction site. | Non-compliance with safety procedures. | Work suspension and reputational damage. | 2026-03-31 | Open |  | Lindsey Houston | Execution | RIBA 2 | Dependency on external stakeholders limits immediate risk reduction. | 56 | Risk exposure reduced to acceptable levels through proactive mitigation execution. | 43 | 224 | Critical | 172 | Low | 5020853.74 | 3855298.41 | 98 | 75 | Threat | Quality | Handover | Design | Band 1 | Procurement | Authority | Procurement | RBS-993.3 | 2026-04-14 | 2026-07-08 | Yes | Project 13 | PLAN-1893 | Strengthen coordination with approving authorities. | RESP-75166 | Kristen Austin | Regulatory Engagement Plan | Not Started | Establish early submission schedules, conduct pre-submission meetings, and assign a dedicated authority liaison to track approvals. | 2026-03-01 | 2026-06-18 | 108 | 2026-06-18 | No | 2026-03-02 | 1747769.4 | 1633952.94 | 93.49 | RISK-1055 | Related Risk Title 92 | Open
Risk | Sports District | Goodburgh | Sports | PRJ-2094 | SUB-15 | Water Park Infrastructure Upgrade | Development | Delayed | RISK-1093 | 2026-03-01 | 2026-05-21 | Delay in Authority Clearance | Regulatory approvals are not received within planned timelines. | Incomplete documentation submission and compliance gaps. | Construction start delay and milestone impact. | 2026-03-21 | Mitigating |  | Theresa Wall | Concept | RIBA 5 | Risk impact remains moderate due to incomplete coordination. | 35 | Risk exposure reduced to acceptable levels through proactive mitigation execution. | 10 | 35 | High | 10 | High | 5666789.9 | 1619082.83 | 110 | 31 | Threat | Quality | Execution | Design | Band 3 | Commercial | Construction | Construction | RBS-342.7 | 2026-04-07 | 2026-08-10 | No | Project 8 | PLAN-6693 | Strengthen coordination with approving authorities. | RESP-59156 | Kirsten Maddox | Regulatory Engagement Plan | Not Started | Establish early submission schedules, conduct pre-submission meetings, and assign a dedicated authority liaison to track approvals. | 2026-03-01 | 2026-04-12 | 41 | 2026-04-12 | No | 2026-03-02 | 1881319.13 | 2252207.92 | 100 | RISK-1019 | Related Risk Title 93 | Mitigating
Risk | Sports District | Thomasland | Sports | PRJ-2095 | SUB-13 | Water Park Infrastructure Upgrade | Delivery | Completed | RISK-1094 | 2026-03-01 | 2026-06-17 | Scope Creep | Additional requirements introduced after contract award. | Uncontrolled change management process. | Budget overrun and timeline extension. | 2026-03-20 | Mitigating |  | Amanda Flores | Handover | RIBA 2 | Current controls are partially implemented and require strengthening. | 33 | Risk exposure reduced to acceptable levels through proactive mitigation execution. | 20 | 132 | Low | 80 | Low | 5618477.17 | 3405137.68 | 321 | 194 | Threat | Time | Design | Design | Band 1 | Construction | Design | Construction | RBS-609.6 | 2026-03-22 | 2026-08-02 | Yes | Project 11 | PLAN-1459 | Enhance structured design approval workflow. | RESP-40088 | Sara Hammond | Design Review Governance | Not Started | Implement formal design review cycles with defined SLAs, digital tracking tools, and consolidated stakeholder feedback. | 2026-03-01 | 2026-04-24 | 53 | 2026-04-24 | Yes | 2026-03-02 | 484095.56 | 363674.55 | 75.12 | RISK-1079 | Related Risk Title 94 | Mitigating
Risk | Sports District | Drakeshire | Sports | PRJ-2096 | SUB-7 | Theme Park Expansion Phase 1 | Commercial | Active | RISK-1095 | 2026-03-01 | 2026-06-10 | Contractor Underperformance | Main contractor fails to achieve planned progress targets. | Insufficient manpower allocation and weak supervision. | Extended project duration and cost overrun risk. | 2026-03-21 | Open |  | Jordan Wood | Design | RIBA 2 | Escalation mechanisms are not consistently applied across packages. | 57 | Proactive monitoring system established with early warning indicators. | 53 | 285 | Critical | 265 | Low | 6281996.27 | 5841154.43 | 127 | 118 | Minor | Cost | Concept | Procurement | Band 3 | Authority | Design | Authority | RBS-359.3 | 2026-04-29 | 2026-06-26 | Yes | Project 9 | PLAN-8316 | Improve contractor productivity tracking. | RESP-21316 | Alexander Branch | Contractor Performance Monitoring | In Progress | Introduce weekly progress dashboards, KPI monitoring, and corrective action plans for underperforming packages. | 2026-03-01 | 2026-04-17 | 46 | 2026-04-17 | No | 2026-03-02 | 1845824.82 | 938862.26 | 50.86 | RISK-1042 | Related Risk Title 95 | Open
Risk | Retail District | South Vanessa | Retail | PRJ-2097 | SUB-14 | Luxury Resort Construction | Development | Completed | RISK-1096 | 2026-03-01 | 2026-03-13 | Delay in Authority Clearance | Regulatory approvals are not received within planned timelines. | Incomplete documentation submission and compliance gaps. | Construction start delay and milestone impact. | 2026-03-03 | Mitigating |  | Stephen Booker | Design | RIBA 5 | Risk impact remains moderate due to incomplete coordination. | 51 | Quality and compliance risks controlled through strengthened QA/QC systems. | 29 | 204 | Critical | 116 | Moderate | 7467303.23 | 4246113.6 | 72 | 40 | Threat | Quality | Design | Procurement | Band 3 | Procurement | Procurement | Construction | RBS-913.2 | 2026-04-04 | 2026-07-02 | No | Project 20 | PLAN-1125 | Improve contractor productivity tracking. | RESP-30278 | Mark Tyler | Contractor Performance Monitoring | Not Started | Introduce weekly progress dashboards, KPI monitoring, and corrective action plans for underperforming packages. | 2026-03-01 | 2026-05-12 | 71 | 2026-05-12 | No | 2026-03-02 | 1977353.84 | 1539520.17 | 77.86 | RISK-1011 | Related Risk Title 96 | Mitigating
Risk | Retail District | Lake Kayleeport | Retail | PRJ-2098 | SUB-3 | Stadium Main Structure Build | Commercial | Active | RISK-1097 | 2026-03-01 | 2026-05-23 | Scope Creep | Additional requirements introduced after contract award. | Uncontrolled change management process. | Budget overrun and timeline extension. | 2026-03-11 | Open |  | Tara King | Execution | RIBA 5 | Risk exposure remains high due to ongoing delays and limited mitigation effectiveness. | 28 | Residual risk maintained within approved risk appetite thresholds. | 16 | 112 | High | 64 | Moderate | 3169067.63 | 1810895.79 | 140 | 80 | Threat | Cost | Handover | Procurement | Band 1 | Procurement | Commercial | Procurement | RBS-587.4 | 2026-04-23 | 2026-06-17 | Yes | Project 10 | PLAN-6663 | Improve contractor productivity tracking. | RESP-60284 | Timothy Pearson | Contractor Performance Monitoring | Completed | Introduce weekly progress dashboards, KPI monitoring, and corrective action plans for underperforming packages. | 2026-03-01 | 2026-06-28 | 118 | 2026-06-28 | No | 2026-03-02 | 1360047.34 | 1296980.31 | 95.36 | RISK-1055 | Related Risk Title 97 | Open
Risk | Sports District | Harrishaven | Sports | PRJ-2099 | SUB-14 | Retail Boulevard Development | Delivery | Delayed | RISK-1098 | 2026-03-01 | 2026-03-22 | Design Coordination Conflict | Clashes identified between architectural and MEP drawings. | Lack of BIM coordination prior to IFC issuance. | On-site rework and additional construction costs. | 2026-03-11 | Mitigating |  | April Carney | Handover | RIBA 1 | Budget constraints are restricting full implementation of mitigation measures. | 23 | Risk exposure reduced to acceptable levels through proactive mitigation execution. | 15 | 46 | Moderate | 30 | Low | 8536510.56 | 5567289.5 | 293 | 191 | Threat | Quality | Handover | Design | Band 2 | Construction | Procurement | Commercial | RBS-588.6 | 2026-04-02 | 2026-09-02 | No | Project 13 | PLAN-3856 | Strengthen interdisciplinary design coordination. | RESP-92840 | Jennifer Black | BIM Coordination Process | Not Started | Conduct mandatory BIM clash detection workshops before IFC issuance to eliminate on-site conflicts. | 2026-03-01 | 2026-05-16 | 75 | 2026-05-16 | No | 2026-03-02 | 1390727.02 | 1273195.69 | 91.55 | RISK-1075 | Related Risk Title 98 | Mitigating
Risk | Hospitality District | New Brookeborough | Hospitality | PRJ-2100 | SUB-6 | Water Park Infrastructure Upgrade | Delivery | Active | RISK-1099 | 2026-03-01 | 2026-06-04 | Delay in Material Delivery | Critical construction materials are not delivered as per approved schedule. | Supplier production backlog and late procurement planning. | Schedule slippage impacting structural and finishing activities. | 2026-03-07 | Mitigating |  | Eric Black | Concept | RIBA 5 | Budget constraints are restricting full implementation of mitigation measures. | 30 | Authority approvals streamlined via early engagement plan. | 6 | 120 | Low | 24 | Critical | 2181751.15 | 436350.23 | 224 | 44 | Minor | Cost | Concept | Construction | Band 3 | Design | Commercial | Construction | RBS-594.1 | 2026-03-21 | 2026-05-02 | Yes | Project 8 | PLAN-9101 | Strengthen site health and safety practices. | RESP-91320 | Ashley Conner | HSE Reinforcement Program | Completed | Conduct mandatory safety training, periodic audits, and enforce zero-tolerance safety compliance policies. | 2026-03-01 | 2026-06-25 | 115 | 2026-06-25 | No | 2026-03-02 | 1570479.9 | 1659681.48 | 100 | RISK-1072 | Related Risk Title 99 | Mitigating