## l1_risk_regenerated
Record Type | District | Sub-District | Portfolio | Project | Sub-Project | Project Name | BU Attributes | Project Status | Risk ID | Date Raised | Last Review | Risk Title | Risk Description | Cause | Effect | Approval Date | Risk Status | Closed Date | Risk Owner | Progress Stage | RIBA Phase | Current Rationale | Current Probability | Target Rationale | Target Probability | Current Risk Score | Current Risk Level | Target Risk Score | Target Risk Level | Current EMV | Target EMV | Current ETV | Target ETV | Exposure | Driver | Stage | Category 1 | Current Band | Category 2 | Category 3 | Category 4 | RBS | Exposure Start | Exposure End | escalation | Project Name | Plan ID | High level Description | Response ID | Response Owner | title | status | description | Start Date | Due Date | Days from Due | Response Due | Completed_Closed | Last updated | Planned Cost | Actual Cost | Percent Complete | Related Risk ID | Risk Title | Risk Status
Risk | South | Evansport | Entertainment | PRJ-705 | SUB-15 | Project 12 | Development | Delayed | RISK-1000 | 2026-03-01 | 2026-05-19 | Delay in material delivery | The people book important. | Group decade speak foreign prevent thank. | Do form might true involve. | 2026-03-16 | Closed | 2026-05-22 | Michael Green | Handover | RIBA 3 | Every kitchen money. | 27 | Perform industry back least guy add yet. | 22 | 108 | High | 88 | Critical | 5012741.21 | 4084455.8 | 362 | 294 | Minor | Time | Execution | Commercial | Band 2 | Procurement | Authority | Commercial | RBS-452.9 | 2026-04-19 | 2026-09-16 | Yes | Project 4 | PLAN-6612 | Open project analysis happy. | RESP-23179 | Kelsey Murphy | Mitigation for Risk-1000 | Not Started | Writer indeed such family sell. | 2026-03-01 | 2026-05-09 | 68 | 2026-05-09 | Yes | 2026-03-02 | 1222389.9 | 1140782.69 | 93.32 | RISK-1028 | Related Risk Title 0 | Closed
Risk | South | South Paula | Entertainment | PRJ-625 | SUB-10 | Project 5 | Development | Completed | RISK-1001 | 2026-03-01 | 2026-05-12 | Delay in authority clearance | Senior right scene sister. | Mouth nation stuff lawyer ten hundred. | Down factor yard friend various. | 2026-03-23 | Closed | 2026-06-11 | Matthew Ross | Execution | RIBA 2 | Yeah letter him mother. | 29 | Worker road probably born. | 22 | 29 | Moderate | 22 | High | 6218505.43 | 4717486.88 | 265 | 201 | Minor | Reputation | Design | Design | Band 3 | Procurement | Procurement | Procurement | RBS-373.6 | 2026-04-26 | 2026-09-25 | Yes | Project 17 | PLAN-5035 | Congress here thought seat medical always ask. | RESP-26365 | Kathleen Washington | Mitigation for Risk-1001 | Completed | If teacher girl build choice line just professor. | 2026-03-01 | 2026-05-12 | 71 | 2026-05-12 | No | 2026-03-02 | 1480665.23 | 942484.74 | 63.65 | RISK-1059 | Related Risk Title 1 | Closed
Risk | North | East Marytown | Infrastructure | PRJ-568 | SUB-5 | Project 4 | Delivery | Active | RISK-1002 | 2026-03-01 | 2026-05-09 | Delay in design approval | Over pressure shoulder sister speech know. | Career wish since. | Learn say structure. | 2026-03-08 | Closed | 2026-05-23 | Brian Garcia DDS | Execution | RIBA 3 | Eye future pay say example possible save everything. | 79 | Majority approach behavior budget standard. | 57 | 316 | Critical | 228 | High | 3704558.77 | 2672909.49 | 72 | 51 | Minor | Time | Concept | Construction | Band 3 | Procurement | Authority | Authority | RBS-444.8 | 2026-03-13 | 2026-04-25 | Yes | Project 9 | PLAN-6377 | Sell side use federal. | RESP-25287 | Alicia Scott | Mitigation for Risk-1002 | In Progress | Message wall home piece. | 2026-03-01 | 2026-04-21 | 50 | 2026-04-21 | Yes | 2026-03-02 | 598802.81 | 313141.47 | 52.29 | RISK-1036 | Related Risk Title 2 | Closed
Risk | Waterfront | Edwardsborough | Hospitality | PRJ-724 | SUB-10 | Project 14 | Commercial | Active | RISK-1003 | 2026-03-01 | 2026-04-13 | Delay in material delivery | Deep talk necessary need fly store go. | Mind herself quality mission. | Man brother thing explain sure themselves dog. | 2026-03-25 | Mitigating |  | Julie Bryant | Concept | RIBA 2 | Never population cause before ahead strong collection time. | 65 | State letter book behind poor. | 43 | 260 | Low | 172 | Moderate | 662171.63 | 438052 | 225 | 148 | Threat | Quality | Concept | Design | Band 2 | Design | Authority | Design | RBS-380.1 | 2026-04-27 | 2026-09-10 | Yes | Project 6 | PLAN-6503 | Indeed second author my pretty. | RESP-92997 | Robyn Mccarthy | Mitigation for Risk-1003 | Not Started | Evening art skill commercial leader growth line. | 2026-03-01 | 2026-04-18 | 47 | 2026-04-18 | Yes | 2026-03-02 | 484001.35 | 378701.63 | 78.24 | RISK-1078 | Related Risk Title 3 | Mitigating
Risk | Central | North Sharonhaven | Infrastructure | PRJ-857 | SUB-14 | Project 7 | Commercial | On Hold | RISK-1004 | 2026-03-01 | 2026-05-08 | Delay in material delivery | Rock peace compare happy tonight so hot. | Raise traditional speech light find cause. | Particularly go perhaps pressure far people. | 2026-03-17 | Open |  | Debra James | Design | RIBA 5 | Sing throughout blue author raise. | 56 | Low member here. | 1 | 168 | Low | 3 | High | 4790233.6 | 85539.89 | 359 | 6 | Threat | Cost | Concept | Construction | Band 1 | Authority | Authority | Construction | RBS-580.4 | 2026-03-21 | 2026-04-30 | No | Project 6 | PLAN-5529 | Life indeed including interest detail. | RESP-16425 | Jennifer Simpson | Mitigation for Risk-1004 | Not Started | Direction wrong out view. | 2026-03-01 | 2026-06-07 | 97 | 2026-06-07 | Yes | 2026-03-02 | 1122517.34 | 737844.96 | 65.73 | RISK-1006 | Related Risk Title 4 | Open
Risk | North | New Elizabethstad | Hospitality | PRJ-520 | SUB-18 | Project 6 | Delivery | Completed | RISK-1005 | 2026-03-01 | 2026-04-16 | Delay in authority clearance | Material thank respond parent cell painting. | Also would floor federal marriage too. | Where accept director study particularly. | 2026-03-09 | Closed | 2026-05-14 | Steve Lopez | Execution | RIBA 3 | Magazine city at my hope quality bad total. | 33 | Particularly everyone under not stuff. | 9 | 165 | High | 45 | High | 952764.75 | 259844.93 | 356 | 97 | Threat | Quality | Design | Commercial | Band 1 | Construction | Authority | Commercial | RBS-100.1 | 2026-05-07 | 2026-07-27 | No | Project 5 | PLAN-6546 | Business road almost ahead film difference. | RESP-14996 | Walter Ramirez | Mitigation for Risk-1005 | In Progress | No result central dark upon race. | 2026-03-01 | 2026-04-23 | 52 | 2026-04-23 | Yes | 2026-03-02 | 559735.3 | 448314.46 | 80.09 | RISK-1050 | Related Risk Title 5 | Closed
Risk | Waterfront | Debramouth | Entertainment | PRJ-910 | SUB-10 | Project 2 | Commercial | Completed | RISK-1006 | 2026-03-01 | 2026-05-30 | Delay in design approval | Daughter fine word project such yeah six. | Become feel strategy. | Provide truth bit down executive star with teacher. | 2026-03-31 | Open |  | Samuel Lowe | Execution | RIBA 3 | According against just stock ever community. | 40 | Join official list our type. | 14 | 80 | High | 28 | Moderate | 6456199.95 | 2259669.98 | 115 | 40 | Threat | Time | Handover | Procurement | Band 1 | Procurement | Construction | Construction | RBS-754.9 | 2026-04-21 | 2026-07-08 | Yes | Project 6 | PLAN-2501 | Dark state cold treat carry. | RESP-49466 | Ashlee Love | Mitigation for Risk-1006 | Completed | Tree street song teacher open. | 2026-03-01 | 2026-06-29 | 119 | 2026-06-29 | No | 2026-03-02 | 367542.64 | 336286.12 | 91.5 | RISK-1056 | Related Risk Title 6 | Open
Risk | North | North Andrew | Hospitality | PRJ-378 | SUB-9 | Project 3 | Commercial | On Hold | RISK-1007 | 2026-03-01 | 2026-06-23 | Delay in authority clearance | Across road strong hear place son modern. | Because few positive voice. | Friend today difference type feeling his. | 2026-03-29 | Open |  | Amanda Davis | Execution | RIBA 3 | Lot record political leader high. | 77 | Position occur common store. | 29 | 231 | Critical | 87 | Low | 6945155.12 | 2615707.77 | 153 | 57 | Minor | Time | Execution | Design | Band 3 | Procurement | Design | Commercial | RBS-770.1 | 2026-04-13 | 2026-08-24 | Yes | Project 19 | PLAN-7319 | Garden phone increase meet hotel late. | RESP-98202 | Sarah Reed | Mitigation for Risk-1007 | In Progress | Available cold toward site off turn can sing. | 2026-03-01 | 2026-06-17 | 107 | 2026-06-17 | No | 2026-03-02 | 1650355.71 | 832066.04 | 50.42 | RISK-1032 | Related Risk Title 7 | Open
Risk | South | New Ronald | Hospitality | PRJ-989 | SUB-2 | Project 1 | Commercial | Delayed | RISK-1008 | 2026-03-01 | 2026-06-01 | Delay in design approval | Pay bag news well. | Modern keep by budget hand responsibility. | So eat end before color require position. | 2026-03-04 | Open |  | Gabriel Nguyen | Concept | RIBA 5 | Best a public. | 33 | Tree imagine production my market evidence talk. | 27 | 165 | Moderate | 135 | Critical | 3897709.85 | 3189035.33 | 332 | 271 | Threat | Reputation | Design | Construction | Band 3 | Design | Design | Design | RBS-685.3 | 2026-04-11 | 2026-07-20 | No | Project 11 | PLAN-6956 | Morning along every let window still country. | RESP-49439 | Connie Chang | Mitigation for Risk-1008 | In Progress | Early sometimes move since necessary song power argue. | 2026-03-01 | 2026-03-31 | 29 | 2026-03-31 | No | 2026-03-02 | 1889825.69 | 976508.82 | 51.67 | RISK-1093 | Related Risk Title 8 | Open
Risk | North | East Denise | Infrastructure | PRJ-318 | SUB-5 | Project 5 | Commercial | Active | RISK-1009 | 2026-03-01 | 2026-04-26 | Delay in material delivery | According better town audience. | Security establish color guy hand any capital forward. | No majority year field peace election various. | 2026-03-18 | Open |  | Casey Hardin | Handover | RIBA 2 | Education affect owner see four never girl. | 71 | Two for indicate open box dream. | 31 | 355 | Moderate | 155 | High | 9653219.07 | 4214785.79 | 62 | 27 | Opportunity | Time | Execution | Construction | Band 2 | Commercial | Construction | Commercial | RBS-265.8 | 2026-05-16 | 2026-08-25 | No | Project 1 | PLAN-1252 | Nor play it generation marriage like movement. | RESP-93865 | Kyle Raymond | Mitigation for Risk-1009 | Completed | Teacher but issue interview so voice send number. | 2026-03-01 | 2026-04-21 | 50 | 2026-04-21 | Yes | 2026-03-02 | 1056966.9 | 626201.45 | 59.25 | RISK-1037 | Related Risk Title 9 | Open
Risk | Waterfront | South Donaldville | Infrastructure | PRJ-423 | SUB-14 | Project 2 | Commercial | Delayed | RISK-1010 | 2026-03-01 | 2026-03-19 | Delay in design approval | Piece Mr effort produce media. | Likely far improve. | Now stop paper recognize test paper current inside. | 2026-03-06 | Closed | 2026-04-01 | John Brown MD | Handover | RIBA 5 | Moment sure project call her himself cost. | 33 | Travel plan technology east great finally somebody. | 29 | 165 | High | 145 | Low | 4955651.74 | 4354966.68 | 274 | 240 | Opportunity | Quality | Design | Construction | Band 1 | Commercial | Authority | Construction | RBS-799.5 | 2026-04-13 | 2026-09-14 | Yes | Project 18 | PLAN-4802 | True then I hard improve light. | RESP-95608 | Nicole Mora | Mitigation for Risk-1010 | Completed | International great subject stay live law lay. | 2026-03-01 | 2026-05-30 | 89 | 2026-05-30 | No | 2026-03-02 | 891377.36 | 581046.63 | 65.19 | RISK-1076 | Related Risk Title 10 | Closed
Risk | South | Stevensstad | Hospitality | PRJ-140 | SUB-2 | Project 20 | Delivery | On Hold | RISK-1011 | 2026-03-01 | 2026-05-04 | Delay in material delivery | Everything standard box matter paper state. | Democratic those evening box star. | Collection might expert school position gas always. | 2026-03-21 | Mitigating |  | Charles Sanchez | Concept | RIBA 2 | Gun natural southern sure or. | 10 | Music above use tax alone. | 3 | 30 | Critical | 9 | High | 1740022.88 | 522006.86 | 292 | 87 | Opportunity | Reputation | Concept | Commercial | Band 3 | Design | Design | Procurement | RBS-516.9 | 2026-05-19 | 2026-06-26 | No | Project 14 | PLAN-7242 | Us few put degree model read. | RESP-12741 | Daniel Velasquez | Mitigation for Risk-1011 | Not Started | Treatment agent want name voice. | 2026-03-01 | 2026-05-03 | 62 | 2026-05-03 | Yes | 2026-03-02 | 1265293.4 | 773536.39 | 61.13 | RISK-1045 | Related Risk Title 11 | Mitigating
Risk | Central | Lake Michaelborough | Infrastructure | PRJ-881 | SUB-11 | Project 6 | Commercial | Completed | RISK-1012 | 2026-03-01 | 2026-04-19 | Delay in design approval | Try natural three next none hold pick. | With career red ago economy middle. | Create single employee. | 2026-03-10 | Open |  | Jennifer Wells | Concept | RIBA 5 | Strong pretty simply. | 54 | Difficult detail forget especially front community. | 18 | 162 | High | 54 | High | 5327948.95 | 1775982.98 | 285 | 95 | Minor | Quality | Handover | Commercial | Band 2 | Design | Procurement | Authority | RBS-606.7 | 2026-03-26 | 2026-09-06 | Yes | Project 15 | PLAN-6689 | General country interest only by probably. | RESP-60815 | Tina Williams | Mitigation for Risk-1012 | In Progress | Truth officer hotel admit out health think. | 2026-03-01 | 2026-06-10 | 100 | 2026-06-10 | No | 2026-03-02 | 1571239.07 | 1622849.99 | 100 | RISK-1058 | Related Risk Title 12 | Open
Risk | Waterfront | Baileymouth | Hospitality | PRJ-239 | SUB-13 | Project 11 | Commercial | Completed | RISK-1013 | 2026-03-01 | 2026-06-25 | Delay in design approval | Guy since result management time. | Then responsibility wish sing skin time time. | Unit visit yard inside could job itself. | 2026-03-27 | Open |  | Annette Bryant | Concept | RIBA 1 | Most never protect from. | 38 | It amount deep agent senior head. | 24 | 190 | High | 120 | High | 8321839.25 | 5255898.47 | 101 | 63 | Opportunity | Time | Concept | Procurement | Band 1 | Procurement | Design | Construction | RBS-770.9 | 2026-04-12 | 2026-05-23 | Yes | Project 18 | PLAN-7866 | Attorney read not trial million carry voice space. | RESP-17113 | Jonathan King | Mitigation for Risk-1013 | Not Started | Hospital few can adult when. | 2026-03-01 | 2026-06-03 | 93 | 2026-06-03 | Yes | 2026-03-02 | 643406.31 | 682807.6 | 100 | RISK-1094 | Related Risk Title 13 | Open
Risk | North | West Chelsea | Hospitality | PRJ-978 | SUB-15 | Project 3 | Development | Delayed | RISK-1014 | 2026-03-01 | 2026-06-15 | Delay in design approval | Daughter letter little military pressure. | Though camera stay yes look. | Find though technology into raise man. | 2026-03-19 | Closed | 2026-07-01 | Sean Lambert | Execution | RIBA 5 | War style maybe more official take. | 67 | Her federal save floor production answer perform. | 53 | 268 | Critical | 212 | Moderate | 8569818.31 | 6779110.01 | 120 | 94 | Opportunity | Cost | Design | Procurement | Band 2 | Authority | Design | Construction | RBS-895.1 | 2026-03-28 | 2026-07-01 | No | Project 5 | PLAN-4345 | Cover sometimes task these lead. | RESP-97233 | Gail Garza | Mitigation for Risk-1014 | Completed | Book executive really they power election program situation. | 2026-03-01 | 2026-06-10 | 100 | 2026-06-10 | No | 2026-03-02 | 1520734.2 | 1444898.55 | 95.01 | RISK-1062 | Related Risk Title 14 | Closed
Risk | South | Wuside | Infrastructure | PRJ-723 | SUB-6 | Project 3 | Commercial | On Hold | RISK-1015 | 2026-03-01 | 2026-04-16 | Delay in design approval | Officer pretty evidence trade live step only. | Hotel form hair appear fight. | Nice market role water agreement professor recognize. | 2026-03-30 | Mitigating |  | Sandra Castillo | Execution | RIBA 3 | Become weight adult responsibility camera organization. | 21 | Time mouth name too. | 18 | 63 | Moderate | 54 | Critical | 9386924.31 | 8045935.12 | 288 | 246 | Minor | Quality | Execution | Authority | Band 3 | Authority | Construction | Construction | RBS-776.3 | 2026-05-20 | 2026-09-14 | Yes | Project 7 | PLAN-7551 | Identify focus public require property artist. | RESP-85074 | Alicia Carroll | Mitigation for Risk-1015 | Completed | Might interview worker. | 2026-03-01 | 2026-04-02 | 31 | 2026-04-02 | No | 2026-03-02 | 304080.06 | 251282.56 | 82.64 | RISK-1099 | Related Risk Title 15 | Mitigating
Risk | North | Vasquezborough | Hospitality | PRJ-468 | SUB-1 | Project 1 | Commercial | Completed | RISK-1016 | 2026-03-01 | 2026-04-09 | Delay in authority clearance | Specific with view bank. | Art his produce. | School ever world small ahead. | 2026-03-06 | Open |  | Theresa Green MD | Concept | RIBA 4 | Big bill service blue arm. | 55 | Response south I food top response. | 28 | 110 | Critical | 56 | Moderate | 9729995.37 | 4953452.19 | 31 | 15 | Opportunity | Cost | Execution | Authority | Band 3 | Commercial | Construction | Procurement | RBS-993.6 | 2026-04-15 | 2026-06-24 | Yes | Project 7 | PLAN-1086 | Cell occur necessary hour where. | RESP-21110 | Brian Miller | Mitigation for Risk-1016 | Not Started | Never establish pressure whole. | 2026-03-01 | 2026-04-16 | 45 | 2026-04-16 | Yes | 2026-03-02 | 763618.09 | 698747.03 | 91.5 | RISK-1006 | Related Risk Title 16 | Open
Risk | Waterfront | Lake Timothy | Hospitality | PRJ-239 | SUB-14 | Project 14 | Delivery | Delayed | RISK-1017 | 2026-03-01 | 2026-05-28 | Delay in material delivery | Recently ground evidence service. | Establish control opportunity where wear into. | Manager cultural back skin wish work could. | 2026-03-22 | Open |  | Benjamin Johnson | Execution | RIBA 4 | Follow organization yard common. | 21 | Off week material government partner question develop. | 10 | 21 | Low | 10 | Moderate | 1008825.58 | 480393.13 | 125 | 59 | Minor | Cost | Execution | Procurement | Band 2 | Design | Procurement | Design | RBS-564.2 | 2026-05-12 | 2026-09-13 | Yes | Project 13 | PLAN-2246 | Bad television daughter building mouth move song event. | RESP-35978 | Mr. Michael Martinez | Mitigation for Risk-1017 | Not Started | Time best whatever. | 2026-03-01 | 2026-06-05 | 95 | 2026-06-05 | No | 2026-03-02 | 1309385.83 | 690341.35 | 52.72 | RISK-1017 | Related Risk Title 17 | Open
Risk | Waterfront | North Angela | Entertainment | PRJ-393 | SUB-6 | Project 5 | Commercial | Delayed | RISK-1018 | 2026-03-01 | 2026-05-25 | Delay in material delivery | Thus return own product world. | Seven subject such store. | Bill garden one push only race risk. | 2026-03-23 | Open |  | Janice Rosales | Design | RIBA 1 | Response anything my worry. | 13 | According quickly school condition when. | 7 | 65 | Critical | 35 | Moderate | 7814172.32 | 4207631.25 | 23 | 12 | Minor | Cost | Design | Commercial | Band 2 | Construction | Design | Procurement | RBS-625.9 | 2026-03-24 | 2026-06-22 | Yes | Project 5 | PLAN-5906 | Success interesting son nation do. | RESP-85376 | Kristin Shea | Mitigation for Risk-1018 | In Progress | Heavy fall your number. | 2026-03-01 | 2026-04-01 | 30 | 2026-04-01 | Yes | 2026-03-02 | 1246007.68 | 811772.48 | 65.15 | RISK-1090 | Related Risk Title 18 | Open
Risk | South | Lake Richardton | Infrastructure | PRJ-674 | SUB-6 | Project 8 | Commercial | Active | RISK-1019 | 2026-03-01 | 2026-06-12 | Delay in design approval | Fast window story piece suggest page success face. | Information yourself foreign unit physical example. | Citizen actually try. | 2026-03-24 | Closed | 2026-06-25 | Juan Cruz | Concept | RIBA 2 | Easy voice eye today. | 27 | Late several senior surface purpose during. | 26 | 54 | Critical | 52 | Critical | 1704171.88 | 1641054.4 | 234 | 225 | Threat | Quality | Handover | Procurement | Band 3 | Procurement | Construction | Commercial | RBS-606.2 | 2026-05-04 | 2026-08-27 | Yes | Project 20 | PLAN-6819 | Future hand defense follow with. | RESP-14844 | Matthew Greer | Mitigation for Risk-1019 | Completed | Project mention these window law provide cold. | 2026-03-01 | 2026-04-16 | 45 | 2026-04-16 | Yes | 2026-03-02 | 473125.36 | 471960.62 | 99.75 | RISK-1039 | Related Risk Title 19 | Closed
Risk | Waterfront | Berryborough | Entertainment | PRJ-714 | SUB-18 | Project 6 | Delivery | Completed | RISK-1020 | 2026-03-01 | 2026-05-17 | Delay in material delivery | Our close pretty particularly. | Huge purpose none dog walk reflect. | Unit class from do lay thousand. | 2026-03-26 | Closed | 2026-05-27 | Erin Spencer | Handover | RIBA 3 | She pattern role item ability professional. | 67 | Growth their cut town. | 19 | 134 | High | 38 | High | 2049341.78 | 581156.62 | 154 | 43 | Minor | Quality | Design | Authority | Band 3 | Authority | Construction | Procurement | RBS-543.7 | 2026-03-30 | 2026-05-18 | No | Project 10 | PLAN-8860 | Draw new small create group. | RESP-82958 | Mary Reese | Mitigation for Risk-1020 | Completed | Nice can cell suggest customer picture. | 2026-03-01 | 2026-05-23 | 82 | 2026-05-23 | No | 2026-03-02 | 1263118.22 | 1253088.07 | 99.21 | RISK-1098 | Related Risk Title 20 | Closed
Risk | North | South Miguelborough | Entertainment | PRJ-773 | SUB-19 | Project 15 | Delivery | Completed | RISK-1021 | 2026-03-01 | 2026-03-27 | Delay in design approval | Action magazine strategy the treatment above. | Recognize so oil there. | Lose exist skill color understand born. | 2026-03-08 | Open |  | Alexandria Peters | Concept | RIBA 3 | Value because rule clear. | 13 | Necessary accept significant left single black government. | 11 | 13 | Moderate | 11 | Moderate | 1092194.81 | 924164.84 | 39 | 33 | Opportunity | Quality | Handover | Commercial | Band 3 | Procurement | Commercial | Procurement | RBS-213.3 | 2026-04-29 | 2026-10-02 | No | Project 19 | PLAN-6588 | Law pattern she board age recognize. | RESP-39977 | Mr. Mark Sawyer | Mitigation for Risk-1021 | Not Started | Executive he office including development move hit skill. | 2026-03-01 | 2026-04-10 | 39 | 2026-04-10 | Yes | 2026-03-02 | 573679.94 | 537690.64 | 93.73 | RISK-1071 | Related Risk Title 21 | Open
Risk | Waterfront | North Roger | Entertainment | PRJ-676 | SUB-1 | Project 12 | Delivery | Delayed | RISK-1022 | 2026-03-01 | 2026-05-17 | Delay in design approval | Exactly ask difficult sign. | Ability do always couple compare appear ok cell. | Growth how see no perform than marriage front. | 2026-03-25 | Closed | 2026-05-21 | Jeffrey Fisher | Handover | RIBA 3 | Leader during forward positive gun attorney control. | 19 | Western economic role employee in feel. | 5 | 38 | Critical | 10 | Low | 1005924.11 | 264716.87 | 305 | 80 | Minor | Cost | Concept | Commercial | Band 2 | Commercial | Procurement | Authority | RBS-497.2 | 2026-04-07 | 2026-06-21 | No | Project 9 | PLAN-6564 | Talk body able risk capital management without. | RESP-54471 | Anthony Harris | Mitigation for Risk-1022 | Not Started | Project yard both fill people white treat. | 2026-03-01 | 2026-06-29 | 119 | 2026-06-29 | Yes | 2026-03-02 | 1466973.71 | 1063596.59 | 72.5 | RISK-1018 | Related Risk Title 22 | Closed
Risk | North | New Kristin | Entertainment | PRJ-906 | SUB-20 | Project 2 | Commercial | Delayed | RISK-1023 | 2026-03-01 | 2026-04-12 | Delay in authority clearance | These run concern treat yet sign. | Why everyone expect since skin official. | Difficult south popular security. | 2026-03-02 | Mitigating |  | James Gentry | Execution | RIBA 4 | Structure page include though either order. | 69 | Herself use evidence everything sit. | 2 | 69 | Low | 2 | Moderate | 9080900.86 | 263214.52 | 313 | 9 | Minor | Reputation | Concept | Construction | Band 2 | Procurement | Authority | Commercial | RBS-859.7 | 2026-03-14 | 2026-06-16 | Yes | Project 14 | PLAN-3916 | City cultural follow. | RESP-35472 | John Campbell | Mitigation for Risk-1023 | In Progress | Memory argue we national effect air. | 2026-03-01 | 2026-04-05 | 34 | 2026-04-05 | Yes | 2026-03-02 | 1875188.52 | 1714947.96 | 91.45 | RISK-1002 | Related Risk Title 23 | Mitigating
Risk | South | Fitzgeraldhaven | Hospitality | PRJ-160 | SUB-15 | Project 18 | Commercial | Active | RISK-1024 | 2026-03-01 | 2026-04-11 | Delay in authority clearance | Thank hour heavy crime field institution. | Avoid watch plan. | Relationship policy court pay decade movie source whom. | 2026-03-04 | Closed | 2026-04-19 | Thomas Peterson | Concept | RIBA 5 | Begin long notice yourself future degree. | 69 | Guy man population stop country easy executive. | 26 | 138 | Low | 52 | Low | 2975531.37 | 1121214.72 | 40 | 15 | Opportunity | Reputation | Concept | Procurement | Band 1 | Design | Commercial | Design | RBS-651.9 | 2026-04-18 | 2026-06-16 | Yes | Project 9 | PLAN-6840 | Government kitchen above rest. | RESP-41831 | Jeffrey Munoz | Mitigation for Risk-1024 | In Progress | Likely that drug hear free. | 2026-03-01 | 2026-06-12 | 102 | 2026-06-12 | Yes | 2026-03-02 | 861964.26 | 897149.28 | 100 | RISK-1003 | Related Risk Title 24 | Closed
Risk | South | North Lisashire | Hospitality | PRJ-827 | SUB-14 | Project 10 | Delivery | On Hold | RISK-1025 | 2026-03-01 | 2026-04-22 | Delay in material delivery | By do cause machine official argue language. | Enjoy admit herself eat remember. | Cup accept power dark conference. | 2026-03-11 | Open |  | Gregory Schneider | Execution | RIBA 2 | Talk bring bad style. | 63 | Turn product nearly service remain fish. | 60 | 126 | Critical | 120 | High | 3365586.34 | 3205320.32 | 152 | 144 | Threat | Quality | Execution | Design | Band 3 | Commercial | Procurement | Procurement | RBS-875.7 | 2026-05-08 | 2026-09-08 | Yes | Project 20 | PLAN-3745 | Create type rich guess two one. | RESP-48197 | Dr. Eric Flores | Mitigation for Risk-1025 | Completed | Grow significant say work institution. | 2026-03-01 | 2026-06-17 | 107 | 2026-06-17 | Yes | 2026-03-02 | 868226.78 | 988989.77 | 100 | RISK-1069 | Related Risk Title 25 | Open
Risk | South | Stevenchester | Hospitality | PRJ-541 | SUB-10 | Project 10 | Development | Delayed | RISK-1026 | 2026-03-01 | 2026-05-15 | Delay in material delivery | Picture tough stuff soldier difference them place. | Operation fly another news be. | Happen side same. | 2026-03-18 | Mitigating |  | Christine Schwartz | Execution | RIBA 5 | Meet box difference clearly week. | 68 | Number ask year pressure sort. | 62 | 68 | Moderate | 62 | Moderate | 5013521.15 | 4571151.64 | 75 | 68 | Threat | Quality | Design | Commercial | Band 1 | Procurement | Procurement | Construction | RBS-652.7 | 2026-04-15 | 2026-09-22 | Yes | Project 8 | PLAN-7373 | Camera like man sometimes partner travel where. | RESP-92817 | Kristin Jennings | Mitigation for Risk-1026 | In Progress | Quality brother to detail fear heart. | 2026-03-01 | 2026-04-18 | 47 | 2026-04-18 | No | 2026-03-02 | 1958062.98 | 1328078.08 | 67.83 | RISK-1002 | Related Risk Title 26 | Mitigating
Risk | Central | Port Michael | Hospitality | PRJ-415 | SUB-2 | Project 19 | Delivery | On Hold | RISK-1027 | 2026-03-01 | 2026-04-23 | Delay in design approval | Today local ask push require buy. | Page sea listen PM thousand. | Show want cover listen single public. | 2026-03-21 | Mitigating |  | Jason Lawrence | Execution | RIBA 4 | Ask carry tend too board pressure garden. | 78 | Apply eye visit. | 47 | 390 | High | 235 | High | 673802.67 | 406009.3 | 88 | 53 | Minor | Quality | Design | Authority | Band 1 | Design | Procurement | Construction | RBS-621.4 | 2026-04-07 | 2026-06-06 | No | Project 2 | PLAN-4997 | Everyone price do new. | RESP-62857 | Melissa Lopez | Mitigation for Risk-1027 | Not Started | Land anyone indicate. | 2026-03-01 | 2026-05-01 | 60 | 2026-05-01 | Yes | 2026-03-02 | 1924005.22 | 1311178.86 | 68.15 | RISK-1016 | Related Risk Title 27 | Mitigating
Risk | Central | Lake Gregoryhaven | Hospitality | PRJ-254 | SUB-17 | Project 18 | Delivery | Delayed | RISK-1028 | 2026-03-01 | 2026-06-19 | Delay in material delivery | Cause tough action address hand newspaper civil church. | Significant cover above. | Pay country rate everything not. | 2026-03-22 | Mitigating |  | Angel Horton | Execution | RIBA 5 | Republican blood year southern. | 44 | Nice management quality something again man ten message. | 33 | 132 | Moderate | 99 | Critical | 4779668.3 | 3584751.22 | 158 | 118 | Threat | Cost | Execution | Construction | Band 2 | Procurement | Authority | Construction | RBS-903.8 | 2026-05-08 | 2026-06-13 | Yes | Project 4 | PLAN-3014 | Store fear then four very about themselves. | RESP-54716 | John Vargas | Mitigation for Risk-1028 | Not Started | Word series get relate single. | 2026-03-01 | 2026-04-19 | 48 | 2026-04-19 | No | 2026-03-02 | 1288869.83 | 1141027.71 | 88.53 | RISK-1035 | Related Risk Title 28 | Mitigating
Risk | South | Finleystad | Hospitality | PRJ-754 | SUB-9 | Project 2 | Development | Delayed | RISK-1029 | 2026-03-01 | 2026-06-23 | Delay in authority clearance | Mission outside share long. | Focus success own. | Since history ability under in approach. | 2026-03-31 | Closed | 2026-06-25 | Robert Sullivan | Handover | RIBA 5 | Still fine nearly idea go fine. | 15 | Join general police into onto manage wall. | 8 | 60 | Moderate | 32 | Low | 2157557.68 | 1150697.43 | 178 | 94 | Minor | Reputation | Handover | Authority | Band 2 | Construction | Procurement | Authority | RBS-470.5 | 2026-04-23 | 2026-07-04 | Yes | Project 9 | PLAN-8545 | Air provide marriage rate require health not. | RESP-69366 | Karen Hernandez | Mitigation for Risk-1029 | In Progress | Different necessary religious. | 2026-03-01 | 2026-05-10 | 69 | 2026-05-10 | Yes | 2026-03-02 | 485445.61 | 482916.61 | 99.48 | RISK-1097 | Related Risk Title 29 | Closed
Risk | Waterfront | New Autumnmouth | Infrastructure | PRJ-173 | SUB-14 | Project 17 | Development | Active | RISK-1030 | 2026-03-01 | 2026-05-22 | Delay in material delivery | Tv certainly unit generation. | Certainly recently information share enough. | Baby theory source word situation certain. | 2026-03-12 | Open |  | Michele Hudson | Design | RIBA 3 | Determine prepare option. | 45 | Money off bill school. | 8 | 180 | Low | 32 | Critical | 2179114.59 | 387398.15 | 149 | 26 | Threat | Reputation | Design | Procurement | Band 2 | Authority | Construction | Construction | RBS-701.8 | 2026-03-14 | 2026-07-25 | No | Project 19 | PLAN-7235 | Upon add state individual news. | RESP-76668 | Chad Perry | Mitigation for Risk-1030 | In Progress | But out chair. | 2026-03-01 | 2026-04-18 | 47 | 2026-04-18 | No | 2026-03-02 | 465857.23 | 343107.51 | 73.65 | RISK-1061 | Related Risk Title 30 | Open
Risk | North | Coffeyshire | Hospitality | PRJ-737 | SUB-10 | Project 19 | Development | Active | RISK-1031 | 2026-03-01 | 2026-06-19 | Delay in authority clearance | Government drive recognize tell. | Red bill produce your able need. | Animal miss town must paper lawyer. | 2026-03-21 | Mitigating |  | Victoria Wood | Execution | RIBA 1 | Send attack road go top. | 26 | Charge establish head challenge. | 10 | 104 | Low | 40 | High | 7679511.8 | 2953658.38 | 137 | 52 | Threat | Time | Design | Procurement | Band 3 | Procurement | Authority | Commercial | RBS-113.5 | 2026-05-10 | 2026-11-05 | Yes | Project 16 | PLAN-7138 | My if debate claim garden tell entire. | RESP-44651 | Louis Peterson | Mitigation for Risk-1031 | In Progress | Whose strategy allow week go medical middle box. | 2026-03-01 | 2026-06-29 | 119 | 2026-06-29 | No | 2026-03-02 | 696363.66 | 484598.14 | 69.59 | RISK-1012 | Related Risk Title 31 | Mitigating
Risk | Waterfront | Port Blakeside | Infrastructure | PRJ-106 | SUB-5 | Project 3 | Development | Completed | RISK-1032 | 2026-03-01 | 2026-04-29 | Delay in authority clearance | Few security whole return. | Fast tell year writer society whole rock. | Field mind enough office bit mind. | 2026-03-09 | Closed | 2026-05-17 | Angela Black | Concept | RIBA 1 | Her image process end Democrat able billion. | 19 | Economic rock huge a nation kitchen. | 1 | 38 | Moderate | 2 | Low | 6325981.48 | 332946.39 | 297 | 15 | Minor | Quality | Concept | Procurement | Band 2 | Design | Commercial | Construction | RBS-202.6 | 2026-04-11 | 2026-07-04 | Yes | Project 7 | PLAN-6598 | Compare age data past her but ability. | RESP-41632 | William Rogers | Mitigation for Risk-1032 | Not Started | Late artist one lose size bit among human. | 2026-03-01 | 2026-05-05 | 64 | 2026-05-05 | Yes | 2026-03-02 | 976512.35 | 1149123.98 | 100 | RISK-1020 | Related Risk Title 32 | Closed
Risk | North | Washingtonborough | Hospitality | PRJ-569 | SUB-3 | Project 17 | Commercial | On Hold | RISK-1033 | 2026-03-01 | 2026-06-09 | Delay in design approval | Everybody focus describe away kid herself. | Customer reach during travel certainly. | Level both garden back follow represent. | 2026-03-13 | Closed | 2026-06-16 | Sarah Collins | Execution | RIBA 2 | In event bed thousand the coach. | 10 | Anyone send goal whom growth. | 1 | 50 | Low | 5 | Moderate | 6645258.14 | 664525.81 | 55 | 5 | Threat | Time | Handover | Construction | Band 2 | Commercial | Construction | Authority | RBS-470.1 | 2026-03-27 | 2026-07-05 | Yes | Project 3 | PLAN-4267 | Child whole movie wait speak generation house. | RESP-82543 | Jennifer Wiley | Mitigation for Risk-1033 | In Progress | Stage many recent modern keep. | 2026-03-01 | 2026-04-02 | 31 | 2026-04-02 | Yes | 2026-03-02 | 974137.91 | 1008393.44 | 100 | RISK-1076 | Related Risk Title 33 | Closed
Risk | Central | West Jasmineview | Hospitality | PRJ-558 | SUB-7 | Project 16 | Development | On Hold | RISK-1034 | 2026-03-01 | 2026-04-13 | Delay in material delivery | Radio radio house other. | Floor skill treatment maybe. | Per thank statement. | 2026-03-29 | Open |  | Amanda Meyer | Handover | RIBA 1 | Although just commercial mention television cause. | 56 | Process senior in firm cup suffer. | 53 | 280 | High | 265 | High | 3764620.98 | 3562944.86 | 255 | 241 | Opportunity | Quality | Handover | Procurement | Band 3 | Procurement | Construction | Procurement | RBS-714.2 | 2026-05-02 | 2026-08-13 | Yes | Project 12 | PLAN-8058 | Possible air recent official want wall buy final. | RESP-45107 | Robert Robinson | Mitigation for Risk-1034 | Not Started | Likely war effect member traditional international teach apply. | 2026-03-01 | 2026-04-26 | 55 | 2026-04-26 | No | 2026-03-02 | 1681926.11 | 1826728.65 | 100 | RISK-1088 | Related Risk Title 34 | Open
Risk | North | Martinfurt | Infrastructure | PRJ-207 | SUB-1 | Project 10 | Commercial | On Hold | RISK-1035 | 2026-03-01 | 2026-04-16 | Delay in design approval | Floor space factor recognize peace fact cultural. | Action today during miss act Congress. | Force make matter control political city. | 2026-03-03 | Open |  | Angela Morris | Handover | RIBA 3 | Affect return sit born recognize street color. | 25 | Painting describe statement probably he place measure thus. | 19 | 25 | Moderate | 19 | Low | 4611222.4 | 3504529.02 | 78 | 59 | Minor | Reputation | Concept | Construction | Band 2 | Authority | Authority | Construction | RBS-761.6 | 2026-03-10 | 2026-05-12 | Yes | Project 9 | PLAN-6883 | Have here itself tell participant small. | RESP-23008 | Gregory Baker | Mitigation for Risk-1035 | In Progress | Although successful success perhaps nature. | 2026-03-01 | 2026-05-15 | 74 | 2026-05-15 | No | 2026-03-02 | 725077.06 | 382519.47 | 52.76 | RISK-1000 | Related Risk Title 35 | Open
Risk | South | Lambfort | Entertainment | PRJ-613 | SUB-1 | Project 1 | Development | Completed | RISK-1036 | 2026-03-01 | 2026-05-01 | Delay in design approval | Project certain treatment ball. | Six finally safe financial. | Sport avoid statement I. | 2026-03-16 | Closed | 2026-05-03 | Daniel Brown | Execution | RIBA 5 | Matter if hair put. | 13 | Kitchen kid cold role address. | 11 | 52 | Moderate | 44 | Moderate | 9768201.37 | 8265401.16 | 85 | 71 | Opportunity | Time | Design | Construction | Band 1 | Commercial | Construction | Design | RBS-399.3 | 2026-03-18 | 2026-04-20 | Yes | Project 2 | PLAN-7092 | Manage wear yeah. | RESP-30086 | Michelle Kramer | Mitigation for Risk-1036 | Not Started | Themselves south student. | 2026-03-01 | 2026-04-08 | 37 | 2026-04-08 | No | 2026-03-02 | 735211.54 | 399225.42 | 54.3 | RISK-1034 | Related Risk Title 36 | Closed
Risk | Central | Howardstad | Entertainment | PRJ-974 | SUB-20 | Project 12 | Commercial | Delayed | RISK-1037 | 2026-03-01 | 2026-05-03 | Delay in design approval | Anything find tend model trip reveal individual. | Natural network service what. | Eye beyond she example. | 2026-03-18 | Open |  | Jamie Johnson | Design | RIBA 3 | Man two risk major center article know. | 72 | Crime happy them risk party area then indicate. | 33 | 144 | Low | 66 | Low | 2162957.12 | 991355.35 | 29 | 13 | Opportunity | Cost | Design | Commercial | Band 1 | Design | Commercial | Procurement | RBS-270.5 | 2026-05-07 | 2026-09-11 | No | Project 4 | PLAN-1130 | Out miss time beyond bill shoulder. | RESP-73379 | Glen Simpson DVM | Mitigation for Risk-1037 | Completed | Public analysis candidate body. | 2026-03-01 | 2026-04-28 | 57 | 2026-04-28 | Yes | 2026-03-02 | 1331979.38 | 671296.2 | 50.4 | RISK-1052 | Related Risk Title 37 | Open
Risk | North | Smithstad | Entertainment | PRJ-413 | SUB-5 | Project 20 | Delivery | Delayed | RISK-1038 | 2026-03-01 | 2026-05-29 | Delay in design approval | Occur describe so investment by next cup. | Draw provide receive reason soldier nice foot. | Onto rate everybody million. | 2026-03-21 | Mitigating |  | Nancy Allen | Design | RIBA 4 | Parent I hour change. | 59 | Program seem bring reality together mean once little. | 19 | 118 | Low | 38 | Critical | 6921758.31 | 2229040.81 | 266 | 85 | Opportunity | Reputation | Design | Procurement | Band 1 | Commercial | Procurement | Construction | RBS-425.3 | 2026-04-23 | 2026-07-23 | Yes | Project 1 | PLAN-6416 | Back which common almost above always similar. | RESP-42939 | Kristopher Mcpherson | Mitigation for Risk-1038 | Completed | Suddenly determine hope skin ok machine add. | 2026-03-01 | 2026-05-21 | 80 | 2026-05-21 | No | 2026-03-02 | 1364315.33 | 1116646.18 | 81.85 | RISK-1020 | Related Risk Title 38 | Mitigating
Risk | Waterfront | North Dylanborough | Hospitality | PRJ-858 | SUB-13 | Project 13 | Delivery | Completed | RISK-1039 | 2026-03-01 | 2026-05-25 | Delay in design approval | Red station join be crime form south claim. | Kind nature certainly voice sort finally much. | Up one pressure her surface. | 2026-03-08 | Mitigating |  | Dana Peterson | Execution | RIBA 3 | Little soldier key. | 64 | Image according everything recently want unit day. | 47 | 256 | Low | 188 | Low | 4625744.55 | 3397031.15 | 330 | 242 | Opportunity | Quality | Handover | Authority | Band 3 | Commercial | Design | Authority | RBS-248.7 | 2026-03-31 | 2026-05-21 | No | Project 9 | PLAN-3386 | Ever surface similar might magazine food suddenly. | RESP-13054 | Patricia Ramirez | Mitigation for Risk-1039 | Completed | Society explain increase nothing call. | 2026-03-01 | 2026-04-26 | 55 | 2026-04-26 | No | 2026-03-02 | 1097131.03 | 1213167.63 | 100 | RISK-1049 | Related Risk Title 39 | Mitigating
Risk | South | New Johnchester | Entertainment | PRJ-341 | SUB-17 | Project 19 | Commercial | Delayed | RISK-1040 | 2026-03-01 | 2026-05-03 | Delay in authority clearance | Growth let capital early movie. | Style west mean crime half. | Nor build require environmental learn hotel. | 2026-03-16 | Closed | 2026-05-29 | Laura Phillips | Execution | RIBA 4 | Rise candidate decision product have second agree. | 45 | Despite today dark quality. | 13 | 90 | High | 26 | High | 2315933.55 | 669047.47 | 48 | 13 | Threat | Time | Design | Commercial | Band 3 | Procurement | Procurement | Commercial | RBS-212.5 | 2026-04-14 | 2026-08-09 | No | Project 7 | PLAN-6917 | Smile activity source rest account candidate. | RESP-27930 | Becky Jordan | Mitigation for Risk-1040 | Completed | Level discussion sense same likely matter religious. | 2026-03-01 | 2026-04-07 | 36 | 2026-04-07 | No | 2026-03-02 | 1573924.26 | 1542113.64 | 97.98 | RISK-1013 | Related Risk Title 40 | Closed
Risk | North | Robertton | Entertainment | PRJ-718 | SUB-9 | Project 10 | Development | On Hold | RISK-1041 | 2026-03-01 | 2026-06-14 | Delay in design approval | Measure understand edge civil all although husband. | Loss its on every fight several. | Item expert close national region ball have. | 2026-03-21 | Mitigating |  | Adam Wu | Handover | RIBA 2 | Theory interview perhaps should beyond deep have management. | 15 | Spend involve town indicate bit indicate. | 7 | 60 | Low | 28 | Low | 3053451.45 | 1424944.01 | 19 | 8 | Opportunity | Quality | Concept | Procurement | Band 3 | Procurement | Commercial | Authority | RBS-459.5 | 2026-04-12 | 2026-06-06 | Yes | Project 15 | PLAN-7734 | Strong professional high while happy follow. | RESP-89025 | Linda Estes | Mitigation for Risk-1041 | In Progress | Move fine decide front cell. | 2026-03-01 | 2026-05-10 | 69 | 2026-05-10 | No | 2026-03-02 | 917431.26 | 693834.7 | 75.63 | RISK-1082 | Related Risk Title 41 | Mitigating
Risk | Central | Ryanborough | Hospitality | PRJ-373 | SUB-18 | Project 4 | Delivery | Active | RISK-1042 | 2026-03-01 | 2026-06-28 | Delay in authority clearance | List himself how turn. | Least pull scene. | Film medical hard win close game. | 2026-03-31 | Mitigating |  | Elizabeth Pearson | Execution | RIBA 3 | Show class deep instead model be. | 20 | Fish let once future quality. | 9 | 80 | High | 36 | Low | 3276842.04 | 1474578.92 | 147 | 66 | Threat | Time | Concept | Design | Band 3 | Authority | Construction | Procurement | RBS-420.3 | 2026-04-16 | 2026-07-18 | Yes | Project 11 | PLAN-2998 | Arm off cup capital go. | RESP-43532 | Susan Martinez | Mitigation for Risk-1042 | Not Started | Tax Republican believe. | 2026-03-01 | 2026-05-24 | 83 | 2026-05-24 | Yes | 2026-03-02 | 1444270.7 | 1118361.65 | 77.43 | RISK-1026 | Related Risk Title 42 | Mitigating
Risk | South | North Loribury | Infrastructure | PRJ-726 | SUB-15 | Project 1 | Commercial | Completed | RISK-1043 | 2026-03-01 | 2026-06-08 | Delay in design approval | East everybody stand son various wear debate. | Image reality nice degree high. | Mission certainly among we thank. | 2026-03-16 | Open |  | Nicole Smith | Design | RIBA 3 | Down whether identify rock article. | 39 | School water player. | 31 | 39 | Moderate | 31 | Low | 3512736.6 | 2792175.25 | 264 | 209 | Threat | Quality | Design | Authority | Band 1 | Authority | Construction | Design | RBS-999.5 | 2026-03-27 | 2026-06-19 | Yes | Project 13 | PLAN-8084 | Represent big traditional fight window. | RESP-41063 | Matthew Barron | Mitigation for Risk-1043 | Completed | Recent reduce name ever wind skin place us. | 2026-03-01 | 2026-06-05 | 95 | 2026-06-05 | No | 2026-03-02 | 854592.15 | 747972.03 | 87.52 | RISK-1039 | Related Risk Title 43 | Open
Risk | Central | Jenkinshaven | Infrastructure | PRJ-623 | SUB-7 | Project 20 | Commercial | Completed | RISK-1044 | 2026-03-01 | 2026-04-16 | Delay in material delivery | Them window network. | Attack international include individual use dream when. | Fine choice new simple attention large. | 2026-03-28 | Closed | 2026-04-29 | Bryan Franco | Design | RIBA 3 | Interesting but firm number. | 28 | Mother down these southern foreign. | 22 | 28 | Low | 22 | High | 2320489.34 | 1823241.62 | 264 | 207 | Threat | Reputation | Design | Commercial | Band 3 | Authority | Commercial | Procurement | RBS-424.5 | 2026-05-15 | 2026-10-30 | No | Project 7 | PLAN-3440 | Name we million four sit hit offer. | RESP-69263 | Ashley Barker | Mitigation for Risk-1044 | Completed | Piece whom certainly strong. | 2026-03-01 | 2026-04-29 | 58 | 2026-04-29 | No | 2026-03-02 | 75181.62 | 74809.58 | 99.51 | RISK-1032 | Related Risk Title 44 | Closed
Risk | Central | Diazburgh | Hospitality | PRJ-799 | SUB-3 | Project 2 | Commercial | Delayed | RISK-1045 | 2026-03-01 | 2026-05-25 | Delay in design approval | Personal amount woman follow. | Seven approach sure local herself issue investment. | Off oil inside record themselves another huge either. | 2026-03-27 | Open |  | Nathan Peck | Execution | RIBA 1 | Stuff sure speech let boy. | 58 | Interesting pull media note risk another. | 24 | 58 | High | 24 | Critical | 6067034.71 | 2510497.12 | 192 | 79 | Opportunity | Quality | Concept | Procurement | Band 2 | Design | Commercial | Design | RBS-620.9 | 2026-03-31 | 2026-05-11 | Yes | Project 7 | PLAN-2007 | Together feel report type popular list available. | RESP-55712 | Sarah Huff | Mitigation for Risk-1045 | Completed | Three college trade goal. | 2026-03-01 | 2026-05-21 | 80 | 2026-05-21 | No | 2026-03-02 | 1063702.85 | 618934.81 | 58.19 | RISK-1100 | Related Risk Title 45 | Open
Risk | Central | Kellyton | Hospitality | PRJ-751 | SUB-16 | Project 7 | Development | Completed | RISK-1046 | 2026-03-01 | 2026-04-27 | Delay in material delivery | Carry soon main. | Painting field push over although. | Action policy professor later put doctor. | 2026-03-17 | Open |  | Dr. Shelly Martinez | Design | RIBA 5 | Business notice individual fund. | 79 | Chair act minute product strong employee trip. | 35 | 395 | Moderate | 175 | High | 8782702.42 | 3891070.69 | 304 | 134 | Threat | Quality | Handover | Construction | Band 1 | Construction | Construction | Construction | RBS-125.5 | 2026-03-21 | 2026-09-17 | No | Project 10 | PLAN-6484 | Room assume because analysis walk. | RESP-37002 | Jennifer Yoder PhD | Mitigation for Risk-1046 | In Progress | Whom around protect like between pattern. | 2026-03-01 | 2026-04-02 | 31 | 2026-04-02 | No | 2026-03-02 | 1544714.77 | 1449350.25 | 93.83 | RISK-1060 | Related Risk Title 46 | Open
Risk | Waterfront | South Nicholasland | Infrastructure | PRJ-957 | SUB-12 | Project 11 | Commercial | Delayed | RISK-1047 | 2026-03-01 | 2026-03-24 | Delay in design approval | Each cup customer price plan body. | Particularly face accept from kitchen above and. | These suggest I unit. | 2026-03-09 | Closed | 2026-04-21 | Paige Macdonald | Design | RIBA 2 | Occur training chance house change professional. | 49 | Property time time necessary ball election. | 30 | 49 | Moderate | 30 | Low | 4915296.06 | 3009364.93 | 79 | 48 | Minor | Quality | Design | Authority | Band 3 | Commercial | Commercial | Authority | RBS-217.9 | 2026-04-17 | 2026-05-31 | No | Project 5 | PLAN-7336 | Last role Mrs something evening. | RESP-29425 | Jill Cook | Mitigation for Risk-1047 | Completed | Star true practice. | 2026-03-01 | 2026-05-12 | 71 | 2026-05-12 | Yes | 2026-03-02 | 377848.17 | 384015.45 | 100 | RISK-1032 | Related Risk Title 47 | Closed
Risk | Waterfront | East Sarahville | Infrastructure | PRJ-814 | SUB-20 | Project 8 | Commercial | Completed | RISK-1048 | 2026-03-01 | 2026-04-18 | Delay in authority clearance | Central resource throw from discussion address record style. | Suddenly national argue option. | Trouble fight reach. | 2026-03-03 | Open |  | Kimberly Pierce | Handover | RIBA 3 | Clearly already their suddenly bring though he. | 64 | I black easy billion. | 9 | 256 | Critical | 36 | Moderate | 8124850.45 | 1142557.09 | 19 | 2 | Minor | Reputation | Execution | Design | Band 2 | Construction | Construction | Commercial | RBS-628.6 | 2026-03-19 | 2026-07-11 | Yes | Project 3 | PLAN-5624 | Team be low Mrs. | RESP-83583 | Heather Park | Mitigation for Risk-1048 | In Progress | Challenge more minute manager. | 2026-03-01 | 2026-05-26 | 85 | 2026-05-26 | No | 2026-03-02 | 317056.08 | 267231.86 | 84.29 | RISK-1011 | Related Risk Title 48 | Open
Risk | South | West Ralphmouth | Infrastructure | PRJ-666 | SUB-8 | Project 9 | Commercial | Active | RISK-1049 | 2026-03-01 | 2026-04-24 | Delay in design approval | Executive newspaper ever care occur use. | Kid question game break main expect. | Together improve other democratic glass. | 2026-03-26 | Closed | 2026-05-15 | John Graham | Execution | RIBA 1 | Effort property up thousand church deal. | 53 | Poor decision same speak my computer. | 21 | 212 | Low | 84 | Moderate | 5983938.82 | 2370994.63 | 17 | 6 | Opportunity | Time | Design | Authority | Band 1 | Procurement | Design | Procurement | RBS-280.4 | 2026-04-19 | 2026-07-10 | Yes | Project 17 | PLAN-4744 | Decision hour produce positive develop. | RESP-96473 | Sarah Peck | Mitigation for Risk-1049 | Not Started | Could can part figure. | 2026-03-01 | 2026-05-07 | 66 | 2026-05-07 | No | 2026-03-02 | 714525.88 | 690196.77 | 96.6 | RISK-1012 | Related Risk Title 49 | Closed
Risk | Central | Port Rachael | Hospitality | PRJ-551 | SUB-4 | Project 17 | Delivery | Completed | RISK-1050 | 2026-03-01 | 2026-05-21 | Delay in material delivery | Represent understand truth assume election. | Not her style once science Democrat themselves. | Message trip better against enjoy language second talk. | 2026-03-08 | Closed | 2026-06-07 | Tonya Henson | Execution | RIBA 3 | Better however anyone place however might. | 33 | Chance message number. | 22 | 165 | Critical | 110 | High | 3266970.6 | 2177980.4 | 277 | 184 | Opportunity | Time | Concept | Procurement | Band 1 | Authority | Authority | Design | RBS-843.5 | 2026-04-24 | 2026-08-22 | Yes | Project 13 | PLAN-1543 | Travel perhaps southern new wide why media light. | RESP-15260 | Melissa Cole | Mitigation for Risk-1050 | Not Started | Who start claim. | 2026-03-01 | 2026-06-16 | 106 | 2026-06-16 | No | 2026-03-02 | 1439805.88 | 1206459.44 | 83.79 | RISK-1001 | Related Risk Title 50 | Closed
Risk | North | East Rachelmouth | Infrastructure | PRJ-916 | SUB-14 | Project 12 | Commercial | Delayed | RISK-1051 | 2026-03-01 | 2026-03-18 | Delay in authority clearance | Heavy body attention sure detail surface. | Body herself up. | Painting standard any difficult. | 2026-03-07 | Open |  | Yvonne Morris | Handover | RIBA 4 | Treat scene onto. | 11 | Power most stock level. | 11 | 33 | Critical | 33 | Moderate | 9870408.82 | 9870408.82 | 308 | 308 | Opportunity | Reputation | Concept | Authority | Band 2 | Procurement | Construction | Construction | RBS-228.8 | 2026-03-24 | 2026-09-18 | Yes | Project 13 | PLAN-4637 | Cut effect operation for cultural exist various. | RESP-92714 | Andrew Gutierrez | Mitigation for Risk-1051 | In Progress | Development tax he letter position with. | 2026-03-01 | 2026-05-31 | 90 | 2026-05-31 | Yes | 2026-03-02 | 975709.04 | 755629.2 | 77.44 | RISK-1094 | Related Risk Title 51 | Open
Risk | Central | Loganburgh | Hospitality | PRJ-589 | SUB-11 | Project 9 | Delivery | Delayed | RISK-1052 | 2026-03-01 | 2026-04-26 | Delay in design approval | Call join her vote ball charge fill. | Know authority again how often. | Report alone business choose. | 2026-03-08 | Open |  | Dawn Ramos | Design | RIBA 2 | Loss PM tree. | 75 | Throw finish new. | 4 | 150 | Critical | 8 | Moderate | 7971587.64 | 425151.34 | 175 | 9 | Threat | Time | Design | Procurement | Band 2 | Procurement | Construction | Procurement | RBS-991.7 | 2026-05-02 | 2026-06-22 | No | Project 20 | PLAN-3950 | Happy now their daughter join wear sure. | RESP-42625 | Mark Brown | Mitigation for Risk-1052 | Completed | Bar newspaper phone represent personal modern my election. | 2026-03-01 | 2026-05-09 | 68 | 2026-05-09 | No | 2026-03-02 | 1949319.71 | 1468101.37 | 75.31 | RISK-1096 | Related Risk Title 52 | Open
Risk | South | Tapiaport | Hospitality | PRJ-360 | SUB-8 | Project 19 | Delivery | Completed | RISK-1053 | 2026-03-01 | 2026-05-01 | Delay in design approval | Wear middle provide call every but visit pull. | Evening and just answer describe American investment. | Owner represent send head western it hard nature. | 2026-03-13 | Closed | 2026-05-23 | William Wise | Handover | RIBA 3 | Science everything interest air suddenly our since meeting. | 72 | Receive son theory away feeling her as. | 18 | 72 | Moderate | 18 | Critical | 4802178.05 | 1200544.51 | 221 | 55 | Threat | Time | Handover | Construction | Band 3 | Authority | Authority | Procurement | RBS-264.4 | 2026-03-20 | 2026-08-09 | No | Project 15 | PLAN-2848 | Trouble still American accept right mother area owner. | RESP-37812 | Phillip Collins | Mitigation for Risk-1053 | In Progress | Wrong star front at. | 2026-03-01 | 2026-06-19 | 109 | 2026-06-19 | Yes | 2026-03-02 | 1802262.12 | 1104030.51 | 61.26 | RISK-1026 | Related Risk Title 53 | Closed
Risk | Central | South Sarahhaven | Entertainment | PRJ-542 | SUB-9 | Project 8 | Development | Completed | RISK-1054 | 2026-03-01 | 2026-05-27 | Delay in material delivery | Court rather value quickly program scene. | Standard news save act never. | Kid magazine those instead every. | 2026-03-05 | Closed | 2026-06-05 | Michelle Tucker | Design | RIBA 1 | Record so network movie. | 16 | Think push environment yard attention different. | 3 | 16 | Low | 3 | Critical | 1572576.36 | 294858.07 | 14 | 2 | Opportunity | Cost | Handover | Authority | Band 1 | Design | Commercial | Authority | RBS-223.6 | 2026-03-25 | 2026-05-12 | No | Project 20 | PLAN-5348 | These section after. | RESP-45543 | Rodney Mcintyre | Mitigation for Risk-1054 | Completed | Reflect seek goal hot happy keep. | 2026-03-01 | 2026-05-10 | 69 | 2026-05-10 | No | 2026-03-02 | 1156710.25 | 700309.61 | 60.54 | RISK-1041 | Related Risk Title 54 | Closed
Risk | South | Marytown | Entertainment | PRJ-910 | SUB-2 | Project 7 | Development | Completed | RISK-1055 | 2026-03-01 | 2026-04-24 | Delay in authority clearance | Finally late responsibility large. | To officer join term approach none. | Unit no stay by. | 2026-03-08 | Open |  | Amanda Smith | Execution | RIBA 1 | Continue health him. | 57 | Simply everyone boy site section art hit process. | 54 | 114 | Moderate | 108 | Low | 5858193.69 | 5549867.71 | 51 | 48 | Threat | Quality | Handover | Design | Band 3 | Design | Construction | Construction | RBS-607.6 | 2026-04-22 | 2026-08-01 | Yes | Project 14 | PLAN-6109 | Issue recognize action theory. | RESP-21820 | Kayla Wilcox | Mitigation for Risk-1055 | Completed | Sign sound argue side each life customer positive. | 2026-03-01 | 2026-04-07 | 36 | 2026-04-07 | Yes | 2026-03-02 | 1209875.85 | 1180669.38 | 97.59 | RISK-1010 | Related Risk Title 55 | Open
Risk | North | Lake Sharon | Hospitality | PRJ-755 | SUB-7 | Project 15 | Development | Completed | RISK-1056 | 2026-03-01 | 2026-04-19 | Delay in authority clearance | Garden nothing explain performance and. | Fish camera cultural change rule mention right. | Now which director. | 2026-03-27 | Open |  | Brittney Richardson | Execution | RIBA 5 | Young history opportunity candidate find hotel. | 32 | Continue site second simple picture against. | 1 | 96 | High | 3 | Critical | 1612079.51 | 50377.48 | 189 | 5 | Opportunity | Reputation | Execution | Procurement | Band 3 | Authority | Procurement | Authority | RBS-227.7 | 2026-04-03 | 2026-09-24 | Yes | Project 19 | PLAN-5451 | Population bar green whole lawyer painting change win. | RESP-76835 | Kathryn Cruz | Mitigation for Risk-1056 | In Progress | Particular ball police. | 2026-03-01 | 2026-05-04 | 63 | 2026-05-04 | Yes | 2026-03-02 | 1204327.82 | 678713.38 | 56.36 | RISK-1044 | Related Risk Title 56 | Open
Risk | South | New Elizabeth | Hospitality | PRJ-350 | SUB-6 | Project 15 | Development | Completed | RISK-1057 | 2026-03-01 | 2026-04-15 | Delay in authority clearance | Customer above arrive maybe nature. | Government total mother raise fund toward thus. | Paper west blood up shake really. | 2026-03-06 | Mitigating |  | Mark Fisher | Concept | RIBA 2 | Nation few or follow nothing page. | 58 | Manager door all authority low trial movement. | 26 | 290 | Moderate | 130 | Critical | 8542810.87 | 3829535.91 | 213 | 95 | Opportunity | Cost | Handover | Design | Band 1 | Commercial | Commercial | Commercial | RBS-515.8 | 2026-04-18 | 2026-06-09 | Yes | Project 11 | PLAN-1222 | Choice walk evidence require visit. | RESP-73359 | Nicholas Morris | Mitigation for Risk-1057 | Completed | Music focus individual must company enter. | 2026-03-01 | 2026-05-16 | 75 | 2026-05-16 | No | 2026-03-02 | 1875935.32 | 1395394.59 | 74.38 | RISK-1008 | Related Risk Title 57 | Mitigating
Risk | Waterfront | Jimmyville | Hospitality | PRJ-784 | SUB-13 | Project 5 | Commercial | Delayed | RISK-1058 | 2026-03-01 | 2026-06-09 | Delay in design approval | These score catch ask. | Close yourself attack structure. | Week item thought miss skill time pressure effort. | 2026-03-24 | Closed | 2026-06-14 | William Sanders | Execution | RIBA 4 | Decision instead past our worker father. | 16 | Keep call suddenly happen. | 15 | 64 | High | 60 | High | 6900017.46 | 6468766.37 | 324 | 303 | Threat | Cost | Handover | Design | Band 2 | Commercial | Procurement | Design | RBS-271.5 | 2026-05-19 | 2026-09-20 | No | Project 7 | PLAN-3617 | Bring make experience piece. | RESP-80140 | Joan Moore | Mitigation for Risk-1058 | In Progress | Better author those shoulder. | 2026-03-01 | 2026-06-07 | 97 | 2026-06-07 | Yes | 2026-03-02 | 1486705.05 | 1556373.01 | 100 | RISK-1053 | Related Risk Title 58 | Closed
Risk | North | North David | Infrastructure | PRJ-269 | SUB-18 | Project 16 | Development | Delayed | RISK-1059 | 2026-03-01 | 2026-05-25 | Delay in design approval | Front later employee same. | Still religious night. | Happen three will. | 2026-03-30 | Open |  | Ian Russell | Design | RIBA 5 | Act including nor anyone feel. | 19 | Director speak whether after simple report me less. | 3 | 76 | High | 12 | Critical | 4467690.52 | 705424.82 | 129 | 20 | Opportunity | Time | Execution | Authority | Band 2 | Procurement | Construction | Authority | RBS-706.7 | 2026-04-24 | 2026-08-05 | No | Project 13 | PLAN-8128 | Indeed cause ok appear federal test watch wear. | RESP-20452 | Kim Brown | Mitigation for Risk-1059 | Not Started | Fast there research picture. | 2026-03-01 | 2026-04-09 | 38 | 2026-04-09 | No | 2026-03-02 | 1747918.06 | 1003905.53 | 57.43 | RISK-1099 | Related Risk Title 59 | Open
Risk | North | West Jennifer | Entertainment | PRJ-649 | SUB-14 | Project 3 | Delivery | Completed | RISK-1060 | 2026-03-01 | 2026-05-25 | Delay in authority clearance | Me catch first different piece sure report never. | Single care stay house. | Yes worker recent around pass decision feel treat. | 2026-03-05 | Mitigating |  | Andrea Harris | Handover | RIBA 2 | Majority better money sell think know collection. | 50 | Visit blue at affect girl fish leave. | 6 | 150 | Moderate | 18 | Moderate | 920495.74 | 110459.49 | 218 | 26 | Opportunity | Quality | Handover | Design | Band 2 | Construction | Design | Design | RBS-424.7 | 2026-03-25 | 2026-07-16 | No | Project 18 | PLAN-1556 | Manage feel against. | RESP-93019 | Edward Tapia | Mitigation for Risk-1060 | Not Started | Computer cold the ask. | 2026-03-01 | 2026-04-17 | 46 | 2026-04-17 | No | 2026-03-02 | 1126298.86 | 1226496.41 | 100 | RISK-1085 | Related Risk Title 60 | Mitigating
Risk | Waterfront | Samanthastad | Entertainment | PRJ-624 | SUB-13 | Project 3 | Commercial | Active | RISK-1061 | 2026-03-01 | 2026-05-18 | Delay in authority clearance | Carry owner machine charge. | Hard fire partner. | Wear cup reach site fill message. | 2026-03-19 | Mitigating |  | Mathew Macias | Handover | RIBA 3 | While important good service. | 15 | Policy oil realize everybody wear option. | 5 | 30 | Low | 10 | Moderate | 1889362.47 | 629787.49 | 257 | 85 | Opportunity | Cost | Concept | Authority | Band 1 | Authority | Commercial | Design | RBS-835.8 | 2026-04-19 | 2026-05-30 | No | Project 20 | PLAN-6814 | Conference third like clearly affect class. | RESP-65599 | Patricia Russell | Mitigation for Risk-1061 | In Progress | Information because support. | 2026-03-01 | 2026-04-15 | 44 | 2026-04-15 | Yes | 2026-03-02 | 836619.79 | 584397.27 | 69.85 | RISK-1097 | Related Risk Title 61 | Mitigating
Risk | South | Lake Crystal | Infrastructure | PRJ-266 | SUB-17 | Project 10 | Development | Completed | RISK-1062 | 2026-03-01 | 2026-05-16 | Delay in design approval | Age food commercial appear green support. | State determine act television. | Month military my factor. | 2026-03-04 | Open |  | Heather Warren | Concept | RIBA 2 | Pretty yes current know. | 62 | Mention ground too over wish but price. | 28 | 62 | Low | 28 | Critical | 3072669.1 | 1387657.01 | 41 | 18 | Opportunity | Reputation | Execution | Design | Band 2 | Commercial | Commercial | Construction | RBS-756.6 | 2026-04-25 | 2026-08-09 | No | Project 10 | PLAN-4641 | Pass tree rule your present other finish. | RESP-25988 | Nicholas Turner | Mitigation for Risk-1062 | In Progress | Dark weight system other three. | 2026-03-01 | 2026-04-05 | 34 | 2026-04-05 | No | 2026-03-02 | 1501839.79 | 1436359.22 | 95.64 | RISK-1017 | Related Risk Title 62 | Open
Risk | North | Williamsborough | Entertainment | PRJ-345 | SUB-7 | Project 9 | Delivery | Delayed | RISK-1063 | 2026-03-01 | 2026-05-23 | Delay in authority clearance | Production expert ten behavior together station. | Street off away one today. | Style often light medical hand. | 2026-03-12 | Mitigating |  | Kristin Smith | Concept | RIBA 4 | Under hundred employee page society he can. | 33 | Phone star theory cell president tell. | 16 | 33 | High | 16 | High | 9832140.61 | 4767098.48 | 314 | 152 | Opportunity | Reputation | Concept | Design | Band 2 | Design | Construction | Authority | RBS-396.4 | 2026-04-05 | 2026-06-30 | No | Project 20 | PLAN-8890 | These project station season enjoy. | RESP-72968 | Kristin Lewis | Mitigation for Risk-1063 | Completed | Western southern major past outside must our house. | 2026-03-01 | 2026-05-25 | 84 | 2026-05-25 | No | 2026-03-02 | 79368.06 | 63948.52 | 80.57 | RISK-1082 | Related Risk Title 63 | Mitigating
Risk | Waterfront | East Hector | Infrastructure | PRJ-516 | SUB-1 | Project 9 | Development | Active | RISK-1064 | 2026-03-01 | 2026-06-09 | Delay in authority clearance | Deep national by movie possible. | Painting night system response bit discover. | Senior wind agree garden five. | 2026-03-14 | Closed | 2026-06-22 | Debra Rodriguez | Execution | RIBA 4 | Section pressure market successful always sea music. | 27 | Join likely generation ball quickly care happen. | 16 | 81 | Low | 48 | Low | 7615364.69 | 4512808.71 | 216 | 128 | Opportunity | Time | Handover | Commercial | Band 2 | Authority | Authority | Commercial | RBS-818.2 | 2026-04-13 | 2026-08-27 | No | Project 17 | PLAN-4112 | Mouth off street. | RESP-35467 | Sarah Howard | Mitigation for Risk-1064 | Completed | Investment in end hard tonight. | 2026-03-01 | 2026-04-12 | 41 | 2026-04-12 | Yes | 2026-03-02 | 422886.01 | 429446.4 | 100 | RISK-1071 | Related Risk Title 64 | Closed
Risk | Central | East Tammyville | Entertainment | PRJ-326 | SUB-17 | Project 1 | Development | On Hold | RISK-1065 | 2026-03-01 | 2026-04-23 | Delay in design approval | Leg tough draw cultural. | Life side agent religious despite scientist. | Floor happy everyone. | 2026-03-26 | Closed | 2026-05-12 | Robert Gutierrez | Execution | RIBA 2 | Outside return some control painting. | 22 | Plant two improve half long significant. | 3 | 66 | Low | 9 | Critical | 4458243.48 | 607942.29 | 322 | 43 | Threat | Time | Design | Design | Band 3 | Authority | Commercial | Commercial | RBS-965.3 | 2026-05-19 | 2026-09-20 | Yes | Project 3 | PLAN-7829 | Pick individual perhaps own door almost important. | RESP-48705 | Angela Nelson | Mitigation for Risk-1065 | Not Started | Attack catch democratic institution light special toward. | 2026-03-01 | 2026-06-07 | 97 | 2026-06-07 | No | 2026-03-02 | 1688675.47 | 1175378.18 | 69.6 | RISK-1044 | Related Risk Title 65 | Closed
Risk | South | East James | Entertainment | PRJ-508 | SUB-9 | Project 17 | Commercial | Active | RISK-1066 | 2026-03-01 | 2026-03-31 | Delay in authority clearance | Assume draw wonder manage develop area. | Probably ten reflect perhaps leave past blue. | Institution notice test thus full. | 2026-03-13 | Open |  | Janet Hall | Handover | RIBA 5 | Less success suggest series. | 42 | Plan customer relationship kitchen their seat trip similar. | 13 | 42 | Low | 13 | Critical | 333702.75 | 103288.95 | 294 | 91 | Minor | Reputation | Concept | Construction | Band 3 | Design | Authority | Procurement | RBS-444.4 | 2026-04-25 | 2026-06-24 | No | Project 20 | PLAN-1977 | Center join necessary arm sign PM what. | RESP-37859 | Courtney Lopez | Mitigation for Risk-1066 | Not Started | Actually writer admit response mission. | 2026-03-01 | 2026-05-26 | 85 | 2026-05-26 | Yes | 2026-03-02 | 62138.03 | 74514.53 | 100 | RISK-1086 | Related Risk Title 66 | Open
Risk | Central | East Staceyburgh | Entertainment | PRJ-808 | SUB-15 | Project 6 | Commercial | On Hold | RISK-1067 | 2026-03-01 | 2026-04-18 | Delay in material delivery | Record weight left half nature. | Center food individual issue various tree. | Parent plant fill decade majority continue out. | 2026-03-24 | Mitigating |  | Paul Padilla | Concept | RIBA 2 | Indeed answer machine new owner source. | 71 | Difficult national hear throughout blue. | 68 | 355 | Moderate | 340 | Critical | 3906292.77 | 3741238.15 | 116 | 111 | Opportunity | Time | Concept | Procurement | Band 3 | Authority | Design | Procurement | RBS-490.5 | 2026-04-30 | 2026-06-04 | No | Project 18 | PLAN-3478 | Bar throughout them whom. | RESP-11022 | Dustin Bass | Mitigation for Risk-1067 | In Progress | For room price politics stay together. | 2026-03-01 | 2026-04-07 | 36 | 2026-04-07 | No | 2026-03-02 | 1091517.61 | 717686.53 | 65.75 | RISK-1056 | Related Risk Title 67 | Mitigating
Risk | Central | Andrewsville | Hospitality | PRJ-315 | SUB-10 | Project 11 | Development | Active | RISK-1068 | 2026-03-01 | 2026-05-26 | Delay in material delivery | Pull actually the section partner several once. | Hit series commercial able change stock. | Program senior rise price trial ask. | 2026-03-16 | Open |  | Alicia Espinoza | Design | RIBA 4 | Audience program major rise age. | 72 | Carry case girl speech some audience health. | 39 | 288 | Low | 156 | High | 5051005.2 | 2735961.15 | 298 | 161 | Threat | Reputation | Execution | Procurement | Band 2 | Design | Design | Design | RBS-826.8 | 2026-05-07 | 2026-07-21 | Yes | Project 2 | PLAN-1051 | Citizen your last third. | RESP-52901 | Donna Jackson | Mitigation for Risk-1068 | Not Started | Throw particular involve most. | 2026-03-01 | 2026-04-30 | 59 | 2026-04-30 | Yes | 2026-03-02 | 1172195.75 | 903460.42 | 77.07 | RISK-1031 | Related Risk Title 68 | Open
Risk | North | Lake Amanda | Entertainment | PRJ-396 | SUB-7 | Project 7 | Delivery | Active | RISK-1069 | 2026-03-01 | 2026-05-07 | Delay in design approval | Over keep share its. | Follow middle similar somebody station crime seven. | Young machine American town. | 2026-03-17 | Closed | 2026-05-21 | Richard Williams | Design | RIBA 4 | Also treat one feeling. | 19 | Can item every man window pass. | 14 | 57 | High | 42 | Low | 7592288.58 | 5594317.9 | 176 | 129 | Opportunity | Cost | Handover | Commercial | Band 3 | Procurement | Authority | Authority | RBS-666.5 | 2026-04-10 | 2026-08-21 | Yes | Project 3 | PLAN-4613 | New well fine. | RESP-64006 | Kelly Ramos | Mitigation for Risk-1069 | Not Started | Guess notice hard central research war about. | 2026-03-01 | 2026-05-13 | 72 | 2026-05-13 | No | 2026-03-02 | 1420267.48 | 1612472.15 | 100 | RISK-1042 | Related Risk Title 69 | Closed
Risk | North | Christopherfort | Entertainment | PRJ-840 | SUB-18 | Project 4 | Commercial | On Hold | RISK-1070 | 2026-03-01 | 2026-05-05 | Delay in authority clearance | Seek use key eat whole focus. | Age anything generation color stage measure on. | Matter amount fast all door. | 2026-03-09 | Closed | 2026-05-17 | Mark Esparza | Handover | RIBA 1 | Clearly we still seek although answer. | 18 | Maybe particular partner bill. | 9 | 36 | Low | 18 | Moderate | 2535692.06 | 1267846.03 | 353 | 176 | Minor | Reputation | Execution | Design | Band 2 | Commercial | Construction | Construction | RBS-976.2 | 2026-04-18 | 2026-10-06 | No | Project 18 | PLAN-5506 | Both include manager attack still wide yeah imagine. | RESP-74572 | David Wilkinson | Mitigation for Risk-1070 | Completed | Because leg resource. | 2026-03-01 | 2026-05-27 | 86 | 2026-05-27 | No | 2026-03-02 | 1931235.7 | 1596593.15 | 82.67 | RISK-1015 | Related Risk Title 70 | Closed
Risk | Central | Perryborough | Hospitality | PRJ-404 | SUB-19 | Project 7 | Commercial | Active | RISK-1071 | 2026-03-01 | 2026-06-21 | Delay in material delivery | Add world magazine. | Final security personal. | Us manage radio begin mean. | 2026-03-23 | Mitigating |  | Jenny Wagner | Execution | RIBA 4 | Effect read walk prevent color on forward. | 63 | Prevent Republican officer laugh realize. | 19 | 126 | Moderate | 38 | Critical | 3046503.38 | 918786.73 | 171 | 51 | Opportunity | Time | Handover | Procurement | Band 3 | Commercial | Procurement | Design | RBS-567.2 | 2026-04-29 | 2026-08-27 | No | Project 16 | PLAN-7580 | Strategy all start person west. | RESP-21882 | Amanda Howell | Mitigation for Risk-1071 | Completed | Just whose network plan wide. | 2026-03-01 | 2026-04-25 | 54 | 2026-04-25 | No | 2026-03-02 | 1113535.65 | 930079.46 | 83.52 | RISK-1031 | Related Risk Title 71 | Mitigating
Risk | Central | Port Carlos | Hospitality | PRJ-117 | SUB-1 | Project 17 | Development | Completed | RISK-1072 | 2026-03-01 | 2026-04-22 | Delay in design approval | Admit we clearly local mention adult difficult. | Hair own son experience determine nature good. | All push space particular compare. | 2026-03-21 | Closed | 2026-05-22 | Henry Byrd | Handover | RIBA 2 | Commercial agreement article money down. | 64 | Fill yeah hundred affect recently material appear foreign. | 15 | 320 | Low | 75 | Low | 6478080.59 | 1518300.14 | 353 | 82 | Threat | Reputation | Design | Procurement | Band 2 | Commercial | Procurement | Procurement | RBS-191.4 | 2026-04-19 | 2026-08-07 | No | Project 12 | PLAN-3044 | Interesting question herself. | RESP-67674 | Shelby Choi | Mitigation for Risk-1072 | Completed | Defense house situation join professor. | 2026-03-01 | 2026-04-03 | 32 | 2026-04-03 | Yes | 2026-03-02 | 243879.64 | 240764.89 | 98.72 | RISK-1005 | Related Risk Title 72 | Closed
Risk | North | Lisaville | Infrastructure | PRJ-510 | SUB-16 | Project 10 | Development | Active | RISK-1073 | 2026-03-01 | 2026-05-06 | Delay in design approval | Third low someone machine look red. | Themselves into deal great increase recent ready. | Structure throw use. | 2026-03-06 | Mitigating |  | Mark Anderson | Concept | RIBA 5 | Back game force pass happen south simply. | 54 | Factor worry present production. | 33 | 270 | Critical | 165 | Moderate | 5988294.47 | 3659513.29 | 245 | 149 | Minor | Quality | Concept | Procurement | Band 3 | Procurement | Design | Construction | RBS-165.9 | 2026-03-22 | 2026-06-20 | No | Project 11 | PLAN-4419 | Than product billion avoid. | RESP-96868 | Kathleen Murray | Mitigation for Risk-1073 | Not Started | Become carry choice. | 2026-03-01 | 2026-05-29 | 88 | 2026-05-29 | Yes | 2026-03-02 | 1483190.29 | 1593206.77 | 100 | RISK-1030 | Related Risk Title 73 | Mitigating
Risk | Waterfront | South Ashleyfort | Entertainment | PRJ-446 | SUB-8 | Project 17 | Commercial | Completed | RISK-1074 | 2026-03-01 | 2026-04-25 | Delay in design approval | From forget military. | What community issue safe. | Spring ahead everything read. | 2026-03-27 | Closed | 2026-05-13 | Keith Baker | Design | RIBA 5 | According red skin democratic from. | 21 | Edge body too among. | 19 | 63 | Critical | 57 | Critical | 1421057.91 | 1285719.06 | 59 | 53 | Threat | Reputation | Handover | Procurement | Band 3 | Commercial | Commercial | Design | RBS-727.5 | 2026-04-05 | 2026-08-08 | No | Project 8 | PLAN-1391 | Drop message score include. | RESP-45468 | Tyler Johnson | Mitigation for Risk-1074 | Not Started | Charge book finally open. | 2026-03-01 | 2026-06-07 | 97 | 2026-06-07 | No | 2026-03-02 | 516405.16 | 578925.74 | 100 | RISK-1048 | Related Risk Title 74 | Closed
Risk | South | North Samanthafurt | Hospitality | PRJ-337 | SUB-12 | Project 16 | Commercial | Completed | RISK-1075 | 2026-03-01 | 2026-06-03 | Delay in design approval | Son argue admit condition likely white. | Vote truth war idea believe. | Form center behind boy catch thus never. | 2026-03-26 | Closed | 2026-06-22 | John Davis | Handover | RIBA 2 | People country remember. | 28 | Southern box strategy sort series. | 27 | 112 | Moderate | 108 | High | 9814123.31 | 9463618.91 | 68 | 65 | Minor | Cost | Handover | Commercial | Band 1 | Commercial | Authority | Design | RBS-815.2 | 2026-04-17 | 2026-09-07 | No | Project 19 | PLAN-2453 | Forget person election practice instead need trade. | RESP-16549 | William Phillips | Mitigation for Risk-1075 | In Progress | Fill simple answer window plant mouth although may. | 2026-03-01 | 2026-04-18 | 47 | 2026-04-18 | Yes | 2026-03-02 | 1292820.43 | 1306607.67 | 100 | RISK-1089 | Related Risk Title 75 | Closed
Risk | North | Smithside | Entertainment | PRJ-340 | SUB-1 | Project 13 | Commercial | Completed | RISK-1076 | 2026-03-01 | 2026-05-08 | Delay in design approval | Treatment thank million same information meeting. | Fish beat voice themselves such be commercial crime. | Run much along only would week. | 2026-03-14 | Open |  | Mr. Nathan Richardson | Execution | RIBA 5 | Discover even condition budget accept watch prove. | 11 | Rule explain case catch. | 4 | 55 | High | 20 | High | 9627916.39 | 3501060.51 | 46 | 16 | Opportunity | Time | Handover | Construction | Band 1 | Construction | Authority | Procurement | RBS-924.7 | 2026-04-29 | 2026-07-18 | No | Project 11 | PLAN-4610 | Five where speech season. | RESP-14368 | Jane Williams | Mitigation for Risk-1076 | Completed | Law edge fill remain more. | 2026-03-01 | 2026-06-21 | 111 | 2026-06-21 | No | 2026-03-02 | 658240.29 | 485895.09 | 73.82 | RISK-1023 | Related Risk Title 76 | Open
Risk | Waterfront | West Chelseyport | Infrastructure | PRJ-411 | SUB-3 | Project 5 | Commercial | Delayed | RISK-1077 | 2026-03-01 | 2026-05-23 | Delay in authority clearance | Make yourself they give receive kind culture. | Democrat room form low feeling wife financial live. | Close trial significant few. | 2026-03-24 | Mitigating |  | Kayla Ortega | Handover | RIBA 2 | Realize quite treatment doctor as meeting. | 17 | Computer thus billion white difference edge. | 3 | 51 | Low | 9 | Moderate | 7435015.08 | 1312061.48 | 22 | 3 | Opportunity | Quality | Concept | Design | Band 3 | Authority | Construction | Procurement | RBS-191.1 | 2026-05-23 | 2026-09-24 | No | Project 9 | PLAN-5204 | Clear use hair fly result north push. | RESP-42538 | Amanda Snow | Mitigation for Risk-1077 | Completed | Push eye allow wrong music market ahead including. | 2026-03-01 | 2026-04-18 | 47 | 2026-04-18 | No | 2026-03-02 | 922709.45 | 727500.35 | 78.84 | RISK-1067 | Related Risk Title 77 | Mitigating
Risk | North | Riverastad | Entertainment | PRJ-655 | SUB-2 | Project 15 | Development | Completed | RISK-1078 | 2026-03-01 | 2026-05-11 | Delay in material delivery | Whole provide avoid must exist continue. | Traditional thing there interesting there. | Station other feel. | 2026-03-02 | Open |  | Jaime Blake | Execution | RIBA 2 | Move eye imagine way exactly evidence. | 57 | Heart hotel new. | 27 | 114 | Moderate | 54 | Low | 393029.98 | 186172.1 | 61 | 28 | Opportunity | Cost | Execution | Procurement | Band 2 | Commercial | Procurement | Construction | RBS-419.2 | 2026-03-31 | 2026-08-02 | Yes | Project 7 | PLAN-7833 | Available though what always pattern. | RESP-90524 | Michael Henson | Mitigation for Risk-1078 | In Progress | Entire subject participant look not pretty. | 2026-03-01 | 2026-06-28 | 118 | 2026-06-28 | Yes | 2026-03-02 | 1394630.82 | 1146442.71 | 82.2 | RISK-1037 | Related Risk Title 78 | Open
Risk | North | Donaldtown | Hospitality | PRJ-759 | SUB-17 | Project 17 | Development | On Hold | RISK-1079 | 2026-03-01 | 2026-05-22 | Delay in design approval | Pass although often. | Information hit property community nature serious. | Pay weight again garden particularly. | 2026-03-17 | Closed | 2026-06-06 | Ronald Long | Design | RIBA 4 | Hold yes turn against that nothing those business. | 22 | Movie lead low arrive. | 4 | 44 | Low | 8 | Low | 2140364.03 | 389157.1 | 206 | 37 | Minor | Time | Handover | Authority | Band 1 | Construction | Construction | Procurement | RBS-423.8 | 2026-04-02 | 2026-05-24 | No | Project 5 | PLAN-7992 | Computer travel will fall call bank health. | RESP-37360 | Timothy Smith | Mitigation for Risk-1079 | In Progress | Enjoy go important present affect where. | 2026-03-01 | 2026-06-22 | 112 | 2026-06-22 | Yes | 2026-03-02 | 591488.42 | 503266.98 | 85.08 | RISK-1000 | Related Risk Title 79 | Closed
Risk | Waterfront | New Ericchester | Infrastructure | PRJ-914 | SUB-15 | Project 12 | Delivery | Active | RISK-1080 | 2026-03-01 | 2026-05-28 | Delay in material delivery | Base since term as fear. | Group process focus. | Detail then operation not training. | 2026-03-30 | Mitigating |  | Thomas Hale | Design | RIBA 4 | Want see baby specific much tend effect. | 11 | Can rather red report understand service. | 6 | 11 | Critical | 6 | High | 1587389.13 | 865848.62 | 191 | 104 | Opportunity | Reputation | Execution | Authority | Band 2 | Construction | Commercial | Commercial | RBS-162.6 | 2026-04-11 | 2026-10-03 | Yes | Project 3 | PLAN-3321 | Nice night choice age new. | RESP-91448 | Elizabeth Short | Mitigation for Risk-1080 | In Progress | Job government camera yeah almost finish. | 2026-03-01 | 2026-06-16 | 106 | 2026-06-16 | No | 2026-03-02 | 806157.37 | 448152.75 | 55.59 | RISK-1097 | Related Risk Title 80 | Mitigating
Risk | Central | Port Dillon | Hospitality | PRJ-969 | SUB-15 | Project 14 | Delivery | Delayed | RISK-1081 | 2026-03-01 | 2026-04-22 | Delay in material delivery | Traditional until pick model. | Cold indeed before keep challenge test. | Black whose him special body occur. | 2026-03-25 | Closed | 2026-05-21 | Michael Jackson | Execution | RIBA 5 | But north nation after different sell conference. | 54 | Project reveal goal arrive. | 12 | 54 | Moderate | 12 | Critical | 9639329.57 | 2142073.24 | 91 | 20 | Threat | Cost | Execution | Procurement | Band 3 | Design | Design | Procurement | RBS-545.8 | 2026-05-06 | 2026-10-03 | Yes | Project 8 | PLAN-4310 | Ability American magazine line. | RESP-75190 | Mitchell Morton | Mitigation for Risk-1081 | Not Started | Range toward term opportunity five in. | 2026-03-01 | 2026-05-14 | 73 | 2026-05-14 | Yes | 2026-03-02 | 851701.86 | 593728.41 | 69.71 | RISK-1085 | Related Risk Title 81 | Closed
Risk | Waterfront | Port Jose | Infrastructure | PRJ-400 | SUB-2 | Project 16 | Development | On Hold | RISK-1082 | 2026-03-01 | 2026-05-13 | Delay in design approval | Accept blood better step. | Many would second increase like message item fight. | Among star which reason stuff. | 2026-03-07 | Closed | 2026-06-09 | Margaret Mcmahon | Execution | RIBA 2 | Police inside century also something after. | 38 | Pressure real modern five and Congress almost resource. | 2 | 190 | Moderate | 10 | Low | 188367.93 | 9914.1 | 283 | 14 | Minor | Quality | Concept | Design | Band 3 | Authority | Commercial | Commercial | RBS-192.4 | 2026-03-27 | 2026-05-07 | Yes | Project 5 | PLAN-4593 | Just huge send during necessary today. | RESP-50101 | Patrick Cervantes | Mitigation for Risk-1082 | In Progress | Guy least subject. | 2026-03-01 | 2026-05-27 | 86 | 2026-05-27 | Yes | 2026-03-02 | 1883638.33 | 1677942.16 | 89.08 | RISK-1040 | Related Risk Title 82 | Closed
Risk | North | Norrisside | Hospitality | PRJ-114 | SUB-5 | Project 13 | Development | On Hold | RISK-1083 | 2026-03-01 | 2026-05-21 | Delay in authority clearance | Congress bank able property west five. | Stay onto drive sing none. | Party generation concern successful situation unit. | 2026-03-13 | Mitigating |  | Isaac Black | Design | RIBA 5 | Despite general maintain. | 44 | Remain long than evening. | 31 | 176 | Critical | 124 | Low | 4503506.04 | 3172924.71 | 113 | 79 | Minor | Time | Design | Authority | Band 2 | Procurement | Authority | Authority | RBS-626.2 | 2026-04-02 | 2026-08-07 | Yes | Project 12 | PLAN-3035 | Wall whose provide street citizen across. | RESP-43247 | Kathryn Singh MD | Mitigation for Risk-1083 | In Progress | Somebody size several television eye. | 2026-03-01 | 2026-04-05 | 34 | 2026-04-05 | Yes | 2026-03-02 | 1470686.12 | 1650260.23 | 100 | RISK-1098 | Related Risk Title 83 | Mitigating
Risk | Waterfront | New Scottmouth | Infrastructure | PRJ-536 | SUB-3 | Project 3 | Delivery | Delayed | RISK-1084 | 2026-03-01 | 2026-05-03 | Delay in authority clearance | Young level democratic stage. | Experience clearly fill worry adult. | Prevent say the spring white. | 2026-03-14 | Open |  | Gregory Flores | Design | RIBA 2 | Discuss here air perform study. | 25 | Age own exist team. | 18 | 100 | Moderate | 72 | High | 4224179.13 | 3041408.97 | 355 | 255 | Threat | Time | Execution | Construction | Band 1 | Authority | Commercial | Authority | RBS-185.3 | 2026-04-06 | 2026-06-19 | Yes | Project 6 | PLAN-1336 | Myself writer book program. | RESP-76514 | Joseph Rodriguez | Mitigation for Risk-1084 | In Progress | Your agree low low. | 2026-03-01 | 2026-05-31 | 90 | 2026-05-31 | Yes | 2026-03-02 | 320211.15 | 221984.48 | 69.32 | RISK-1037 | Related Risk Title 84 | Open
Risk | North | New Robertmouth | Infrastructure | PRJ-859 | SUB-9 | Project 9 | Development | On Hold | RISK-1085 | 2026-03-01 | 2026-05-01 | Delay in material delivery | Painting field check start blood difference. | Strong fall maybe evening instead food. | Onto bank she particular blood. | 2026-03-06 | Closed | 2026-05-13 | Rachel Gill | Execution | RIBA 2 | Computer deal court. | 20 | Begin ask break determine election card large nation. | 1 | 80 | Critical | 4 | High | 8446459.74 | 422322.99 | 16 | 0 | Opportunity | Quality | Handover | Authority | Band 2 | Design | Design | Design | RBS-583.5 | 2026-03-12 | 2026-06-22 | No | Project 16 | PLAN-2647 | The wonder sell easy. | RESP-50889 | Anthony Escobar | Mitigation for Risk-1085 | Completed | Tv cost carry process message meeting culture. | 2026-03-01 | 2026-05-03 | 62 | 2026-05-03 | No | 2026-03-02 | 585039.06 | 559756.12 | 95.68 | RISK-1002 | Related Risk Title 85 | Closed
Risk | Central | Lisaland | Hospitality | PRJ-450 | SUB-5 | Project 13 | Delivery | Completed | RISK-1086 | 2026-03-01 | 2026-03-16 | Delay in authority clearance | Well take even also. | Can college discover not feeling television society. | Town wrong do total but pay must. | 2026-03-02 | Mitigating |  | Jerry Wood | Design | RIBA 3 | Show minute decide whether true. | 46 | Ready behind any change candidate. | 25 | 92 | Moderate | 50 | High | 3234899.72 | 1758097.67 | 264 | 143 | Threat | Time | Design | Construction | Band 3 | Procurement | Procurement | Procurement | RBS-821.8 | 2026-03-27 | 2026-08-23 | Yes | Project 8 | PLAN-7764 | Method moment though baby myself argue great project. | RESP-89796 | Felicia Bowman | Mitigation for Risk-1086 | Not Started | Agency consider his product article control. | 2026-03-01 | 2026-05-29 | 88 | 2026-05-29 | Yes | 2026-03-02 | 1901705.09 | 1864488.3 | 98.04 | RISK-1023 | Related Risk Title 86 | Mitigating
Risk | Waterfront | South Mary | Entertainment | PRJ-222 | SUB-7 | Project 8 | Commercial | Delayed | RISK-1087 | 2026-03-01 | 2026-03-28 | Delay in authority clearance | Know along begin let with fish mother. | Base true least like car traditional. | Remain article although cold buy. | 2026-03-14 | Closed | 2026-03-31 | Kevin Gutierrez | Concept | RIBA 2 | Allow tell return part leg tend. | 34 | Word suggest respond leader everyone animal. | 11 | 68 | Low | 22 | High | 8746605.75 | 2829784.21 | 124 | 40 | Minor | Cost | Execution | Commercial | Band 3 | Authority | Authority | Procurement | RBS-693.7 | 2026-03-17 | 2026-05-24 | Yes | Project 9 | PLAN-9355 | Might talk all avoid explain. | RESP-76002 | Jonathan Jackson | Mitigation for Risk-1087 | Not Started | Eat have series perform thing live recently work. | 2026-03-01 | 2026-05-26 | 85 | 2026-05-26 | Yes | 2026-03-02 | 1376235.51 | 1333644.8 | 96.91 | RISK-1027 | Related Risk Title 87 | Closed
Risk | North | Robinsonton | Entertainment | PRJ-640 | SUB-19 | Project 10 | Delivery | Completed | RISK-1088 | 2026-03-01 | 2026-03-30 | Delay in authority clearance | Simple explain shake into outside recent. | Room daughter measure sport least care. | West individual director about letter letter. | 2026-03-03 | Open |  | William Oconnell | Execution | RIBA 3 | Bill most friend wide far our. | 40 | Heavy toward least fine learn then cut girl. | 35 | 200 | Critical | 175 | High | 764983.97 | 669360.97 | 152 | 133 | Opportunity | Reputation | Design | Construction | Band 1 | Design | Procurement | Construction | RBS-402.3 | 2026-03-08 | 2026-05-31 | Yes | Project 13 | PLAN-9713 | Natural positive church central. | RESP-83363 | Karen Chavez | Mitigation for Risk-1088 | Completed | News movie color. | 2026-03-01 | 2026-06-25 | 115 | 2026-06-25 | No | 2026-03-02 | 1743483.44 | 1337337.68 | 76.7 | RISK-1063 | Related Risk Title 88 | Open
Risk | Waterfront | West Robertborough | Entertainment | PRJ-987 | SUB-20 | Project 10 | Development | Completed | RISK-1089 | 2026-03-01 | 2026-04-19 | Delay in design approval | Exactly really staff culture. | Next start particular movie collection they choose friend. | Sign these board coach particularly. | 2026-03-08 | Mitigating |  | Brittany Patterson | Handover | RIBA 5 | Beyond health statement man. | 58 | Feel president miss network record instead red deep. | 28 | 174 | High | 84 | High | 3077579 | 1485727.79 | 129 | 62 | Threat | Quality | Concept | Design | Band 2 | Construction | Authority | Authority | RBS-507.2 | 2026-04-28 | 2026-07-23 | No | Project 15 | PLAN-9269 | Time success note body show expect. | RESP-14849 | Carla Levy | Mitigation for Risk-1089 | Completed | Congress seem involve. | 2026-03-01 | 2026-05-09 | 68 | 2026-05-09 | No | 2026-03-02 | 1956552.36 | 1515983.49 | 77.48 | RISK-1060 | Related Risk Title 89 | Mitigating
Risk | South | New Johntown | Hospitality | PRJ-249 | SUB-6 | Project 2 | Delivery | On Hold | RISK-1090 | 2026-03-01 | 2026-06-17 | Delay in design approval | Management south half. | Better deal five a. | Health race news matter girl father window. | 2026-03-30 | Open |  | James Rodriguez | Concept | RIBA 2 | North happen painting expect skin break late suggest. | 64 | Management whatever back her arrive. | 7 | 256 | Moderate | 28 | Moderate | 5557360.02 | 607836.25 | 34 | 3 | Threat | Reputation | Execution | Procurement | Band 2 | Commercial | Authority | Procurement | RBS-606.8 | 2026-04-21 | 2026-07-16 | No | Project 19 | PLAN-5924 | Born bring positive because to appear. | RESP-93232 | Charles Banks | Mitigation for Risk-1090 | Not Started | Message might would play keep. | 2026-03-01 | 2026-06-16 | 106 | 2026-06-16 | No | 2026-03-02 | 550175.83 | 555967.27 | 100 | RISK-1028 | Related Risk Title 90 | Open
Risk | Central | Amyberg | Entertainment | PRJ-214 | SUB-10 | Project 2 | Commercial | Delayed | RISK-1091 | 2026-03-01 | 2026-04-14 | Delay in material delivery | Either director student home dark morning. | Mr power with leg. | Defense design ready design agent. | 2026-03-02 | Closed | 2026-05-14 | Kristin Ingram | Design | RIBA 1 | Professional think future film. | 76 | Foot about fly computer hope leader. | 32 | 228 | High | 96 | Critical | 6488550.89 | 2732021.43 | 24 | 10 | Threat | Reputation | Execution | Commercial | Band 1 | Construction | Authority | Procurement | RBS-176.1 | 2026-03-05 | 2026-06-28 | Yes | Project 5 | PLAN-5917 | Peace always office the minute child institution. | RESP-20230 | Matthew Johnson | Mitigation for Risk-1091 | In Progress | Reduce black skin sit. | 2026-03-01 | 2026-04-09 | 38 | 2026-04-09 | No | 2026-03-02 | 810945.77 | 408315.06 | 50.35 | RISK-1049 | Related Risk Title 91 | Closed
Risk | Waterfront | North Nathanielchester | Hospitality | PRJ-187 | SUB-10 | Project 17 | Commercial | On Hold | RISK-1092 | 2026-03-01 | 2026-05-16 | Delay in design approval | In year trial performance. | Trip near American center word. | Listen quality process prepare. | 2026-03-31 | Open |  | Lindsey Houston | Execution | RIBA 2 | Finally ask important education sometimes top. | 56 | Strategy political figure. | 43 | 224 | Critical | 172 | Low | 5020853.74 | 3855298.41 | 98 | 75 | Threat | Quality | Handover | Design | Band 1 | Procurement | Authority | Procurement | RBS-993.3 | 2026-04-14 | 2026-07-08 | Yes | Project 13 | PLAN-1893 | Action those many travel religious. | RESP-75166 | Kristen Austin | Mitigation for Risk-1092 | Not Started | Class since management physical water country spring. | 2026-03-01 | 2026-06-18 | 108 | 2026-06-18 | No | 2026-03-02 | 1747769.4 | 1633952.94 | 93.49 | RISK-1055 | Related Risk Title 92 | Open
Risk | South | Goodburgh | Entertainment | PRJ-178 | SUB-15 | Project 17 | Development | Delayed | RISK-1093 | 2026-03-01 | 2026-05-21 | Delay in design approval | Among case life. | Prevent available tough player theory. | Today instead consumer chair moment owner letter. | 2026-03-21 | Mitigating |  | Theresa Wall | Concept | RIBA 5 | Up bar against modern garden cover likely. | 35 | Tend behind detail experience suddenly out. | 10 | 35 | High | 10 | High | 5666789.9 | 1619082.83 | 110 | 31 | Threat | Quality | Execution | Design | Band 3 | Commercial | Construction | Construction | RBS-342.7 | 2026-04-07 | 2026-08-10 | No | Project 8 | PLAN-6693 | Dinner discover network word total need. | RESP-59156 | Kirsten Maddox | Mitigation for Risk-1093 | Not Started | Congress news side smile leader reveal thank. | 2026-03-01 | 2026-04-12 | 41 | 2026-04-12 | No | 2026-03-02 | 1881319.13 | 2252207.92 | 100 | RISK-1019 | Related Risk Title 93 | Mitigating
Risk | North | Thomasland | Hospitality | PRJ-259 | SUB-13 | Project 19 | Delivery | Completed | RISK-1094 | 2026-03-01 | 2026-06-17 | Delay in design approval | National law next road represent realize know forget. | Campaign minute mission law. | Them hundred usually put want final. | 2026-03-20 | Mitigating |  | Amanda Flores | Handover | RIBA 2 | Cover large very clear method less people. | 33 | Face certain without cost. | 20 | 132 | Low | 80 | Low | 5618477.17 | 3405137.68 | 321 | 194 | Threat | Time | Design | Design | Band 1 | Construction | Design | Construction | RBS-609.6 | 2026-03-22 | 2026-08-02 | Yes | Project 11 | PLAN-1459 | Generation pattern about animal nearly poor. | RESP-40088 | Sara Hammond | Mitigation for Risk-1094 | Not Started | Road beautiful tax. | 2026-03-01 | 2026-04-24 | 53 | 2026-04-24 | Yes | 2026-03-02 | 484095.56 | 363674.55 | 75.12 | RISK-1079 | Related Risk Title 94 | Mitigating
Risk | North | Drakeshire | Entertainment | PRJ-230 | SUB-7 | Project 14 | Commercial | Active | RISK-1095 | 2026-03-01 | 2026-06-10 | Delay in design approval | Country way bit sense fight. | Law production enough. | Pull lawyer responsibility require. | 2026-03-21 | Open |  | Jordan Wood | Design | RIBA 2 | Information nor bad film land identify. | 57 | Prove among unit. | 53 | 285 | Critical | 265 | Low | 6281996.27 | 5841154.43 | 127 | 118 | Minor | Cost | Concept | Procurement | Band 3 | Authority | Design | Authority | RBS-359.3 | 2026-04-29 | 2026-06-26 | Yes | Project 9 | PLAN-8316 | Effort event account wrong who often section. | RESP-21316 | Alexander Branch | Mitigation for Risk-1095 | In Progress | Machine model front. | 2026-03-01 | 2026-04-17 | 46 | 2026-04-17 | No | 2026-03-02 | 1845824.82 | 938862.26 | 50.86 | RISK-1042 | Related Risk Title 95 | Open
Risk | Waterfront | South Vanessa | Infrastructure | PRJ-801 | SUB-14 | Project 8 | Development | Completed | RISK-1096 | 2026-03-01 | 2026-03-13 | Delay in material delivery | Stock drug usually. | Teacher themselves explain. | Trial soldier bring take. | 2026-03-03 | Mitigating |  | Stephen Booker | Design | RIBA 5 | Common beat within population all strong start hold. | 51 | Create avoid find result. | 29 | 204 | Critical | 116 | Moderate | 7467303.23 | 4246113.6 | 72 | 40 | Threat | Quality | Design | Procurement | Band 3 | Procurement | Procurement | Construction | RBS-913.2 | 2026-04-04 | 2026-07-02 | No | Project 20 | PLAN-1125 | Partner production strategy. | RESP-30278 | Mark Tyler | Mitigation for Risk-1096 | Not Started | Region source drop music deal. | 2026-03-01 | 2026-05-12 | 71 | 2026-05-12 | No | 2026-03-02 | 1977353.84 | 1539520.17 | 77.86 | RISK-1011 | Related Risk Title 96 | Mitigating
Risk | Waterfront | Lake Kayleeport | Entertainment | PRJ-568 | SUB-3 | Project 6 | Commercial | Active | RISK-1097 | 2026-03-01 | 2026-05-23 | Delay in design approval | Need enough join safe. | Until attack position deal certain by policy. | Own and create much they rest medical. | 2026-03-11 | Open |  | Tara King | Execution | RIBA 5 | Pressure reality large develop history movie so apply. | 28 | Away several reason during professional as. | 16 | 112 | High | 64 | Moderate | 3169067.63 | 1810895.79 | 140 | 80 | Threat | Cost | Handover | Procurement | Band 1 | Procurement | Commercial | Procurement | RBS-587.4 | 2026-04-23 | 2026-06-17 | Yes | Project 10 | PLAN-6663 | Accept billion us able two value away tend. | RESP-60284 | Timothy Pearson | Mitigation for Risk-1097 | Completed | Go give service candidate major woman people. | 2026-03-01 | 2026-06-28 | 118 | 2026-06-28 | No | 2026-03-02 | 1360047.34 | 1296980.31 | 95.36 | RISK-1055 | Related Risk Title 97 | Open
Risk | Central | Harrishaven | Hospitality | PRJ-276 | SUB-14 | Project 3 | Delivery | Delayed | RISK-1098 | 2026-03-01 | 2026-03-22 | Delay in authority clearance | Seven action central response partner. | Common either word finally allow teacher drug. | Sometimes single exist account race modern. | 2026-03-11 | Mitigating |  | April Carney | Handover | RIBA 1 | Spend town reach thing reveal. | 23 | Here brother prove agent from. | 15 | 46 | Moderate | 30 | Low | 8536510.56 | 5567289.5 | 293 | 191 | Threat | Quality | Handover | Design | Band 2 | Construction | Procurement | Commercial | RBS-588.6 | 2026-04-02 | 2026-09-02 | No | Project 13 | PLAN-3856 | Seek real herself put around guess up current. | RESP-92840 | Jennifer Black | Mitigation for Risk-1098 | Not Started | Safe present shake there radio light gun. | 2026-03-01 | 2026-05-16 | 75 | 2026-05-16 | No | 2026-03-02 | 1390727.02 | 1273195.69 | 91.55 | RISK-1075 | Related Risk Title 98 | Mitigating
Risk | Waterfront | New Brookeborough | Hospitality | PRJ-958 | SUB-6 | Project 6 | Delivery | Active | RISK-1099 | 2026-03-01 | 2026-06-04 | Delay in design approval | Brother available professor perform four sit material catch. | Mind popular suddenly difference international him. | Do wonder cultural. | 2026-03-07 | Mitigating |  | Eric Black | Concept | RIBA 5 | Book window go themselves large. | 30 | Nice improve purpose budget view. | 6 | 120 | Low | 24 | Critical | 2181751.15 | 436350.23 | 224 | 44 | Minor | Cost | Concept | Construction | Band 3 | Design | Commercial | Construction | RBS-594.1 | 2026-03-21 | 2026-05-02 | Yes | Project 8 | PLAN-9101 | Become trade something establish. | RESP-91320 | Ashley Conner | Mitigation for Risk-1099 | Completed | Reflect federal know open. | 2026-03-01 | 2026-06-25 | 115 | 2026-06-25 | No | 2026-03-02 | 1570479.9 | 1659681.48 | 100 | RISK-1072 | Related Risk Title 99 | Mitigating