## Sheet1
Activity ID | Project ID | Programme version | Activity Name | Activity Type | Activity Status | Qiddiya - District ID | Qiddiya - Development ID | Qiddiya - Class L1 ID | Qiddiya - Class L2 ID | Qiddiya - Asset ID | Qiddiya - Stage Gate Level 1 ID | Qiddiya - Stage Gate Level 2 ID | Qiddiya - Phase ID | Qiddiya - Business Class ID | Qiddiya - Precinct ID | Qiddiya - Core Assets ID | Actual Start Date | Actual End Date | Early Start Date | Early End Date | Start | Finish | SG-Summary | QIC-BOD PC | QIC-BOD PC-Date | QIC-BOD-ML-ID | QIC-BOD-ML-DES | QIC-BOD-ML-Date
PRJ-1654-ACT-0001 | PRJ-1654 | Pre-Work | Structural Steel Installation | Task Dependent | Not Started | Sports District | Theme Park Expansion | Vertical Construction | Utilities | AST-64987 | SG1-2 | SG2-4 | PH-384 | Development | South Precinct | Non-Core | 2024-08-15 | 2024-12-09 | 2024-08-08 | 2024-10-20 | 2024-08-16 | 2024-10-27 | Construction readiness confirmed with contractor mobilized. | 61.1 | 2024-08-23 | ML-6574 | Completion of Structural Frame | 2024-11-13
PRJ-1159-ACT-0002 | PRJ-1159 | Actual Construction | Landscape Hardscape Installation | Milestone | Not Started | Retail District | Theme Park Expansion | Landscape | Utilities | AST-57400 | SG1-5 | SG2-2 | PH-171 | Development | South Precinct | Non-Core | 2025-03-25 | 2025-06-27 | 2025-03-13 | 2025-11-01 | 2025-03-16 | 2025-11-03 | Milestone achieved ahead of schedule. | 30.1 | 2025-04-05 | ML-2307 | Authority Inspection Clearance | 2025-12-27
PRJ-1238-ACT-0003 | PRJ-1238 | Pre-Work | Facade Panel Installation | Milestone | Completed | Sports District | Water Park Development | Vertical Construction | Internal Fitout | AST-59735 | SG1-3 | SG2-5 | PH-324 | Central Ops | North Precinct | Core | 2024-08-19 | 2025-04-07 | 2024-07-17 | 2025-03-22 | 2024-07-25 | 2025-04-05 | Milestone achieved ahead of schedule. | 24.9 | 2024-10-26 | ML-1525 | Facade Weather Tight Achieved | 2025-05-26
PRJ-1323-ACT-0004 | PRJ-1323 | Actual Construction | Electrical Cable Routing | Task Dependent | Active | Sports District | Water Park Development | Landscape | Utilities | AST-66155 | SG1-5 | SG2-4 | PH-470 | Strategic Delivery | South Precinct | Non-Core | 2026-04-22 | 2026-11-14 | 2026-03-30 | 2026-10-09 | 2026-04-01 | 2026-10-15 | Design freeze confirmed and procurement initiated. | 89 | 2026-10-03 | ML-2489 | Substantial Completion Achieved | 2026-12-02
PRJ-1048-ACT-0005 | PRJ-1048 | Actual Construction | Commissioning & Testing | Milestone | Not Started | Entertainment District | Stadium Construction | Landscape | Foundations | AST-48469 | SG1-4 | SG2-2 | PH-564 | Development | East Precinct | Core | 2024-09-09 | 2025-05-28 | 2024-07-23 | 2024-12-23 | 2024-08-12 | 2024-12-28 | Stage Gate review completed with minor design comments. | 41.3 | 2025-01-06 | ML-9317 | Substantial Completion Achieved | 2025-02-24
PRJ-1108-ACT-0006 | PRJ-1108 | Actual Construction | Facade Panel Installation | Resource Dependent | Not Started | Entertainment District | Stadium Construction | Landscape | Superstructure | AST-17592 | SG1-2 | SG2-5 | PH-180 | Development | West Precinct | Core | 2025-08-28 | 2026-04-21 | 2025-08-15 | 2026-07-13 | 2025-09-03 | 2026-07-19 | Construction readiness confirmed with contractor mobilized. | 92.3 | 2026-01-28 | ML-9727 | Authority Inspection Clearance | 2026-09-06
PRJ-1128-ACT-0007 | PRJ-1128 | Actual Construction | Electrical Cable Routing | Resource Dependent | Completed | Retail District | Theme Park Expansion | Vertical Construction | Superstructure | AST-18392 | SG1-3 | SG2-1 | PH-667 | Strategic Delivery | South Precinct | Core | 2024-09-20 | 2025-06-08 | 2024-09-02 | 2025-07-14 | 2024-09-19 | 2025-07-19 | Construction readiness confirmed with contractor mobilized. | 72.7 | 2024-12-31 | ML-2163 | MEP Rough-In Completion | 2025-09-02
PRJ-1646-ACT-0008 | PRJ-1646 | Pre-Work | Internal Fitout Works | Milestone | Completed | Retail District | Water Park Development | MEP Works | Internal Fitout | AST-34957 | SG1-1 | SG2-1 | PH-541 | Central Ops | West Precinct | Non-Core | 2024-05-06 | 2024-07-26 | 2024-04-28 | 2024-10-23 | 2024-04-30 | 2024-10-24 | Board approval granted for progression to next phase. | 68.6 | 2024-06-29 | ML-8651 | Facade Weather Tight Achieved | 2024-12-18
PRJ-1746-ACT-0009 | PRJ-1746 | Actual Construction | Electrical Cable Routing | Task Dependent | Active | Retail District | Water Park Development | Infrastructure | Internal Fitout | AST-82132 | SG1-1 | SG2-1 | PH-653 | Development | North Precinct | Core | 2024-04-26 | 2024-08-04 | 2024-04-19 | 2024-07-27 | 2024-04-20 | 2024-08-08 | Board approval granted for progression to next phase. | 55.9 | 2024-05-31 | ML-3724 | MEP Rough-In Completion | 2024-09-03
PRJ-1497-ACT-0010 | PRJ-1497 | Actual Construction | Foundation Excavation Works | Resource Dependent | Completed | Retail District | Water Park Development | Vertical Construction | Facade | AST-38534 | SG1-1 | SG2-5 | PH-655 | Development | East Precinct | Core | 2026-09-07 | 2027-05-04 | 2026-08-31 | 2027-02-27 | 2026-09-12 | 2027-02-28 | Design freeze confirmed and procurement initiated. | 93 | 2027-01-01 | ML-1821 | Facade Weather Tight Achieved | 2027-04-06
PRJ-1488-ACT-0011 | PRJ-1488 | Actual Construction | Facade Panel Installation | Task Dependent | Completed | Sports District | Theme Park Expansion | Infrastructure | Internal Fitout | AST-96163 | SG1-5 | SG2-5 | PH-635 | Central Ops | East Precinct | Core | 2026-11-12 | 2027-02-06 | 2026-10-21 | 2027-09-21 | 2026-10-26 | 2027-09-22 | Stage Gate review completed with minor design comments. | 11.5 | 2027-01-11 | ML-6147 | Authority Inspection Clearance | 2027-10-07
PRJ-1271-ACT-0012 | PRJ-1271 | Pre-Work | Structural Steel Installation | Task Dependent | Completed | Sports District | Stadium Construction | Vertical Construction | Facade | AST-19016 | SG1-2 | SG2-3 | PH-391 | Strategic Delivery | West Precinct | Non-Core | 2026-04-04 | 2026-10-27 | 2026-03-01 | 2026-07-17 | 2026-03-21 | 2026-07-26 | Stage Gate review completed with minor design comments. | 64 | 2026-08-26 | ML-9666 | Substantial Completion Achieved | 2026-07-26
PRJ-1683-ACT-0013 | PRJ-1683 | Actual Construction | Internal Fitout Works | Task Dependent | Completed | Hospitality District | Luxury Resort Build | Landscape | Foundations | AST-22097 | SG1-4 | SG2-3 | PH-145 | Development | East Precinct | Core | 2025-08-28 | 2025-12-05 | 2025-09-01 | 2025-12-19 | 2025-09-05 | 2025-12-27 | Board approval granted for progression to next phase. | 31.8 | 2025-10-20 | ML-5291 | Facade Weather Tight Achieved | 2026-01-06
PRJ-1759-ACT-0014 | PRJ-1759 | Pre-Work | Structural Steel Installation | Resource Dependent | Not Started | Entertainment District | Stadium Construction | Landscape | Foundations | AST-56898 | SG1-2 | SG2-2 | PH-205 | Central Ops | West Precinct | Core | 2026-06-08 | 2026-09-18 | 2026-06-10 | 2027-05-14 | 2026-06-23 | 2027-05-31 | Board approval granted for progression to next phase. | 8.4 | 2026-09-10 | ML-4878 | Authority Inspection Clearance | 2027-07-25
PRJ-1166-ACT-0015 | PRJ-1166 | Actual Construction | Electrical Cable Routing | Task Dependent | Active | Sports District | Water Park Development | MEP Works | Facade | AST-50001 | SG1-2 | SG2-2 | PH-124 | Strategic Delivery | West Precinct | Non-Core | 2025-01-03 | 2025-09-15 | 2024-12-28 | 2025-09-20 | 2024-12-28 | 2025-09-25 | Milestone achieved ahead of schedule. | 79.8 | 2025-01-30 | ML-5564 | MEP Rough-In Completion | 2025-11-19
PRJ-1071-ACT-0016 | PRJ-1071 | Pre-Work | Foundation Excavation Works | Task Dependent | Completed | Retail District | Stadium Construction | Landscape | Internal Fitout | AST-89457 | SG1-5 | SG2-1 | PH-494 | Strategic Delivery | East Precinct | Core | 2025-08-04 | 2026-03-06 | 2025-07-05 | 2026-03-05 | 2025-07-25 | 2026-03-21 | Stage Gate review completed with minor design comments. | 22 | 2025-10-10 | ML-8144 | Facade Weather Tight Achieved | 2026-03-21
PRJ-1532-ACT-0017 | PRJ-1532 | Actual Construction | Commissioning & Testing | Milestone | Active | Hospitality District | Luxury Resort Build | Landscape | Utilities | AST-26683 | SG1-2 | SG2-4 | PH-488 | Strategic Delivery | East Precinct | Non-Core | 2025-03-06 | 2025-10-06 | 2025-01-25 | 2025-10-09 | 2025-02-07 | 2025-10-11 | Milestone achieved ahead of schedule. | 73.4 | 2025-05-21 | ML-9977 | Completion of Structural Frame | 2025-12-03
PRJ-1000-ACT-0018 | PRJ-1000 | Actual Construction | Water Feature Testing | Milestone | Not Started | Entertainment District | Stadium Construction | Landscape | Foundations | AST-40784 | SG1-3 | SG2-2 | PH-303 | Strategic Delivery | North Precinct | Core | 2025-10-06 | 2026-05-03 | 2025-09-08 | 2026-03-26 | 2025-09-14 | 2026-04-08 | Design freeze confirmed and procurement initiated. | 69.2 | 2026-02-13 | ML-5011 | Substantial Completion Achieved | 2026-05-08
PRJ-1625-ACT-0019 | PRJ-1625 | Pre-Work | Ride Equipment Installation | Task Dependent | Active | Sports District | Water Park Development | MEP Works | Foundations | AST-83060 | SG1-2 | SG2-1 | PH-567 | Strategic Delivery | West Precinct | Non-Core | 2024-06-19 | 2024-11-10 | 2024-05-16 | 2025-02-26 | 2024-05-29 | 2025-03-18 | Design freeze confirmed and procurement initiated. | 28.2 | 2024-12-03 | ML-8251 | Substantial Completion Achieved | 2025-04-26
PRJ-1834-ACT-0020 | PRJ-1834 | Actual Construction | Water Feature Testing | Milestone | Not Started | Hospitality District | Luxury Resort Build | Infrastructure | Facade | AST-40735 | SG1-3 | SG2-3 | PH-427 | Development | South Precinct | Core | 2026-10-25 | 2027-08-09 | 2026-10-13 | 2027-07-21 | 2026-10-30 | 2027-08-04 | Milestone achieved ahead of schedule. | 84.8 | 2027-01-03 | ML-4788 | MEP Rough-In Completion | 2027-08-28
PRJ-1710-ACT-0021 | PRJ-1710 | Actual Construction | Internal Fitout Works | Milestone | Completed | Entertainment District | Luxury Resort Build | MEP Works | Foundations | AST-56105 | SG1-3 | SG2-4 | PH-529 | Strategic Delivery | West Precinct | Core | 2024-11-19 | 2025-06-21 | 2024-11-06 | 2025-04-13 | 2024-11-08 | 2025-04-26 | Design freeze confirmed and procurement initiated. | 10.9 | 2025-03-06 | ML-5471 | Substantial Completion Achieved | 2025-05-23
PRJ-1497-ACT-0022 | PRJ-1497 | Pre-Work | Facade Panel Installation | Task Dependent | Completed | Retail District | Water Park Development | MEP Works | Superstructure | AST-16590 | SG1-3 | SG2-4 | PH-435 | Strategic Delivery | West Precinct | Non-Core | 2024-02-24 | 2024-12-04 | 2024-02-19 | 2024-11-02 | 2024-02-29 | 2024-11-14 | Construction readiness confirmed with contractor mobilized. | 7.6 | 2024-06-03 | ML-6529 | Authority Inspection Clearance | 2025-01-01
PRJ-1900-ACT-0023 | PRJ-1900 | Pre-Work | Foundation Excavation Works | Milestone | Not Started | Entertainment District | Theme Park Expansion | Vertical Construction | Superstructure | AST-12671 | SG1-5 | SG2-2 | PH-344 | Strategic Delivery | West Precinct | Core | 2026-02-05 | 2026-11-17 | 2026-02-02 | 2026-08-28 | 2026-02-15 | 2026-09-05 | Construction readiness confirmed with contractor mobilized. | 100 | 2026-05-05 | ML-4571 | Completion of Structural Frame | 2026-10-04
PRJ-1716-ACT-0024 | PRJ-1716 | Actual Construction | Facade Panel Installation | Resource Dependent | Completed | Sports District | Theme Park Expansion | Vertical Construction | Foundations | AST-49529 | SG1-5 | SG2-1 | PH-679 | Development | East Precinct | Non-Core | 2025-07-01 | 2025-10-12 | 2025-06-03 | 2026-01-23 | 2025-06-08 | 2026-02-11 | Milestone achieved ahead of schedule. | 60 | 2025-09-18 | ML-7071 | Completion of Structural Frame | 2026-02-15
PRJ-1518-ACT-0025 | PRJ-1518 | Actual Construction | Landscape Hardscape Installation | Milestone | Completed | Retail District | Luxury Resort Build | MEP Works | Utilities | AST-45179 | SG1-3 | SG2-2 | PH-188 | Central Ops | West Precinct | Core | 2025-11-20 | 2026-08-13 | 2025-11-16 | 2026-01-19 | 2025-11-29 | 2026-02-03 | Design freeze confirmed and procurement initiated. | 46.4 | 2026-04-02 | ML-8613 | MEP Rough-In Completion | 2026-03-11
PRJ-1624-ACT-0026 | PRJ-1624 | Actual Construction | Water Feature Testing | Milestone | Completed | Hospitality District | Theme Park Expansion | Vertical Construction | Foundations | AST-41635 | SG1-4 | SG2-4 | PH-668 | Strategic Delivery | West Precinct | Non-Core | 2026-02-20 | 2026-07-08 | 2026-02-15 | 2026-09-20 | 2026-02-15 | 2026-10-05 | Board approval granted for progression to next phase. | 80.8 | 2026-05-18 | ML-8342 | Facade Weather Tight Achieved | 2026-11-24
PRJ-1017-ACT-0027 | PRJ-1017 | Actual Construction | Mechanical Plant Room Setup | Resource Dependent | Completed | Hospitality District | Stadium Construction | MEP Works | Facade | AST-50189 | SG1-3 | SG2-2 | PH-223 | Strategic Delivery | East Precinct | Core | 2024-08-07 | 2025-01-23 | 2024-07-02 | 2025-01-23 | 2024-07-09 | 2025-02-04 | Construction readiness confirmed with contractor mobilized. | 50 | 2024-12-20 | ML-9779 | Facade Weather Tight Achieved | 2025-04-05
PRJ-1780-ACT-0028 | PRJ-1780 | Actual Construction | Structural Steel Installation | Task Dependent | Completed | Sports District | Stadium Construction | Infrastructure | Foundations | AST-82529 | SG1-3 | SG2-2 | PH-602 | Development | North Precinct | Non-Core | 2025-01-16 | 2025-07-24 | 2025-01-08 | 2025-06-06 | 2025-01-14 | 2025-06-21 | Board approval granted for progression to next phase. | 26.6 | 2025-03-02 | ML-8690 | Facade Weather Tight Achieved | 2025-07-21
PRJ-1451-ACT-0029 | PRJ-1451 | Pre-Work | Structural Steel Installation | Task Dependent | Not Started | Hospitality District | Theme Park Expansion | Vertical Construction | Foundations | AST-83147 | SG1-4 | SG2-5 | PH-331 | Entertainment | West Precinct | Non-Core | 2025-12-13 | 2026-03-26 | 2025-11-27 | 2026-04-23 | 2025-11-28 | 2026-05-01 | Design freeze confirmed and procurement initiated. | 12 | 2026-05-23 | ML-5871 | Substantial Completion Achieved | 2026-06-25
PRJ-1602-ACT-0030 | PRJ-1602 | Pre-Work | Electrical Cable Routing | Task Dependent | Completed | Entertainment District | Water Park Development | Infrastructure | Internal Fitout | AST-69048 | SG1-5 | SG2-4 | PH-398 | Development | South Precinct | Non-Core | 2026-05-16 | 2026-08-19 | 2026-05-10 | 2026-12-11 | 2026-05-28 | 2026-12-30 | Board approval granted for progression to next phase. | 67.7 | 2026-06-25 | ML-5632 | Facade Weather Tight Achieved | 2027-02-12
PRJ-1880-ACT-0031 | PRJ-1880 | Actual Construction | Ride Equipment Installation | Task Dependent | Not Started | Entertainment District | Water Park Development | Landscape | Utilities | AST-84607 | SG1-3 | SG2-4 | PH-227 | Entertainment | East Precinct | Non-Core | 2026-08-12 | 2027-01-05 | 2026-07-11 | 2026-10-14 | 2026-07-18 | 2026-10-22 | Stage Gate review completed with minor design comments. | 26.4 | 2026-09-19 | ML-5460 | Authority Inspection Clearance | 2026-11-23
PRJ-1552-ACT-0032 | PRJ-1552 | Pre-Work | Landscape Hardscape Installation | Milestone | Active | Entertainment District | Water Park Development | MEP Works | Utilities | AST-95394 | SG1-4 | SG2-3 | PH-285 | Entertainment | West Precinct | Core | 2026-09-25 | 2027-06-18 | 2026-10-06 | 2027-06-30 | 2026-10-08 | 2027-07-19 | Construction readiness confirmed with contractor mobilized. | 7.5 | 2026-11-22 | ML-8700 | Facade Weather Tight Achieved | 2027-08-10
PRJ-1418-ACT-0033 | PRJ-1418 | Pre-Work | Water Feature Testing | Resource Dependent | Not Started | Hospitality District | Stadium Construction | Landscape | Foundations | AST-62976 | SG1-5 | SG2-1 | PH-655 | Entertainment | West Precinct | Core | 2025-11-19 | 2026-08-01 | 2025-11-10 | 2026-06-20 | 2025-11-13 | 2026-06-25 | Milestone achieved ahead of schedule. | 82.3 | 2026-04-08 | ML-4073 | Substantial Completion Achieved | 2026-07-28
PRJ-1370-ACT-0034 | PRJ-1370 | Pre-Work | Mechanical Plant Room Setup | Milestone | Not Started | Hospitality District | Theme Park Expansion | MEP Works | Foundations | AST-39451 | SG1-1 | SG2-4 | PH-220 | Strategic Delivery | West Precinct | Non-Core | 2026-10-19 | 2027-02-08 | 2026-10-16 | 2027-07-24 | 2026-10-17 | 2027-07-30 | Design freeze confirmed and procurement initiated. | 16.5 | 2027-03-29 | ML-9337 | Substantial Completion Achieved | 2027-09-13
PRJ-1279-ACT-0035 | PRJ-1279 | Pre-Work | Ride Equipment Installation | Resource Dependent | Active | Hospitality District | Stadium Construction | Infrastructure | Facade | AST-49132 | SG1-5 | SG2-5 | PH-601 | Strategic Delivery | West Precinct | Non-Core | 2026-05-14 | 2026-09-10 | 2026-04-15 | 2027-02-24 | 2026-04-30 | 2027-03-03 | Board approval granted for progression to next phase. | 53.3 | 2026-06-17 | ML-6654 | Authority Inspection Clearance | 2027-03-24
PRJ-1565-ACT-0036 | PRJ-1565 | Pre-Work | Commissioning & Testing | Resource Dependent | Completed | Retail District | Luxury Resort Build | MEP Works | Superstructure | AST-74923 | SG1-1 | SG2-2 | PH-614 | Central Ops | North Precinct | Non-Core | 2026-03-12 | 2026-08-26 | 2026-02-01 | 2026-11-25 | 2026-02-11 | 2026-12-01 | Design freeze confirmed and procurement initiated. | 86.3 | 2026-06-25 | ML-2633 | MEP Rough-In Completion | 2027-01-03
PRJ-1932-ACT-0037 | PRJ-1932 | Actual Construction | Structural Steel Installation | Milestone | Not Started | Hospitality District | Luxury Resort Build | Landscape | Internal Fitout | AST-80912 | SG1-1 | SG2-5 | PH-170 | Strategic Delivery | East Precinct | Core | 2026-08-19 | 2026-12-21 | 2026-07-20 | 2026-09-16 | 2026-07-24 | 2026-09-29 | Design freeze confirmed and procurement initiated. | 37.2 | 2027-02-12 | ML-2480 | Facade Weather Tight Achieved | 2026-10-26
PRJ-1100-ACT-0038 | PRJ-1100 | Pre-Work | Landscape Hardscape Installation | Task Dependent | Completed | Retail District | Water Park Development | Vertical Construction | Superstructure | AST-20350 | SG1-5 | SG2-4 | PH-346 | Entertainment | South Precinct | Core | 2024-07-10 | 2024-09-16 | 2024-07-19 | 2025-04-28 | 2024-07-24 | 2025-05-07 | Stage Gate review completed with minor design comments. | 39.1 | 2024-10-28 | ML-8555 | Facade Weather Tight Achieved | 2025-06-16
PRJ-1260-ACT-0039 | PRJ-1260 | Actual Construction | Structural Steel Installation | Milestone | Active | Retail District | Stadium Construction | Vertical Construction | Internal Fitout | AST-73335 | SG1-1 | SG2-2 | PH-490 | Central Ops | East Precinct | Non-Core | 2026-08-02 | 2026-12-05 | 2026-07-30 | 2027-01-22 | 2026-07-30 | 2027-02-05 | Design freeze confirmed and procurement initiated. | 98.8 | 2026-10-17 | ML-1359 | Facade Weather Tight Achieved | 2027-03-30
PRJ-1674-ACT-0040 | PRJ-1674 | Actual Construction | Commissioning & Testing | Task Dependent | Completed | Sports District | Stadium Construction | Vertical Construction | Foundations | AST-92242 | SG1-1 | SG2-3 | PH-551 | Development | East Precinct | Core | 2026-04-18 | 2026-06-27 | 2026-03-21 | 2026-09-19 | 2026-03-21 | 2026-10-07 | Design freeze confirmed and procurement initiated. | 78.7 | 2026-06-15 | ML-2476 | Facade Weather Tight Achieved | 2026-12-04
PRJ-1302-ACT-0041 | PRJ-1302 | Actual Construction | Internal Fitout Works | Resource Dependent | Completed | Hospitality District | Theme Park Expansion | MEP Works | Foundations | AST-28449 | SG1-2 | SG2-4 | PH-670 | Central Ops | North Precinct | Non-Core | 2025-10-24 | 2026-06-13 | 2025-10-26 | 2026-07-24 | 2025-10-31 | 2026-07-30 | Construction readiness confirmed with contractor mobilized. | 83.9 | 2025-12-28 | ML-1228 | Facade Weather Tight Achieved | 2026-08-15
PRJ-1549-ACT-0042 | PRJ-1549 | Actual Construction | Landscape Hardscape Installation | Milestone | Not Started | Entertainment District | Luxury Resort Build | Landscape | Internal Fitout | AST-25292 | SG1-2 | SG2-1 | PH-138 | Central Ops | West Precinct | Core | 2024-10-02 | 2025-05-30 | 2024-08-30 | 2025-06-21 | 2024-09-10 | 2025-06-29 | Stage Gate review completed with minor design comments. | 49.8 | 2025-03-09 | ML-2592 | MEP Rough-In Completion | 2025-07-14
PRJ-1908-ACT-0043 | PRJ-1908 | Actual Construction | Commissioning & Testing | Resource Dependent | Not Started | Hospitality District | Water Park Development | MEP Works | Internal Fitout | AST-40947 | SG1-3 | SG2-1 | PH-476 | Central Ops | North Precinct | Non-Core | 2024-10-31 | 2025-07-17 | 2024-09-20 | 2025-06-08 | 2024-10-04 | 2025-06-19 | Board approval granted for progression to next phase. | 67.2 | 2025-03-05 | ML-5520 | Substantial Completion Achieved | 2025-07-01
PRJ-1991-ACT-0044 | PRJ-1991 | Pre-Work | Foundation Excavation Works | Task Dependent | Completed | Sports District | Water Park Development | Vertical Construction | Facade | AST-29340 | SG1-5 | SG2-1 | PH-383 | Strategic Delivery | South Precinct | Non-Core | 2024-10-03 | 2024-11-27 | 2024-09-05 | 2025-06-20 | 2024-09-07 | 2025-06-26 | Milestone achieved ahead of schedule. | 98.9 | 2025-02-24 | ML-3858 | MEP Rough-In Completion | 2025-07-03
PRJ-1676-ACT-0045 | PRJ-1676 | Pre-Work | Foundation Excavation Works | Milestone | Not Started | Retail District | Luxury Resort Build | Landscape | Utilities | AST-87812 | SG1-1 | SG2-4 | PH-615 | Strategic Delivery | North Precinct | Non-Core | 2024-02-22 | 2024-09-19 | 2024-02-22 | 2024-06-17 | 2024-02-22 | 2024-06-28 | Board approval granted for progression to next phase. | 10 | 2024-06-08 | ML-8504 | Facade Weather Tight Achieved | 2024-08-08
PRJ-1987-ACT-0046 | PRJ-1987 | Pre-Work | Water Feature Testing | Task Dependent | Not Started | Hospitality District | Stadium Construction | MEP Works | Utilities | AST-79541 | SG1-3 | SG2-4 | PH-617 | Entertainment | North Precinct | Core | 2024-03-16 | 2024-06-24 | 2024-02-18 | 2024-05-22 | 2024-03-04 | 2024-06-03 | Design freeze confirmed and procurement initiated. | 90.4 | 2024-06-06 | ML-4522 | Completion of Structural Frame | 2024-06-30
PRJ-1462-ACT-0047 | PRJ-1462 | Actual Construction | Structural Steel Installation | Task Dependent | Completed | Retail District | Theme Park Expansion | Infrastructure | Foundations | AST-22219 | SG1-4 | SG2-1 | PH-481 | Strategic Delivery | North Precinct | Non-Core | 2025-04-22 | 2026-01-04 | 2025-04-02 | 2025-12-25 | 2025-04-12 | 2026-01-08 | Milestone achieved ahead of schedule. | 34.7 | 2025-06-26 | ML-3002 | Substantial Completion Achieved | 2026-02-03
PRJ-1362-ACT-0048 | PRJ-1362 | Actual Construction | Structural Steel Installation | Task Dependent | Not Started | Hospitality District | Stadium Construction | Infrastructure | Facade | AST-85248 | SG1-2 | SG2-4 | PH-674 | Development | East Precinct | Core | 2026-05-20 | 2026-12-31 | 2026-05-07 | 2026-07-22 | 2026-05-16 | 2026-08-10 | Construction readiness confirmed with contractor mobilized. | 25.2 | 2026-11-04 | ML-3955 | Authority Inspection Clearance | 2026-08-27
PRJ-1719-ACT-0049 | PRJ-1719 | Pre-Work | Commissioning & Testing | Task Dependent | Completed | Sports District | Luxury Resort Build | MEP Works | Internal Fitout | AST-54681 | SG1-2 | SG2-3 | PH-419 | Central Ops | North Precinct | Core | 2025-09-20 | 2026-01-16 | 2025-09-13 | 2026-05-15 | 2025-09-24 | 2026-05-15 | Design freeze confirmed and procurement initiated. | 18.5 | 2026-03-01 | ML-3549 | Completion of Structural Frame | 2026-05-25
PRJ-1772-ACT-0050 | PRJ-1772 | Pre-Work | Water Feature Testing | Resource Dependent | Active | Entertainment District | Stadium Construction | MEP Works | Utilities | AST-97442 | SG1-3 | SG2-1 | PH-325 | Entertainment | North Precinct | Core | 2024-05-08 | 2025-01-25 | 2024-04-03 | 2024-07-07 | 2024-04-11 | 2024-07-21 | Construction readiness confirmed with contractor mobilized. | 44.3 | 2024-07-02 | ML-4349 | Substantial Completion Achieved | 2024-08-09
PRJ-1968-ACT-0051 | PRJ-1968 | Pre-Work | Foundation Excavation Works | Milestone | Completed | Hospitality District | Theme Park Expansion | MEP Works | Foundations | AST-67176 | SG1-1 | SG2-4 | PH-179 | Central Ops | West Precinct | Non-Core | 2025-03-13 | 2025-06-27 | 2025-02-28 | 2025-07-07 | 2025-03-08 | 2025-07-16 | Design freeze confirmed and procurement initiated. | 21.7 | 2025-06-18 | ML-7843 | Substantial Completion Achieved | 2025-08-03
PRJ-1117-ACT-0052 | PRJ-1117 | Actual Construction | Landscape Hardscape Installation | Milestone | Active | Entertainment District | Luxury Resort Build | Landscape | Facade | AST-39041 | SG1-3 | SG2-2 | PH-178 | Development | South Precinct | Non-Core | 2026-05-03 | 2027-02-07 | 2026-03-30 | 2026-06-13 | 2026-04-09 | 2026-06-18 | Stage Gate review completed with minor design comments. | 85.2 | 2026-07-04 | ML-6752 | Substantial Completion Achieved | 2026-08-03
PRJ-1981-ACT-0053 | PRJ-1981 | Pre-Work | Facade Panel Installation | Task Dependent | Completed | Retail District | Luxury Resort Build | MEP Works | Utilities | AST-94278 | SG1-5 | SG2-3 | PH-423 | Strategic Delivery | West Precinct | Core | 2024-10-30 | 2025-03-25 | 2024-10-26 | 2025-04-23 | 2024-10-29 | 2025-04-27 | Construction readiness confirmed with contractor mobilized. | 77.2 | 2025-04-15 | ML-8682 | MEP Rough-In Completion | 2025-05-25
PRJ-1646-ACT-0054 | PRJ-1646 | Actual Construction | Mechanical Plant Room Setup | Task Dependent | Completed | Entertainment District | Luxury Resort Build | MEP Works | Utilities | AST-82655 | SG1-1 | SG2-4 | PH-685 | Strategic Delivery | East Precinct | Non-Core | 2025-09-19 | 2025-12-10 | 2025-08-25 | 2026-03-30 | 2025-09-12 | 2026-03-31 | Design freeze confirmed and procurement initiated. | 8.6 | 2025-12-22 | ML-9214 | Substantial Completion Achieved | 2026-04-09
PRJ-1980-ACT-0055 | PRJ-1980 | Actual Construction | Internal Fitout Works | Milestone | Completed | Sports District | Stadium Construction | Landscape | Facade | AST-60779 | SG1-4 | SG2-3 | PH-153 | Central Ops | North Precinct | Non-Core | 2024-06-05 | 2024-09-01 | 2024-05-03 | 2025-02-10 | 2024-05-06 | 2025-02-20 | Board approval granted for progression to next phase. | 28.5 | 2024-09-25 | ML-2548 | Completion of Structural Frame | 2025-03-27
PRJ-1694-ACT-0056 | PRJ-1694 | Actual Construction | Structural Steel Installation | Task Dependent | Completed | Entertainment District | Stadium Construction | MEP Works | Facade | AST-26750 | SG1-5 | SG2-1 | PH-533 | Central Ops | North Precinct | Non-Core | 2026-02-24 | 2026-09-27 | 2026-02-22 | 2026-09-04 | 2026-03-02 | 2026-09-23 | Construction readiness confirmed with contractor mobilized. | 92.1 | 2026-05-14 | ML-6060 | MEP Rough-In Completion | 2026-10-04
PRJ-1973-ACT-0057 | PRJ-1973 | Pre-Work | Facade Panel Installation | Milestone | Active | Sports District | Luxury Resort Build | Vertical Construction | Superstructure | AST-33703 | SG1-5 | SG2-2 | PH-548 | Development | West Precinct | Non-Core | 2025-03-13 | 2025-07-06 | 2025-02-27 | 2025-10-28 | 2025-03-14 | 2025-11-03 | Stage Gate review completed with minor design comments. | 85.2 | 2025-04-07 | ML-4891 | Facade Weather Tight Achieved | 2025-12-01
PRJ-1625-ACT-0058 | PRJ-1625 | Actual Construction | Water Feature Testing | Resource Dependent | Active | Retail District | Luxury Resort Build | Vertical Construction | Superstructure | AST-89254 | SG1-2 | SG2-3 | PH-153 | Entertainment | East Precinct | Core | 2025-08-06 | 2026-02-25 | 2025-07-30 | 2026-05-05 | 2025-08-06 | 2026-05-22 | Board approval granted for progression to next phase. | 69.4 | 2025-12-30 | ML-9452 | Facade Weather Tight Achieved | 2026-07-15
PRJ-1127-ACT-0059 | PRJ-1127 | Pre-Work | Ride Equipment Installation | Resource Dependent | Not Started | Retail District | Stadium Construction | Vertical Construction | Internal Fitout | AST-20696 | SG1-3 | SG2-2 | PH-128 | Central Ops | North Precinct | Non-Core | 2025-08-19 | 2025-12-17 | 2025-08-01 | 2025-11-08 | 2025-08-06 | 2025-11-16 | Stage Gate review completed with minor design comments. | 82.6 | 2025-11-16 | ML-3392 | MEP Rough-In Completion | 2025-11-24
PRJ-1039-ACT-0060 | PRJ-1039 | Actual Construction | Structural Steel Installation | Task Dependent | Active | Sports District | Stadium Construction | Infrastructure | Foundations | AST-41252 | SG1-4 | SG2-5 | PH-568 | Development | North Precinct | Non-Core | 2025-08-23 | 2025-10-09 | 2025-08-06 | 2026-05-23 | 2025-08-10 | 2026-06-07 | Stage Gate review completed with minor design comments. | 25.5 | 2025-09-30 | ML-9782 | Facade Weather Tight Achieved | 2026-06-08
PRJ-1647-ACT-0061 | PRJ-1647 | Pre-Work | Foundation Excavation Works | Milestone | Completed | Entertainment District | Stadium Construction | Infrastructure | Utilities | AST-81313 | SG1-5 | SG2-5 | PH-667 | Development | West Precinct | Non-Core | 2026-11-24 | 2027-08-15 | 2026-11-14 | 2027-11-06 | 2026-11-21 | 2027-11-10 | Construction readiness confirmed with contractor mobilized. | 27.9 | 2027-03-10 | ML-1713 | Facade Weather Tight Achieved | 2027-12-20
PRJ-1396-ACT-0062 | PRJ-1396 | Pre-Work | Electrical Cable Routing | Task Dependent | Active | Hospitality District | Water Park Development | MEP Works | Internal Fitout | AST-92802 | SG1-2 | SG2-2 | PH-164 | Entertainment | North Precinct | Non-Core | 2026-01-23 | 2026-09-01 | 2026-02-03 | 2026-07-31 | 2026-02-03 | 2026-08-11 | Stage Gate review completed with minor design comments. | 74.8 | 2026-04-18 | ML-4302 | Authority Inspection Clearance | 2026-08-13
PRJ-1810-ACT-0063 | PRJ-1810 | Pre-Work | Internal Fitout Works | Resource Dependent | Active | Entertainment District | Stadium Construction | Landscape | Foundations | AST-58237 | SG1-4 | SG2-4 | PH-550 | Entertainment | East Precinct | Core | 2025-03-01 | 2025-11-04 | 2025-02-02 | 2025-04-25 | 2025-02-12 | 2025-05-04 | Design freeze confirmed and procurement initiated. | 8.5 | 2025-08-13 | ML-9129 | Facade Weather Tight Achieved | 2025-06-17
PRJ-1509-ACT-0064 | PRJ-1509 | Pre-Work | Ride Equipment Installation | Task Dependent | Active | Hospitality District | Stadium Construction | MEP Works | Utilities | AST-65851 | SG1-2 | SG2-4 | PH-459 | Entertainment | North Precinct | Non-Core | 2026-02-03 | 2026-04-29 | 2026-01-14 | 2026-12-11 | 2026-01-22 | 2026-12-13 | Construction readiness confirmed with contractor mobilized. | 56.8 | 2026-04-26 | ML-8126 | MEP Rough-In Completion | 2026-12-30
PRJ-1654-ACT-0065 | PRJ-1654 | Pre-Work | Foundation Excavation Works | Task Dependent | Not Started | Sports District | Stadium Construction | Landscape | Internal Fitout | AST-84349 | SG1-1 | SG2-5 | PH-257 | Entertainment | East Precinct | Non-Core | 2024-05-05 | 2024-09-08 | 2024-04-07 | 2024-07-22 | 2024-04-27 | 2024-08-03 | Board approval granted for progression to next phase. | 69.4 | 2024-08-25 | ML-8273 | Authority Inspection Clearance | 2024-09-20
PRJ-1078-ACT-0066 | PRJ-1078 | Actual Construction | Electrical Cable Routing | Milestone | Not Started | Hospitality District | Stadium Construction | MEP Works | Superstructure | AST-90199 | SG1-3 | SG2-4 | PH-304 | Development | South Precinct | Core | 2024-10-13 | 2025-04-18 | 2024-09-27 | 2025-08-23 | 2024-10-08 | 2025-09-04 | Stage Gate review completed with minor design comments. | 74.9 | 2025-02-17 | ML-8406 | Completion of Structural Frame | 2025-09-15
PRJ-1920-ACT-0067 | PRJ-1920 | Pre-Work | Internal Fitout Works | Resource Dependent | Completed | Sports District | Theme Park Expansion | Vertical Construction | Superstructure | AST-41029 | SG1-4 | SG2-1 | PH-469 | Central Ops | West Precinct | Core | 2026-07-30 | 2026-10-16 | 2026-06-20 | 2026-10-01 | 2026-06-30 | 2026-10-12 | Construction readiness confirmed with contractor mobilized. | 89.7 | 2026-09-08 | ML-2412 | Facade Weather Tight Achieved | 2026-10-16
PRJ-1316-ACT-0068 | PRJ-1316 | Actual Construction | Facade Panel Installation | Task Dependent | Completed | Sports District | Water Park Development | MEP Works | Utilities | AST-17263 | SG1-1 | SG2-5 | PH-256 | Central Ops | South Precinct | Core | 2026-04-06 | 2026-06-27 | 2026-03-10 | 2027-01-12 | 2026-03-26 | 2027-01-25 | Milestone achieved ahead of schedule. | 47.7 | 2026-09-27 | ML-6286 | Completion of Structural Frame | 2027-03-25
PRJ-1726-ACT-0069 | PRJ-1726 | Pre-Work | Electrical Cable Routing | Milestone | Completed | Sports District | Water Park Development | Vertical Construction | Utilities | AST-89316 | SG1-3 | SG2-5 | PH-142 | Development | North Precinct | Core | 2025-03-27 | 2025-09-16 | 2025-03-21 | 2025-11-20 | 2025-04-06 | 2025-11-29 | Construction readiness confirmed with contractor mobilized. | 16.9 | 2025-06-12 | ML-5336 | Facade Weather Tight Achieved | 2026-01-09
PRJ-1215-ACT-0070 | PRJ-1215 | Actual Construction | Mechanical Plant Room Setup | Resource Dependent | Active | Entertainment District | Theme Park Expansion | Vertical Construction | Internal Fitout | AST-64476 | SG1-4 | SG2-4 | PH-308 | Central Ops | South Precinct | Non-Core | 2026-05-22 | 2026-12-01 | 2026-04-18 | 2026-06-27 | 2026-05-03 | 2026-07-17 | Design freeze confirmed and procurement initiated. | 81.4 | 2026-11-13 | ML-6231 | MEP Rough-In Completion | 2026-09-01
PRJ-1881-ACT-0071 | PRJ-1881 | Pre-Work | Landscape Hardscape Installation | Task Dependent | Not Started | Entertainment District | Stadium Construction | MEP Works | Utilities | AST-64805 | SG1-2 | SG2-2 | PH-435 | Central Ops | South Precinct | Core | 2025-12-25 | 2026-04-03 | 2025-12-04 | 2026-08-18 | 2025-12-08 | 2026-08-29 | Board approval granted for progression to next phase. | 16.6 | 2026-04-19 | ML-9163 | Substantial Completion Achieved | 2026-09-30
PRJ-1478-ACT-0072 | PRJ-1478 | Pre-Work | Internal Fitout Works | Task Dependent | Active | Retail District | Luxury Resort Build | Landscape | Utilities | AST-11071 | SG1-1 | SG2-4 | PH-237 | Central Ops | East Precinct | Non-Core | 2026-10-08 | 2027-06-11 | 2026-10-03 | 2027-05-23 | 2026-10-18 | 2027-05-23 | Design freeze confirmed and procurement initiated. | 25.4 | 2027-01-06 | ML-6995 | MEP Rough-In Completion | 2027-05-25
PRJ-1410-ACT-0073 | PRJ-1410 | Actual Construction | Structural Steel Installation | Milestone | Completed | Entertainment District | Water Park Development | Infrastructure | Internal Fitout | AST-58915 | SG1-3 | SG2-5 | PH-474 | Strategic Delivery | South Precinct | Non-Core | 2024-04-22 | 2024-10-31 | 2024-03-28 | 2025-03-25 | 2024-04-14 | 2025-03-31 | Design freeze confirmed and procurement initiated. | 47.8 | 2024-09-09 | ML-9193 | Authority Inspection Clearance | 2025-04-02
PRJ-1046-ACT-0074 | PRJ-1046 | Actual Construction | Facade Panel Installation | Task Dependent | Active | Hospitality District | Stadium Construction | MEP Works | Utilities | AST-49294 | SG1-4 | SG2-1 | PH-477 | Central Ops | North Precinct | Non-Core | 2024-04-07 | 2025-01-10 | 2024-03-10 | 2024-07-13 | 2024-03-20 | 2024-07-28 | Construction readiness confirmed with contractor mobilized. | 18.3 | 2024-09-10 | ML-6040 | Authority Inspection Clearance | 2024-09-16
PRJ-1920-ACT-0075 | PRJ-1920 | Actual Construction | Foundation Excavation Works | Task Dependent | Completed | Sports District | Theme Park Expansion | Infrastructure | Superstructure | AST-12482 | SG1-4 | SG2-3 | PH-528 | Strategic Delivery | West Precinct | Core | 2024-03-21 | 2024-08-29 | 2024-02-09 | 2025-02-15 | 2024-02-24 | 2025-02-23 | Construction readiness confirmed with contractor mobilized. | 21.2 | 2024-08-29 | ML-7723 | Substantial Completion Achieved | 2025-03-27
PRJ-1793-ACT-0076 | PRJ-1793 | Actual Construction | Water Feature Testing | Milestone | Active | Hospitality District | Stadium Construction | MEP Works | Superstructure | AST-42311 | SG1-3 | SG2-5 | PH-405 | Strategic Delivery | East Precinct | Non-Core | 2026-08-21 | 2027-03-20 | 2026-08-19 | 2026-11-06 | 2026-08-23 | 2026-11-22 | Construction readiness confirmed with contractor mobilized. | 34.8 | 2026-10-04 | ML-4396 | Substantial Completion Achieved | 2027-01-05
PRJ-1721-ACT-0077 | PRJ-1721 | Actual Construction | Mechanical Plant Room Setup | Resource Dependent | Not Started | Hospitality District | Theme Park Expansion | Landscape | Foundations | AST-55398 | SG1-4 | SG2-3 | PH-590 | Strategic Delivery | South Precinct | Non-Core | 2026-10-18 | 2027-04-21 | 2026-09-13 | 2027-04-27 | 2026-09-28 | 2027-05-08 | Stage Gate review completed with minor design comments. | 69.3 | 2027-01-23 | ML-5450 | Authority Inspection Clearance | 2027-05-16
PRJ-1111-ACT-0078 | PRJ-1111 | Pre-Work | Foundation Excavation Works | Milestone | Not Started | Entertainment District | Water Park Development | MEP Works | Internal Fitout | AST-72580 | SG1-2 | SG2-3 | PH-428 | Central Ops | North Precinct | Core | 2025-05-04 | 2025-10-15 | 2025-05-04 | 2025-10-20 | 2025-05-05 | 2025-11-05 | Stage Gate review completed with minor design comments. | 36.4 | 2025-09-01 | ML-4804 | Substantial Completion Achieved | 2025-12-09
PRJ-1756-ACT-0079 | PRJ-1756 | Actual Construction | Water Feature Testing | Milestone | Completed | Entertainment District | Stadium Construction | Landscape | Internal Fitout | AST-94058 | SG1-5 | SG2-5 | PH-605 | Strategic Delivery | West Precinct | Non-Core | 2024-03-04 | 2024-11-07 | 2024-03-04 | 2024-08-08 | 2024-03-17 | 2024-08-13 | Board approval granted for progression to next phase. | 88.3 | 2024-03-06 | ML-4159 | Facade Weather Tight Achieved | 2024-10-03
PRJ-1115-ACT-0080 | PRJ-1115 | Pre-Work | Foundation Excavation Works | Milestone | Completed | Retail District | Luxury Resort Build | Landscape | Foundations | AST-62538 | SG1-1 | SG2-2 | PH-243 | Entertainment | East Precinct | Core | 2025-11-09 | 2026-03-29 | 2025-10-25 | 2026-03-11 | 2025-11-08 | 2026-03-31 | Milestone achieved ahead of schedule. | 58.9 | 2025-12-28 | ML-1111 | Facade Weather Tight Achieved | 2026-04-16
PRJ-1392-ACT-0081 | PRJ-1392 | Actual Construction | Mechanical Plant Room Setup | Resource Dependent | Not Started | Retail District | Stadium Construction | Infrastructure | Facade | AST-58174 | SG1-5 | SG2-2 | PH-324 | Strategic Delivery | West Precinct | Core | 2025-05-01 | 2025-06-20 | 2025-04-19 | 2026-01-30 | 2025-04-27 | 2026-02-09 | Milestone achieved ahead of schedule. | 10.9 | 2025-05-31 | ML-8454 | MEP Rough-In Completion | 2026-03-28
PRJ-1620-ACT-0082 | PRJ-1620 | Actual Construction | Electrical Cable Routing | Task Dependent | Completed | Entertainment District | Theme Park Expansion | Vertical Construction | Utilities | AST-80341 | SG1-2 | SG2-2 | PH-435 | Entertainment | North Precinct | Core | 2026-02-23 | 2026-07-29 | 2026-01-18 | 2026-10-19 | 2026-02-04 | 2026-11-03 | Construction readiness confirmed with contractor mobilized. | 54.9 | 2026-07-08 | ML-9008 | Completion of Structural Frame | 2026-11-08
PRJ-1920-ACT-0083 | PRJ-1920 | Actual Construction | Water Feature Testing | Milestone | Not Started | Retail District | Stadium Construction | Infrastructure | Superstructure | AST-85800 | SG1-1 | SG2-1 | PH-533 | Central Ops | North Precinct | Core | 2026-11-04 | 2027-07-19 | 2026-11-10 | 2027-08-12 | 2026-11-11 | 2027-08-26 | Construction readiness confirmed with contractor mobilized. | 58.1 | 2027-04-25 | ML-2130 | Completion of Structural Frame | 2027-10-24
PRJ-1483-ACT-0084 | PRJ-1483 | Actual Construction | Landscape Hardscape Installation | Task Dependent | Completed | Sports District | Stadium Construction | Infrastructure | Superstructure | AST-80419 | SG1-4 | SG2-5 | PH-230 | Strategic Delivery | North Precinct | Core | 2024-02-27 | 2024-11-13 | 2024-02-21 | 2024-09-22 | 2024-03-05 | 2024-09-27 | Design freeze confirmed and procurement initiated. | 87.6 | 2024-06-02 | ML-5888 | Substantial Completion Achieved | 2024-10-26
PRJ-1689-ACT-0085 | PRJ-1689 | Pre-Work | Landscape Hardscape Installation | Milestone | Active | Entertainment District | Water Park Development | Vertical Construction | Foundations | AST-23224 | SG1-5 | SG2-1 | PH-557 | Development | South Precinct | Core | 2026-05-18 | 2027-02-22 | 2026-05-06 | 2027-04-08 | 2026-05-18 | 2027-04-15 | Board approval granted for progression to next phase. | 22.9 | 2026-06-15 | ML-7590 | Facade Weather Tight Achieved | 2027-05-13
PRJ-1239-ACT-0086 | PRJ-1239 | Actual Construction | Commissioning & Testing | Task Dependent | Active | Sports District | Water Park Development | MEP Works | Facade | AST-46064 | SG1-1 | SG2-5 | PH-279 | Entertainment | West Precinct | Core | 2025-03-23 | 2025-09-03 | 2025-03-16 | 2025-05-31 | 2025-03-20 | 2025-06-16 | Milestone achieved ahead of schedule. | 61.8 | 2025-09-11 | ML-6642 | Authority Inspection Clearance | 2025-08-15
PRJ-1658-ACT-0087 | PRJ-1658 | Pre-Work | Mechanical Plant Room Setup | Task Dependent | Active | Sports District | Luxury Resort Build | Infrastructure | Utilities | AST-64090 | SG1-4 | SG2-5 | PH-642 | Strategic Delivery | West Precinct | Core | 2026-03-02 | 2026-07-01 | 2026-02-09 | 2026-12-31 | 2026-02-19 | 2027-01-13 | Design freeze confirmed and procurement initiated. | 76.7 | 2026-07-01 | ML-5177 | MEP Rough-In Completion | 2027-01-26
PRJ-1338-ACT-0088 | PRJ-1338 | Pre-Work | Foundation Excavation Works | Task Dependent | Not Started | Sports District | Luxury Resort Build | Vertical Construction | Facade | AST-49739 | SG1-1 | SG2-2 | PH-294 | Development | West Precinct | Core | 2024-06-29 | 2024-11-18 | 2024-05-30 | 2025-03-25 | 2024-06-10 | 2025-03-27 | Milestone achieved ahead of schedule. | 69 | 2024-11-30 | ML-4350 | Substantial Completion Achieved | 2025-04-21
PRJ-1937-ACT-0089 | PRJ-1937 | Actual Construction | Internal Fitout Works | Resource Dependent | Not Started | Retail District | Stadium Construction | Vertical Construction | Facade | AST-51015 | SG1-4 | SG2-1 | PH-676 | Strategic Delivery | South Precinct | Core | 2025-05-14 | 2026-02-21 | 2025-04-25 | 2026-04-03 | 2025-05-05 | 2026-04-12 | Milestone achieved ahead of schedule. | 29.8 | 2025-09-22 | ML-5272 | Facade Weather Tight Achieved | 2026-05-17
PRJ-1957-ACT-0090 | PRJ-1957 | Actual Construction | Ride Equipment Installation | Resource Dependent | Active | Retail District | Luxury Resort Build | Vertical Construction | Facade | AST-32185 | SG1-2 | SG2-5 | PH-600 | Strategic Delivery | North Precinct | Core | 2026-05-11 | 2026-10-20 | 2026-05-01 | 2026-11-26 | 2026-05-05 | 2026-12-02 | Construction readiness confirmed with contractor mobilized. | 52.4 | 2026-10-25 | ML-2217 | MEP Rough-In Completion | 2027-01-31
PRJ-1837-ACT-0091 | PRJ-1837 | Actual Construction | Structural Steel Installation | Task Dependent | Completed | Retail District | Luxury Resort Build | Infrastructure | Foundations | AST-79758 | SG1-5 | SG2-4 | PH-112 | Development | East Precinct | Non-Core | 2024-05-04 | 2024-10-14 | 2024-03-27 | 2024-06-07 | 2024-04-09 | 2024-06-11 | Board approval granted for progression to next phase. | 25.8 | 2024-08-28 | ML-1280 | Completion of Structural Frame | 2024-07-13
PRJ-1832-ACT-0092 | PRJ-1832 | Actual Construction | Electrical Cable Routing | Resource Dependent | Not Started | Hospitality District | Luxury Resort Build | MEP Works | Utilities | AST-41877 | SG1-2 | SG2-3 | PH-182 | Development | North Precinct | Non-Core | 2026-06-18 | 2026-10-17 | 2026-05-28 | 2026-10-26 | 2026-05-31 | 2026-10-29 | Board approval granted for progression to next phase. | 55 | 2026-09-16 | ML-7213 | Authority Inspection Clearance | 2026-11-22
PRJ-1565-ACT-0093 | PRJ-1565 | Pre-Work | Structural Steel Installation | Milestone | Not Started | Sports District | Water Park Development | MEP Works | Facade | AST-16102 | SG1-1 | SG2-3 | PH-656 | Development | South Precinct | Non-Core | 2026-09-30 | 2027-02-09 | 2026-08-12 | 2026-11-28 | 2026-09-01 | 2026-11-28 | Design freeze confirmed and procurement initiated. | 66.3 | 2026-12-23 | ML-1256 | Substantial Completion Achieved | 2026-12-11
PRJ-1601-ACT-0094 | PRJ-1601 | Pre-Work | Commissioning & Testing | Milestone | Completed | Hospitality District | Theme Park Expansion | Infrastructure | Internal Fitout | AST-40427 | SG1-1 | SG2-3 | PH-506 | Central Ops | North Precinct | Non-Core | 2024-10-17 | 2025-04-03 | 2024-10-20 | 2025-07-03 | 2024-10-22 | 2025-07-12 | Design freeze confirmed and procurement initiated. | 36.5 | 2024-11-21 | ML-8381 | Authority Inspection Clearance | 2025-08-12
PRJ-1233-ACT-0095 | PRJ-1233 | Pre-Work | Structural Steel Installation | Resource Dependent | Not Started | Retail District | Water Park Development | MEP Works | Facade | AST-57277 | SG1-1 | SG2-1 | PH-105 | Central Ops | West Precinct | Non-Core | 2025-12-25 | 2026-08-21 | 2025-12-17 | 2026-11-24 | 2025-12-29 | 2026-12-07 | Construction readiness confirmed with contractor mobilized. | 80.8 | 2026-01-12 | ML-5419 | Facade Weather Tight Achieved | 2026-12-13
PRJ-1135-ACT-0096 | PRJ-1135 | Actual Construction | Structural Steel Installation | Resource Dependent | Not Started | Hospitality District | Luxury Resort Build | MEP Works | Foundations | AST-83339 | SG1-2 | SG2-5 | PH-633 | Strategic Delivery | West Precinct | Core | 2024-07-17 | 2025-03-27 | 2024-06-14 | 2024-11-15 | 2024-06-27 | 2024-11-29 | Stage Gate review completed with minor design comments. | 38.6 | 2024-08-09 | ML-3274 | Completion of Structural Frame | 2024-12-16
PRJ-1308-ACT-0097 | PRJ-1308 | Actual Construction | Mechanical Plant Room Setup | Resource Dependent | Not Started | Retail District | Water Park Development | MEP Works | Foundations | AST-27758 | SG1-3 | SG2-1 | PH-505 | Central Ops | West Precinct | Non-Core | 2025-06-28 | 2026-03-22 | 2025-06-29 | 2026-05-09 | 2025-07-03 | 2026-05-11 | Design freeze confirmed and procurement initiated. | 51 | 2025-07-17 | ML-8212 | Facade Weather Tight Achieved | 2026-06-01
PRJ-1440-ACT-0098 | PRJ-1440 | Actual Construction | Water Feature Testing | Milestone | Completed | Retail District | Water Park Development | Landscape | Internal Fitout | AST-46739 | SG1-4 | SG2-3 | PH-216 | Strategic Delivery | South Precinct | Core | 2024-11-03 | 2025-03-30 | 2024-09-25 | 2025-04-17 | 2024-10-05 | 2025-05-06 | Milestone achieved ahead of schedule. | 96.6 | 2025-01-23 | ML-8563 | MEP Rough-In Completion | 2025-07-05
PRJ-1725-ACT-0099 | PRJ-1725 | Actual Construction | Facade Panel Installation | Resource Dependent | Not Started | Retail District | Luxury Resort Build | MEP Works | Utilities | AST-76402 | SG1-4 | SG2-5 | PH-137 | Central Ops | North Precinct | Core | 2025-03-16 | 2026-01-10 | 2025-02-24 | 2025-12-12 | 2025-03-05 | 2025-12-14 | Milestone achieved ahead of schedule. | 29 | 2025-04-24 | ML-5067 | MEP Rough-In Completion | 2026-01-25
PRJ-1680-ACT-0100 | PRJ-1680 | Pre-Work | Landscape Hardscape Installation | Milestone | Completed | Sports District | Luxury Resort Build | Landscape | Internal Fitout | AST-70694 | SG1-5 | SG2-5 | PH-254 | Central Ops | North Precinct | Non-Core | 2025-12-15 | 2026-08-21 | 2025-12-08 | 2026-05-03 | 2025-12-28 | 2026-05-22 | Design freeze confirmed and procurement initiated. | 6 | 2026-02-19 | ML-2712 | Completion of Structural Frame | 2026-06-09