## Sheet1
Activity ID | Project ID | Prog Version | Activity Name | Activity Type | Activity Status | District | Development | Class L1 ID | Class L2 ID | Asset | Project Status | Stage Gate L1 ID | Stage Gate L2 ID | Phase | Business Class | Precinct | Core Assets | Start Date | End Date | SG-Summary | QIC-BOD PC | QIC-BOD PC-Date | QIC-BOD-ML-ID | QIC-BOD-ML-DES | QIC-BOD-ML-Date
D13-LPR-1304-17340 | IMS-D13-2026-01-FC-001.00 | Current | Summary - Cost Plan (2.E) | TT_Task | TK_NotStart | 37475 | 75770 | 289428 | 293653 | 147855 | 256836 | 75825 |  | 75979 | 145767
D05-WRPB-SG3-3F-900 | IMS-S&R-2025-03-BL-001.00 | BL | Cost Plan (3.F) | TT_Task | TK_NotStart | 38239 | 75771 |  |  | 144041 |  | 75834 | 75902 |  |  |  | 75769
D11-EDU-1102-10150 | IMS-D11-2024-12-BL-001.00 | BL | Summary - Feasibility Model (2.B) | TT_Task | TK_NotStart | 38241 | 75771 |  |  | 108126 |  | 75833 | 75893 |  | 145767 |  | 75769
D18-RES-057-P11-1560 | IMS-D18-PH2-2026-01-FC-001.00 | Current | Summary - Legal Report (2.L) | TT_Task | TK_NotStart | 79108 | 75771 | 293641 | 295888 | 257098 | 295882 | 295545 |  | 82603 | 145229 |  | 75769
D05-MOT-AD0017-SG4-106 | IMS-D05-2026-01-FC-001.NA | Current | Summary - Concept Design Report - Interior (4.B) | TT_Task | TK_NotStart | 38239 | 75771 | 297445 | 297446 | 297465 | 295882 | 75835 | 76020 |  | 145232 |  | 17774
D03-REL-0303-11350 | IMS-D2&3-2025-12-BL-002.00 | BL | Summary - Review & Approval (SG2) | TT_Task | TK_NotStart
D15-REL-1502-10870 | IMS-D15-2024-12-BL-001.00 | BL | Summary - Risks & Opportunities Register (3.K) | TT_Task | TK_NotStart | 38235 | 75771 |  |  | 88654 |  | 75834 | 76052 |  | 145767 |  | 75769
D02-RES-0202-28010 | IMS-D02&03-2026-01-FC-001.00 | Current | Summary - Cost Plan (3.G) | TT_Task | TK_NotStart | 293657 | 75771 | 293641 | 295887 | 293702 | 256836 | 295546 |  | 82612 | 145229 |  | 75769
D02-WRPP-SG7-7B-100 | IMS-S&R-2026-01-FC-001.00 | Current | Summary - Business Plan (7.B) | TT_Task | TK_NotStart | 293657 | 75771 | 293640 | 293681 | 274790 |  | 295550 | 75814 | 88529 | 145767 |  | 75769
D12-ENT-0000-10760 | IMS-D12-2025-11-FC-001.00 | Pre | Summary - Asset Development Stage Gate 7: Completion | TT_WBS | TK_NotStart | 80321 | 75771 |  |  | 82187 | 256836 | 75838 | 75990 |  | 145232 | 82180 | 75769
D11-RES-111C-11080 | IMS-D11-2025-11-FC-001.00 | Pre | Summary - Review & Approval (SG6) | TT_Task | TK_NotStart | 38241 | 75771 |  |  | 85803 | 256836 | 75837 | 75907 | 75981 | 145229 |  | 75769
D12-FAC-0000-39550 | IMS-D12-2025-03-BL-001.01 | BL | Summary - Asset Development Stage Gate 1: Strategy Brief | TT_WBS | TK_Complete | 80321 | 75771 |  |  | 82224 |  | 75832 | 75987 |  | 145232 | 82178 | 75769
D03-LPR-0301-10290 | IMS-D03-2024-12-BL-001.00 | BL | Summary - Review & Approval (SG3) | TT_Task | TK_NotStart | 38240 | 75770 |  |  | 100487 |  | 75826 | 75863 |  | 145767
D12-DEV-MDU-066 | IMS-S&R-2025-11-FC-001.00 | Pre | D12 - Security Operations Centre | TT_Task | TK_Active
D00-UT-ICT-MMR4-SG1-1320 | IMS-D24-2025-01-BL-001.00 | BL | Summary - Review & Approval (SG1) - MMR4 | TT_Task | TK_NotStart
D14-LDP-1401-10010 | IMS-D14-2026-01-FC-001.00 | Current | Master Dev/Infra/Asset BU Committee Review & Approval (SG4) | TT_Task | TK_NotStart | 38238 | 75770 | 293636 | 293654 | 274711 |  | 75831 |  | 274684 | 145767 | 274740
DXX-HOS-AD504-GR-100 | IMS-TBC-2026-01-FC-001.NA | Current | Overall Summary - Economy Hotel (HOS_40) | TT_WBS | TK_NotStart | 147317 | 75771 | 293652 | 295603 | 297579 | 295882 | 75791 |  |  | 145228 |  | 17774
D10-RES-0000-SG2-15680 | IMS-D10-2026-01-FC-001.00 | Current | Summary - Contractor Procurement Strategy (2.H) | TT_Task | TK_Active | 38237 | 75771 | 293652 | 297430 | 85904 | 256836 | 295545 |  |  | 145232 | 85875 | 75769
D09-FMA-9C02-10020 | IMS-CA-FM-2026-01-FC-001.00 | Current | Summary - Develop Own Operate Model (1.B) | TT_Task | TK_NotStart | 38233 | 75771 | 293640 | 295570 | 87421 |  | 295544 | 75883 |  | 145767 | 87370 | 75769
D05-LDP-LP0118-SG3-113 | IMS-D05-2026-01-FC-001.NA | Current | Development Committee Review & Approval (SG3) | TT_Task | TK_NotStart | 38239 | 75770 | 293636 | 293654 | 297447 | 295882 | 75974 |  |  | 145767
D00-TBU-QMM-SG7-150 | IMS-TRN-BU-2026-01-FC-001.00 | Current | Summary - Business Plan (7.B) | TT_Task | TK_NotStart | 102118 | 75771 | 297024 | 297030 | 289570 | 256836 | 295550 |  |  | 145760 |  | 75769
D17-CDSA-SG1-1A-900 | IMS-S&R-2025-11-FC-001.00 | Pre | Strategy Brief (1.A) | TT_Task | TK_Complete | 106083 | 75771 |  |  | 144034 | 256836 | 75832 | 75884 |  | 145767 |  | 75769
D03-EDU-0303-SG4-14050 | IMS-CA-ED-2026-01-FC-001.00 | Current | Summary - Regulatory Approvals (4.M) | TT_Task | TK_NotStart | 293657 | 75771 | 293640 | 295541 | 100513 |  | 295547 |  |  | 145767 |  | 75769
D18-RES-058-P11-3510 | IMS-D18-PH2-2026-01-FC-001.00 | Current | Asset BU Committee Review & Approval (SG7) | TT_Task | TK_NotStart | 79108 | 75771 | 293641 | 295888 | 257099 | 295882 | 295550 |  | 82603 | 145229 |  | 75769
D10-POSN-SG5-010 | IMS-S&R-2025-11-FC-001.00 | Pre | Summary - Stage Gate 5: Detailed Design | TT_WBS | TK_NotStart | 38237 | 75771 |  |  | 144063 | 256836 | 75836 | 75992 |  | 145767 |  | 75769
AW-IDS-6080 | IMS-D10-2025-11-FC-001.00 | Pre | STAGE 4 - Schematic Design Complete (5) | TT_FinMile | TK_NotStart | 38237 | 75771 |  |  | 85935 | 256836 | 75835 |  |  | 145232 | 85874 | 17774
D10-RES-0000-03050 | IMS-D10-2025-11-FC-001.00 | Pre | Summary - Stage Gate 1: Strategy Brief | TT_WBS | TK_Complete | 38237 | 75771 |  |  | 85929 | 256836 | 75832 | 75987 |  | 145232 | 85875 | 75769
D18-RES-062-P12-2180 | IMS-D18-PH2-2026-01-FC-001.00 | Current | Summary - Business Plan (4.C) | TT_Task | TK_NotStart | 79108 | 75771 | 293641 | 295887 | 257103 | 295882 | 295547 |  | 82602 | 145229 |  | 75769
D18-SEC-008-P01-3000 | IMS-D18-PH1-2024-12-BL-001.00 | BL | Summary - Review & Approval (SG5) | TT_Task | TK_NotStart | 79108 | 75771 |  |  | 257028 |  | 75836 | 75914 | 75981 | 145767 | 82497 | 75769
D03-SEC-0303-10010 | IMS-D03-2024-12-BL-001.00 | BL | Summary - Stage Gate 7: Completion Summary | TT_WBS | TK_NotStart | 38240 | 100529
D09-HOS-126-P01-4920 | IMS-D09-2026-01-FC-001.00 | Current | Summary - Business Plan (5.C) | TT_Task | TK_NotStart | 38233 | 75771 | 293652 | 295603 | 143266 | 256836 | 75836 | 76021 | 75981 | 145228 | 87371 | 17774
D12-RES-0000-16970 | IMS-D12-2025-03-BL-001.01 | BL | Summary - Asset Development Stage Gate 1: Strategy Brief | TT_WBS | TK_Complete | 80321 | 75771 |  |  | 82193 |  | 75832 | 75987 |  | 145232 | 82179 | 17774
D00-UT-SW-WTS.S-SG5-1060 | IMS-D24-2025-01-BL-001.00 | BL | Summary - Completion (5.D) - WTS (Southern) | TT_Task | TK_NotStart
D18-LS-PH2-SG3-300 | IMS-D18-PH2-2026-01-FC-001.00 | Current | Summary - Business Plan (3.B) | TT_Task | TK_NotStart | 79108 | 75770 | 289428 | 293653 | 256979 | 295882 | 75826 |  | 75980 | 145767
D18-RES-063-P12-1150 | IMS-D18-PH2-2024-12-BL-001.00 | BL | Summary - Review & Approval (SG1) | TT_Task | TK_NotStart | 79108 | 75771 |  |  | 257104 |  | 75832 | 75880 | 82602 | 145229 |  | 75769
D03-EDU-0302-11450 | IMS-D2&3-2025-12-BL-002.00 | BL | Summary - Initial Project Execution Plan (2.H) | TT_Task | TK_NotStart
D18-LUT-003-P01-1570 | IMS-D18-PH1-2024-12-BL-001.00 | BL | Summary - Development Program (1.C) | TT_Task | TK_Complete | 79108 | 75770 |  |  | 256916 |  | 75824 | 75852 | 75981 | 145767 | 82490
D03-EDU-0301-SG6-14810 | IMS-CA-ED-2026-01-FC-001.00 | Current | Summary - Financial model (6.D) | TT_Task | TK_NotStart | 293657 | 75771 | 293640 | 295541 | 100478 |  | 295549 |  |  | 145767 |  | 75769
D24-ENT-0019-12310 | IMS-D24-2025-11-FC-001.00 | Pre | Summary - Operations Strategy (6.L) | TT_Task | TK_NotStart | 106078 | 75771 |  |  | 141764 | 256836 | 75837 | 76083 | 75981 | 145233 | 236004 | 17774
D15-EDU-1506-10710 | IMS-CA-ED-2026-01-FC-001.00 | Current | Summary - Concept Design Report – Exterior (3.A) | TT_Task | TK_NotStart | 38235 | 75771 | 293640 | 295541 | 88690 |  | 295546 |  | 88528 | 145767 |  | 75769
D00-UT-PWR-PSS31-SG3-1100 | IMS-UT-2025-03-BL-001.00 | BL | Summary - Stage Gate 3: Detailed Design | TT_Task | TK_NotStart | 102118 | 75770 |  |  | 141757 |  | 75826 |  | 76175 | 145767 | 82490
D2&3-SOC-MPB-SG5-300 | IMS-CA-SOL-2026-01-FC-001.00 | Current | Summary - Regulatory Approvals (5.M) | TT_Task | TK_NotStart | 293657 | 75771 | 293640 | 295579 | 100498 |  | 295548 |  |  | 145767 |  | 75769
D18-DSOC-SG3-900 | IMS-S&R-2025-03-BL-001.00 | BL | Summary - Review & Approval (SG3) | TT_Task | TK_NotStart | 79108 | 75771 |  |  | 257028 |  | 75834 | 75898 |  |  |  | 75769
D18-ENT-001-P01-3710 | IMS-D18-PH1-2026-01-FC-001.00 | Current | Summary - Regulatory Approvals (3.M) | TT_Task | TK_NotStart | 79108 | 75771 | 295582 | 295586 | 295606 | 256836 | 75834 |  | 75981 | 145232 | 82498 | 17774
D18-HOS-037-P01-1430 | IMS-D18-PH1-2026-01-FC-001.00 | Current | Summary - Pre-Concept Design Report - Exterior (2.D) | TT_Task | TK_Active | 79108 | 75771 | 293652 | 295603 | 289519 | 256836 | 75833 |  | 75981 | 145228 | 82497 | 17774
D06-DSOC-SG3-3J-900 | IMS-S&R-2026-01-FC-001.00 | Current | Summary - Project Execution Plan (3.L) | TT_Task | TK_NotStart | 38236 | 75771 | 293640 | 293681 | 143986 |  | 295546 | 75899 | 88529 | 145767 |  | 75769
D18-RES-037-P09-2570 | IMS-D18-PH2-2024-12-BL-001.00 | BL | Summary - Detailed Design Report (5.A) | TT_Task | TK_NotStart | 79108 | 75771 |  |  | 257078 |  | 75836 | 75917 | 82606 | 145229 |  | 75769
D16-SPO-0012-10110 | IMS-D16-2026-01-FC-001.00 | Current | Summary - Overarching Strategy (1.A) | TT_Task | TK_Complete | 143959 | 75771 | 293637 | 293655 | 274724 | 256836 | 75832 | 76002 | 75981 | 145233 |  | 17774
D01-HOS-AD0408-SG1-200 | IMS-D01-2026-01-FC-001.NA | Current | Summary - Overarching Strategy (1.A) | TT_Task | TK_NotStart | 38231 | 75771 | 293652 | 295603 | 297400 | 295882 | 75832 | 76002 |  | 145228 |  | 17774
D09-WRPB-SG4-4A-900 | IMS-S&R-2025-03-BL-001.00 | BL | Schematic Design Report (4.A) | TT_Task | TK_NotStart | 38233 | 75771 |  |  | 87408 |  | 75835 | 75897 |  |  |  | 75769